## Retail Audit Web App
| Retail Audit Application |  | 2018-08-29
Wednesday
Sl. No. | Module | Man Hours | Man Days |  | No | Man Days | Total Effort
| WEB APPLICATION |  |  | Designer UI | 1 | 4 | 4
1 | Analysis and Planning | 12 | 1.5 | Designer HTML | 1 | 4 | 4
2 | SRS | 20 | 2.5 | Sr Developer | 1 | 10 | 10
3 | Functional Specification | 20 | 2.5 | Jr Developer | 1 | 26 | 26
4 | HTML Prototype | 32 | 4 | Android App | 1 | 19 | 19
6 | Development and Production |  |  | PM | 1 | 0 | 0
7 | Set up development environment and server - php codeigniter | 0 | 0 | BA | 1 | 1.5 | 1.5
8 | Super Admin - |  |  | Tech writer | 1 | 5 | 5
9 | Dashboard | 4 | 0.5 | QA | 1 | 15 | 15
10 | Manage Roles & Permissions | 8 | 1 | Total |  |  | 84.5
11 | Manage Users | 8 | 1
12 | Master Management |  |  | Total Delivery days | 51.5
| Products | 10 | 1.25 | Total Effort | 84.5 | (+1 Day deployment)
| Retailers (sub items like route map, route master, contact etc..) | 36 | 4.5
| Country, Region | 4 | 0.5
| Shops | 6 | 0.75
| Users (Auditor) | 6 | 0.75
| Shops Products upload (No subcategories - direct SKU) | 6 | 0.75
| Create Shop Template | 12 | 1.5
13 | Audit Schedule | 32 | 4
| Audit Analytics | 24 | 3
14 | Reports (3) | 76 | 9.5
39 | Mobile API | 56 | 7
40 | Testing and training |  | 0
41 | Test for full functionality on all major and active browsers | 64 | 8
40 | PM | 20 | 2.5
42 | Total | 456 | 57
Assumptions
Languages : English only
Template will be purchased by the client

## Mobile -Android
| Retail Audit Application |  | 2018-09-18
# | Module | Hours | Man Days
Ui Design
| Page Design in XML | 70 | 8.75
| Page Desing in Photoshohp | 32 | 4
Development
1 | Basic Setup | 8 | 1
2 | Splash Screen | 1 | 0.125 | Android Development |  | 18.875
3 | Login | 1 | 0.125 | Design (Photoshop) |  | 4
4 | Home Screen | 1 | 0.125 | Testing |  | 7.125
5 | Trade Coverage Listing page | 6 | 0.75
6 | Profile | 2 | 0.25 |  | Total(Days) | 30
7 | Dashboard | 1 | 0.125
8 | Availability | 4 | 0.5
9 | Price Check | 2 | 0.25
10 | Comptetitor Tracking | 6 | 0.75
11 | Planogram | 2 | 0.25
12 | Promotion | 6 | 0.75
13 | Survey | 6 | 0.75
14 | Call Analysis | 4 | 0.5
15 | New Retailer | 3 | 0.375
16 | Logout | 1 | 0.125
17 | Popup and alerts | 4 | 0.5
Api Integration
| Api integration | 23 | 2.875
Testing
| testing | 57 | 7.125
| Total effort |  | 30
Mobile Portrait mode only
Consider only online mode
It will support Kitkat and above