## Print Management
Print Management | March 10 2017 | March 10 2017
| Friday | Friday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 24 | 3 | Designer | 1 | 40 | 5 | 5
Functional Specification | 24 | 3 | Sr Developer | 1 | 232 | 29 | 29 | 57.75 | 58
Project Management | 46.2 | 5.775 | Jr Developer | 1 | 232 | 29 | 29
Graphic Design | 32 | 4 | PM | 1 | 46.2 | 11.775 | 11.775
Development |  | 0 | QA | 2 | 77.3 | 9.6625 | 19.325
Operation Module (Supervisor) |  | 0 | Total |  | 627.5 |  | 94.1 | 752.8
Item Master | 6 | 0.75
Minimum Qty Notification | 6 | 0.75 | Total Delivery days | 43.6625
Minimum Qty Notification Scheduler | 6 | 0.75 | Total Man day Effort | 94.1
Source File Upload (Manual) | 4 | 0.5
File format check | 8 | 1
Source File Upload (Scheduled) | 6 | 0.75
Source File 3rd party integration | 12 | 1.5
Order Submission Single record | 6 | 0.75
Order Submission Batches | 12 | 1.5
Release to production Order Pools | 6 | 0.75
Production Module (Operator) |  | 0
Order Pooling (new , reprint) | 8 | 1
View Orders in Pool | 4 | 0.5
Identify System Errors | 6 | 0.75
System Error correction | 6 | 0.75
Send system error records to Operator | 6 | 0.75
Create Material request | 8 | 1
Print Orders | 6 | 0.75
Update production log : Uncompleted Jobs | 6 | 0.75
Update production log : Update machine readings | 6 | 0.75
Update production log : Generate QC Reports | 8 | 1
Update production log : Attach QC Reports | 6 | 0.75
Update production log : Scan Damaged Items | 12 | 1.5
Update production log : Update QC results for Manual checked samples | 6 | 0.75
Tag Damaged items to be returned to store keeper | 6 | 0.75
Tag unused items to be returned to storekeeper (after shipping) | 6 | 0.75
Inventory Manager (Store Keeper) |  | 0
Receive Items and update inventpry (from Client / Supplier) | 6 | 0.75
Receive Items and update inventpry (from Operator / QC) | 6 | 0.75
Review Material Request raised by Operators | 6 | 0.75
Release material request | 6 | 0.75
Print Material Release form | 6 | 0.75
Scan Material release form | 6 | 0.75
Update Inventory | 4 | 0.5
Quality Check |  | 0
QC Printed Orders | 8 | 1
Indicated Orders that are Qced, defective orders with comments | 8 | 1
Update QC Report | 6 | 0.75
Upload Scans of defective orders | 8 | 1
Send scans to Supervisor to process | 4 | 0.5
Shipping |  | 0
View Ready to Dispatch orders | 4 | 0.5
Consolidate orders and create reference number and delivery type | 6 | 0.75
Generate Airway billing number using courier API | 8 | 1
Generate 3rd party shipment creation file | 6 | 0.75
import airway bill number from 3rd party shipping companies | 6 | 0.75
Scan returned shipments | 8 | 1
Customer Portal |  | 0
View status of order (Released, printed,dispatched, shipped) | 8 | 1
View Production log | 4 | 0.5
View Airwaybill no | 4 | 0.5
Link to respective courier's shipment portal | 6 | 0.75
Admin |  | 0
Manage Users | 6 | 0.75
Item Master | 6 | 0.75
Configure Printers | 6 | 0.75
Configure Scanners | 6 | 0.75
Configure 3rd party Shippers and portal links | 6 | 0.75
Manage System errors | 6 | 0.75
Manage Logs | 6 | 0.75
Configure email | 6 | 0.75
System Features |  | 0
Auditing, Logging | 6 | 0.75
Exception Handling | 6 | 0.75
Authentication, Authorization | 8 | 1
Courier Integration (DHL, ARAMEX) | 12 | 1.5
3rd Party Integration (File transfer) | 12 | 1.5
Read XML, CSV | 12 | 1.5
Driver Integration for printing | 12 | 1.5
Driver Integration for scanning documents | 12 | 1.5
Database Services | 8 | 1
Services Layer | 8 | 1
Workflow | 12 | 1.5
0
0
0
0
Testing & Deployment
Testing | 138.6 | 17.325
UAT | 16 | 2
Deployment | 8 | 1
Total Effort | 750.8 | 93.85