## RFP Gateway
| RFP Gateway |  | 2020-11-06
Thursday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 4 | 4
1 | Business analysis | 32 | 4 | Sr Developer | 1 | 29 | 29 | 33.25 | 81.05 | 73.75 | 74
2 | Project Management | 56.4 | 7.05 | Jr Developer | 1.5 | 30 | 45
3 | SRS,FS,User Manual | 16 | 2 | PM | 1 | 7.05 | 7.05
4 | Design and Prototype | 32 | 4 | BA | 1 | 4 | 4
| Development |  |  | Tech writer | 1 | 2 | 2
5 | Application basic setup | 8 | 1 | QA | 1.5 | 20.0167 | 30.025
| Council Module |  |  | Total |  | 96.0667 | 121.075
| Registration | 6 | 0.75
| Sign in / remember pw, forgot pw | 6 | 0.75 | Effort | 121.075 | + 1 Day (Deployment)
| Manage Category /Sub category Masters (Add/Edit/Delete) | 6 | 0.75 | Delivery Time | 67.0667 | + 1 Day (Deployment)
| Dashboard |  | 0
| Corporations and MBE’s Registration - Approval/Rejection/Request more details | 8 | 1
| View Registration status | 4 | 0.5
| Corporations and MBE’s Profile Updates- Approval/Rejection/Request more details | 8 | 1
| View all existing Corporations and MBE’s | 4 | 0.5
| Enable / Disable Corporations and MBE’s | 4 | 0.5
| View & Send messages to Corporations & MBEs | 6 | 0.75
| Search functionality based on all available filters | 8 | 1
| Manage Annual Subscription of Corporations and MBE’s | 8 | 1
| View Reports & Analytics based on: |  | 0
| Total number of RFPs | 4 | 0.5
| Number of RFPs floated by each corporation | 4 | 0.5
| Numbers of Quotes received/declined for each RFP | 4 | 0.5
| Numbers of Response received for each RFP | 4 | 0.5
| Award details of each RFP | 4 | 0.5
| Search by category, sub category, supplier etc. | 4 | 0.5
| Demographic Analysis based on fields captured in enrollment process | 4 | 0.5
| Trend Analysis over time | 12 | 1.5
| Projection Demand Survey for corporations based on category | 12 | 1.5
| Notifications and Alerts | 12 | 1.5
Corporations Module
| Sign Up/Register |  | 0
| Fill the basic details | 6 | 0.75
| Select Council | 2 | 0.25
| Select Category/Sub Category of services required | 2 | 0.25
| Select Subscription Model and make payment (if any) | 2 | 0.25
| Submit for Approval | 4 | 0.5
| Sign in / remember pw, forgot pw | 8 | 1
| Dashboard |  | 0
| View Published RFPs | 4 | 0.5
| View and Manage quotes received from MBEs | 4 | 0.5
| Award RFP | 4 | 0.5
| View & Send Message to MBE & Council | 6 | 0.75
| View Statuses | 2 | 0.25
| View Closing Date & Time | 2 | 0.25
| Search Functionality with all available filters | 12 | 1.5
| View/Update Profile | 6 | 0.75
| Manage RFPs |  | 0
| Create/Save as Draft RFPs with all required details | 6 | 0.75
| Select Category/ Sub category of the RFP | 2 | 0.25
| Upload RFP attachments and documents | 12 | 1.5
| Publish RFP |  | 0
| Notifications and Alerts | 4 | 0.5
| Fill and submit Demand Projection Survey (predefined) | 12 | 1.5
| View Reports & Analytics | 12 | 1.5
Minortity Business Enterprises(MBE) Module
| Sign Up/Register | 8 | 1
| Fill the basic details | 6 | 0.75
| Select Council | 6 | 0.75
| Select category/sub category of products / services rendered | 4 | 0.5
| Select Subscription Model and make payment (if any) | 4 | 0.5
| Submit for Approval | 4 | 0.5
| Sign in / remember pw, forgot pw | 8 | 1
| Dashboard |  | 0
| Search & View New RFPs | 8 | 1
| Download/ Print RFP details | 4 | 0.5
| Create Quote | 6 | 0.75
| Upload proposal documents and attachments | 4 | 0.5
| Submit Quote | 4 | 0.5
| View & Send Message to Corporation & Council | 8 | 1
| View all Submitted RFPs | 6 | 0.75
| View Quote History | 6 | 0.75
| Search Functionality with all available filters | 6 | 0.75
| View/Update Profile | 6 | 0.75
| Notifications and Alerts | 12 | 1.5
| View Reports & Analytics | 12 | 1.5
Admin Module
| Manage Regions (Add/Edit/Delete) | 6 | 0.75
| Manage Councils | 8 | 1
| Manage MBE | 4 | 0.5
| Mnaage Corporations | 4 | 0.5
| Notifications and Alerts | 6 | 0.75
| Maintain Roles and access | 8 | 1
| View Usage & statistics. | 8 | 1
| Monitor pending approvals | 4 | 0.5
| LMS Integration (APIs need to be provided to integrate) | 12 | 1.5
Security
| Protection against injection attacks (SQL, CRLF) | 6 | 0.75
| URL encoding, Input validation | 6 | 0.75
| Cookie Encryption, Cookie replay attacks | 6 | 0.75
| Session hijacking prevention | 6 | 0.75
| Cross site scripting and session management | 6 | 0.75
System
| Authentication, Authorization, Entitlements | 12 | 1.5
| Auditing & logging | 12 | 1.5
| Exception logging & error handling | 12 | 1.5
| Subscription management | 12 | 1.5
| Payment gateway Integration | 12 | 1.5
| Document management | 12 | 1.5
| Search engine | 12 | 1.5
| Reporting engine | 12 | 1.5
| Communication / Message management | 12 | 1.5
| SMS gateway integration | 18 | 2.25
Quality Assurance
| QA & Bug Fixing | 200.2 | 25.025
| UAT | 40 | 5
| Deployment per instance | 8 | 1
| Total Effort |  | 121.825
Assumptions
Only English language is considered
The effort may change after a detailed system Study