## AndroidDev
RMG |  | 2017-11-09
Module | Hours | Man Days
Initiation
Development
Mobile Design and Development
Basic Setup | 8 | 1
Splash Screen
Design and Development | 12 | 1.5
Login Page
Design,Development and api integration | 8 | 1
Registation page
Design,Development and api integration | 8 | 1
Sample Report selection page
Design,Development and api integration | 12 | 1.5
Contact us for Custom Report Generation
Design,Development and api integration | 4 | 0.5
View Our Sample Reports Detail page
Design,Development and api integration | 8 | 1
Chart integration with filter (30) | 48 | 6
Order your Report
Design, Development and api integration | 8 | 1
Table format integration with filter | 16 | 2
Filter Selection, show and filter integration with Api | 8 | 1
Chart integration with filter (30) | 24 | 3
Confirm Report
Design, Development and api integration | 8 | 1
Add to cart | 2 | 0.25
Filter integration with Api | 8 | 1
Cart
Design, Development and api integration | 8 | 1
Report Payment (Login/Guest) page
Design ,Development and api integration | 8 | 1
Payment Gateway
Payment gateway integration and Api intergration | 32 | 4
Api integration for email | 2 | 0.25
total effort |  | 29
Assumption
This application will support Sdk version 19(kitkat) and above
This application designed for tablets only.

## iOS
RMG | 2017-11-09
Module | Hours | Man Days
Initiation
Development
Mobile Design and Development
Basic Setup | 8 | 1
Splash Screen
Design and Development | 8 | 1
Login Page |  | 0
Design,Development and api integration | 12 | 1.5
Registation page |  | 0
Design,Development and api integration | 12 | 1.5
Sample Report selection page |  | 0
Design,Development and api integration | 16 | 2
Contact us for Custom Report Generation |  | 0
Design,Development and api integration | 16 | 2
View Our Sample Reports Detail page |  | 0
Design,Development and api integration | 8 | 1
Chart integration with filter (30) | 48 | 6
Order your Report |  | 0
Design, Development and api integration | 8 | 1
Filter Selection, show and filter integration with Api | 16 | 2
Table format integration with filter | 16 | 2
Chart format integration with filter (30) | 24 | 3
Confirm Report |  | 0
Design, Development and api integration | 20 | 2.5
Add to cart | 24 | 3
Filter integration with Api | 16 | 2
Cart |  | 0
Design, Development and api integration | 8 | 1
Report Payment (Login/Guest) page |  | 0
Design ,Development and api integration | 8 | 1
Payment Gateway |  | 0
Payment gateway integration and Api intergration | 32 | 4
Api integration for email | 4 | 0.5
0
0
0
0
total effort |  | 38