## Overall
| Development Effort | Total effort |  |  |  |  | Design | Reports | QA
Web | 80.75 | 73.2083 |  |  |  |  | 40 | 270 | Mobile API | QA
IOS | 38 | 55.4583 |  |  |  |  | API Generation -1 |  | 40
Android | 29 | 46.4583 |  |  |  |  | 40 |  | 60 | 60
| Total | 175.125
|  | No | Man hours | Man Days | Total Effort |  |  | 510 | Others
| Designer | 1 | 40 | 5 | 5 |  |  | Mobile design | Mobile development
| Sr.Developer | 1 | 142 | 17.75 | 17.75 | 486 | 446
| Jr Developer | 1 | 304 | 38 | 38
| IOS Developer | 1 | 304 | 38 | 38
| Android Developer | 1 | 232 | 29 | 29 | [5 empty] | 15 | [10 empty] | 157.75
| PM | 1 | 98.2 | 12.275 | 12.275
| QA | 3 | 93.6 | 11.7 | 35.1
| Total |  | 1213.8 |  | 175.125
| Total Delivery days | 85 | 78
| Total Man day Effort | 175.125 | 131.3438 | #VALUE! | #VALUE!
| 1899-12-31 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90
Web Design | 5 | bar: 175.125 2 to #VALUE! 5
API (RDA) | 5 | bar: 175.125 2 to #VALUE! 5
Mobile design |  | #VALUE! 6: 10 (IOS + Android)
Sample Reports |  | #VALUE! 6: 33 days (30 Charts)
IOS Views |  | #VALUE! 20: 15 (IOS Screen Design)
Android Views |  | #VALUE! 20: 15 (Android Screen Design)
Mobile API |  | #VALUE! 40: 5 (Mob View API)
Web Development |  | #VALUE! 45: 33 (Web Development)
IOS development |  | #VALUE! 36: 15 -20 days spread across 43 days
Android Development |  | #VALUE! 36: 15 -20 days spread across 43 days
QA |  | #VALUE! 75: Andoid
IOS
Web
Days | bar: 175.125 2 to #VALUE! 5
Web Design | Report (Charts) | 131.3438 3: Mobile API; #VALUE! 5: Web Development; #VALUE! 7: QA
5 | 33.75 | 131.3438 3: 5; #VALUE! 5: 33; #VALUE! 7: 5; #VALUE! 8: 10
API (ReportDataAccess) | Mobile Design (IOS + Android) | 175.125 2: Mobile View; 131.3438 3: Mobile Development; #VALUE! 6: QA
5 | 10 | 175.125 2: 23; 131.3438 3: 23; #VALUE! 6: 5

## IOS
RMG | 2017-11-09
Module | Hours | Man Days
Initiation
Development
Mobile Design and Development
Basic Setup | 8 | 1
Splash Screen
Design and Development | 8 | 1
Login Page |  | 0
Design,Development and api integration | 12 | 1.5
Registation page |  | 0
Design,Development and api integration | 12 | 1.5
Sample Report selection page |  | 0
Design,Development and api integration | 16 | 2
Contact us for Custom Report Generation |  | 0
Design,Development and api integration | 16 | 2
View Our Sample Reports Detail page |  | 0
Design,Development and api integration | 8 | 1
Chart integration with filter (30) | 48 | 6
Order your Report |  | 0
Design, Development and api integration | 8 | 1
Filter Selection, show and filter integration with Api | 16 | 2
Table format integration with filter | 16 | 2
Chart format integration with filter (30) | 24 | 3
Confirm Report |  | 0
Design, Development and api integration | 20 | 2.5
Add to cart | 24 | 3
Filter integration with Api | 16 | 2
Cart |  | 0
Design, Development and api integration | 8 | 1
Report Payment (Login/Guest) page |  | 0
Design ,Development and api integration | 8 | 1
Payment Gateway |  | 0
Payment gateway integration and Api intergration | 32 | 4
Api integration for email | 4 | 0.5
0
0
0
0
total effort | 304 | 38
38

## Android
RMG |  | 2017-11-09
Module | Hours | Man Days
Initiation
Development
Mobile Design and Development
Basic Setup | 8 | 1
Splash Screen
Design and Development | 12 | 1.5
Login Page
Design,Development and api integration | 8 | 1
Registation page
Design,Development and api integration | 8 | 1
Sample Report selection page
Design,Development and api integration | 12 | 1.5
Contact us for Custom Report Generation
Design,Development and api integration | 4 | 0.5
View Our Sample Reports Detail page
Design,Development and api integration | 8 | 1
Chart integration with filter (30) | 48 | 6
Order your Report
Design, Development and api integration | 8 | 1
Table format integration with filter | 16 | 2
Filter Selection, show and filter integration with Api | 8 | 1
Chart integration with filter (30) | 24 | 3
Confirm Report
Design, Development and api integration | 8 | 1
Add to cart | 2 | 0.25
Filter integration with Api | 8 | 1
Cart
Design, Development and api integration | 8 | 1
Report Payment (Login/Guest) page
Design ,Development and api integration | 8 | 1
Payment Gateway
Payment gateway integration and Api intergration | 32 | 4
Api integration for email | 2 | 0.25
total effort | 232 | 29
29
Assumption
This application will support Sdk version 19(kitkat) and above
This application designed for tablets only.

## Estimate Web
| RMG RL | Nov 10 2017
Friday
Sl. No. | Module | Man Hrs
Exploration and Discovery
1 | Create Use case
2 | Survey and freeze the proposed use case
3 | Conduct planning meetings to discuss and finalize project scope/details
7 | Design
8 | Create custome HTML theme based on purchased theme
9 | HTML Prototype -complete | 40
10 | Development and Production
11 | Set up development environment and server Codeigniter Framework + MySql
User Area
13 | Login & Registration | 8
| Home Page | 6
| Online Store | 16
14 | Top Programmes
15 | Time Slot Alanysis
16 | TG Perfomance
17 | Market Perfomance
| View Sample reports (30 charts) | 240
| Create Order & Save filters | 30
| Confirm Report | 20
Report Template
Select Frequency
Rate Card
| Shopping Cart | 16
| Payment Options | 10
| Payment Confirmation & Success | 12
| PDF Generation and Manage Email | 12
Admin
| User Management | 8
| Email Alerts | 8
| Rate Card Management | 8
| API Generation - API to access Data for Report | 40
| API Generation - Mobile View | 40
| Order creation -offline | 12
33 | Testing and training | 120
34 | Test for full functionality on all major and active browsers
35 | Conduct one-time training for site editing/updates/administration
36 | Launch
37 | Configure production server
38 | Deploy/transfer to production server
39 | Publish the Web site to Production Server
40 | Total | 646
80.75