## Employee Satisfaction Effort
Raviz Rewards Card | July 21 2017
Friday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 40 | 5 | 5
Functional Specification | 8 | 1 | Sr.Developer | 1 | 148 | 18.5 | 18.5 | 0 | 38
Project Management | 0 | 0 | Jr Developer | 1 | 156 | 19.5 | 19.5
Solutioning | 8 | 1 | PM | 1 | 24 | 3 | 3
Graphic Design (Android App + Web application) | 24 | 3 | QA | 2 | 2 | 0.25 | 0.5
Working Prototype | 16 | 2 | Total |  | 370 |  | 46.5 | 372
Development
web Admin |  |  | Total Delivery days | 24.75
Manage Picker (Assign Shift & Route) |  |  | Total Man day Effort | 46.5
Manage Floor Manager |  |  | Installation & training | 3
Script Admin
Load Dat files manually: Admin |  |  |  |  | Week1 | Week2 | week 3 | week4 | week5 | week6
Designer
Windows Service |  |  | Sr Developer
Load dat files, Location, customer and Prod files into staging tables (SQL bulk load or manual?) |  |  | Jr Developer
Identify Route, Bay, customer, pallet, truck, Item, Order, Pallete Type: move to prod tables |  |  | PM
Create logs for load files |  |  | QA
Create Assignments and link to routes
Honeywell Device (Picker App)
Splash screen
Login
Select Route
Assign Pallets or assignments to picker
Show Pallete Type
Show first item
Confirm item pick with cases picked
Show next item
Confirm total no of pallets picked for aassignment
Overide confirm by floor manager
Print sticker
Dashboard for floor manager
Testing & Deployment |  | 0
Testing | 0 | 0
UAT | 4 | 0.5
Deployment Support | 4 | 0.5
Total Effort | 72 | 9
Assumptions
Device/s and required SDK and Test cards will be provided by the client
Merchant ID and other required payment gateway details will be provided by the client
Required source code of the modules should be provided if it require integration with any existing application
Access to the database will be provided to update the payment transactions