## RentAny
RentAny Estimate |  | Oct 09 2018
Thursday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 32 | 4 | Designer | 1 | 120 | 15 | 15
Functional Specification | 32 | 4 | Web Developer | 1 | 500 | 62.5 | 62.5 | 0 | 113.5
Project Management | 0 | 0 | sr. developer | 1 | 408 | 51 | 51
Graphic Design | 80 | 10 | PM | 1 | 64 | 8 | 8
Working Prototype | 40 | 5 | QA | 2 | 2 | 0.25 | 0.5
Development |  |  | Total |  | 1094 |  | 137 | 1096
Web Site Features
Static Pages ( About, Contact Us, Help, Privacy, T&C, Careers, Blog , FAQ, How It Works) |  | 0 | Total Delivery days | 77.75
Home page categories of rental items, How it works |  | 0 | Total Man day Effort | 137
Common Features
Login via FB, G+ |  | 0
Create an Account (Renter & Lender) |  | 0
Login, forgot pw, remember pw, Change PW |  | 0
Modify Profile Lender (Email, Phone, Address, Surname, Add Picture), My Items, My Bookings, Notifications or messages |  | 0
Modify Profile Renter (Email, Phone, Address, Surname, Add Picture), My Items, My Bookings, Notifications or messages |  | 0
Renter Web App
Item Search with search options (Newest, Rated, Views, Images, Price, Distance) |  | 0
Search using Map (Map View) |  | 0
Live Search (See what others are searching and renting now) |  | 0
Item List /w image, rating, price, description |  | 0
Item detail page (Item rating, Item condition, Item Pickup, Item Detailed Description, Owner name, Owner image, owner rating, View Owner profile, Item on Map, Minimum rental time, Rent from date, Rent to date, Rental price, rental agreement, Check out now) |  | 0
Related items in Item details page (Does not Use AI in phase 1)
Leave Reviews for items and lender
Optional: Purchase insurance
Pay Security Deposit
Lender Web App
Create Item Listing(Title, Description, image, Age of Item, Estimated Value, Item Address, Item Category, Minimum rental period : hours, days, weeks or month, delivery Type, Hourly fee, weekly fee, monthly fee, yearly fee, rental agreement, Item Details, Owner details) |  | 0
Set availability of item (Monday - Sunday, Hours, as applicable) |  | 0
Item Condition report as applicable during Item creation: Overall condition, Exterior condition, repair details, Fiunctionality, cleanliness, item modifications, Additional comments) |  | 0
Security deposit requirments
System Features
Authentication & authorization |  | 0
Auditing & logging |  | 0
Exception handling |  | 0
Manage documents, images & directories |  | 0
Automatically make item unavailable if rented |  | 0
Image cleansing (Nude, Category varification etc. using image analysis libraries from amazon, Azure etc) |  | 0
Instant message lender (Offline) |  | 0
Instant message renter (Offline) |  | 0
Admin
Manage Users
Manage & Verify Items |  | 0
Verify images flagged by the system |  | 0
Manage rental agreement templates |  | 0
Verify Renter & lender via OTP |  | 0
Insurance Management of items |  | 0
Testing & Deployment
Testing | 0 | 0
UAT | 4 | 0.5
Deployment | 8 | 1
Total Effort | 196 | 24.5
Assumptions
References: http://rentangles.com, https://www.loanables.com, https://ruckify.com/, http://us.zilok.com/

## Sheet1
Features