## RentAny
RentAny Estimate |  | Oct 09 2018
Thursday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 24 | 3 | Designer | 1 | 104 | 13 | 13
Functional Specification | 24 | 3 | Web Developer | 1 | 224 | 28 | 28 | 42.75 | 43
Project Management | 34.2 | 4.275 | sr. developer | 1 | 120 | 15 | 15
Graphic Design | 8 | 1 | PM | 1 | 82.2 | 10.275 | 10.275
Working Prototype | 96 | 12 | QA | 2 | 53.3 | 6.6625 | 13.325
Development |  |  | Total |  | 583.5 |  | 79.6 | 636.8
Web Site Features
Static Pages ( About, Contact Us, Help, Privacy, T&C, Careers, Blog , FAQ, How It Works) | 32 | 4 | Total Delivery days | 47.6625
Home page categories of rental items, How it works | 12 | 1.5 | Total Man day Effort | 79.6
Common Features
Login via FB, G+ | 12 | 1.5 | Previous Effort for Web API & Mobile Apps
Create an Account (Renter & Lender) | 16 | 2 | Channel | Hours
Login, forgot pw, remember pw, Change PW | 8 | 1 | Web Development | 438
Modify Profile Lender (Email, Phone, Address, Surname, Add Picture), My Items, My Bookings, Notifications or messages | 16 | 2 | Android Mobile Development | 243
Modify Profile Renter (Email, Phone, Address, Surname, Add Picture), My Items, My Bookings, Notifications or messages | 16 | 2 | iOS Mobile Development | 250
Renter Web App |  |  | Web QA | 110
Item Search with search options (Newest, Rated, Views, Images, Price, Distance) | 12 | 1.5 | Android QA | 81
Search using Map (Map View) | 8 | 1 | iOS QA | 87
Live Search (See what others are searching and renting now) | 12 | 1.5 |  | 337
Item List /w image, rating, price, description | 12 | 1.5
Item detail page (Item rating, Item condition, Item Pickup, Item Detailed Description, Owner name, Owner image, owner rating, View Owner profile, Item on Map, Minimum rental time, Rent from date, Rent to date, Rental price, rental agreement, Check out now) | 24 | 3
Related items in Item details page (Does not Use AI in phase 1) | 24 | 3
Leave Reviews for items and lender | 4 | 0.5
Optional: Purchase insurance | 8 | 1
Pay Security Deposit | 8 | 1
Lender Web App
Create Item Listing(Title, Description, image, Age of Item, Estimated Value, Item Address, Item Category, Minimum rental period : hours, days, weeks or month, delivery Type, Hourly fee, weekly fee, monthly fee, yearly fee, rental agreement, Item Details, Owner details) | 32 | 4
Set availability of item (Monday - Sunday, Hours, as applicable) | 8 | 1
Item Condition report as applicable during Item creation: Overall condition, Exterior condition, repair details, Fiunctionality, cleanliness, item modifications, Additional comments) | 8 | 1
0
System Features
Authentication & authorization | 4 | 0.5
Auditing & logging | 4 | 0.5
Exception handling | 4 | 0.5
Manage documents, images & directories | 4 | 0.5
Automatically make item unavailable if rented | 4 | 0.5
Image cleansing (Nude, Category varification etc. using image analysis libraries from amazon, Azure etc) | 12 | 1.5
Instant message lender (Offline) | 4 | 0.5
Instant message renter (Offline) | 4 | 0.5
Admin
Manage Users | 4 | 0.5
Manage & Verify Items | 4 | 0.5
Verify images flagged by the system | 4 | 0.5
Manage rental agreement templates | 12 | 1.5
Verify Renter & lender via OTP | 6 | 0.75
Insurance Management of items |  | 0
Testing & Deployment
Testing | 102.6 | 12.825
UAT | 4 | 0.5
Deployment | 8 | 1
Total Effort | 642.8 | 80.35
Assumptions
References: http://rentangles.com, https://www.loanables.com, https://ruckify.com/, http://us.zilok.com/
Not included, This would require more details on the calculations
Insurance Management of items
Security deposit requirments

## Sheet1
Features