## Sprint
Sprint 1
Basic Setup | Web |  | Web API
Splash Screen
Login- Single Sign On Mechanism, auto password change/reset |  |  |  | Login
Happiness page - comment |  | Happiness Report |  | Happiness post
Dashboard |  | Dashboard |  | Dashboard
Logout |  |  |  | Logout
Unit test cases |  | Unit test |  | Unit test | Effort Estimate | Man Days
Sprint 2 |  |  |  |  | Android | 106.9125
News listing(News + videos) -news feed, filter news by dates, search news | Web | Add, edit, list & delete News | Web API | News list, filter by date, search news | IOS | 101.5125
News details page - add multiple images, interactive images |  |  |  | News details | Web App | 65.86
Vacancies listing |  | Add, edit, list & delete Vacancies |  | Vacancies listing | Web API | 18
Vacancies details page |  |  |  | Vacancies details | Total | 292.285
Benefits listing |  | Add, edit, list & delete Benefits |  | Benefits listing
benefits details page |  |  |  | Benefits details
Unit test cases |  | Unit test |  | Unit test
Sprint 3
Training listing | Web | Add, edit, list & delete Training | Web | Training List
Training details page |  |  |  | Training Details
Profile page |  |  |  | Profile Page
Profile search and review |  |  |  | Profile search and view
Survey listing and view |  | Add, edit, list & delete Survey |  | Survey listing and view
Notification list page |  |  |  | Notification list
Notification detail page |  |  |  | Notification detail
Unit test cases |  | Unit test |  | Unit test
Sprint 4
Innovation - post innovation, anonymous posting, comment, like, dislike, search by keyword |  | View and report |  | Innovation listing and post comment like, dislike search
Campaign listing page - General/special, pop up when closed |  | Add, Edit, List, Delete campaign |  | Campaign list
Special Campaign - list , post |  |  |  | Special Campaign list
Prescheduled posts |  | Notification to user
Unit test cases |  | Unit test |  | Unit test
Sprint 5
360 video player | Web |  | Web API
Private chat
Add Ethics hotline contact details |  | Update Ethics hotline contact details |  | Ethics hotline contact details
Google analytics
Unit test cases |  | Unit test |  | Unit test

## Android
SaadaConnect - Android
# | Modules | Hours | Days
|  |  |  | Activity | # | days | Total
| Ui Design |  |  | Design | 1 | 21 | 21
|  |  |  | Developer 1 | 1 | 45 | 45 | 66.375 | 66
| Page Design | 168 | 21 | Developer 2 | 0.5 | 42 | 21
|  |  |  | QA | 1 | 19.9125 | 19.9125
| Development |  |  |  |  | Total | 106.9125
| PHASE 1 |  |  | Delivery Days | 85.9125
1 | Basic Setup | 8 | 1 | total effort | 106.9125
2 | Splash Screen | 8 | 1
3 | Login- Single Sign On Mechanism, auto password change/reset | 6 | 0.75
4 | Happiness page - comment , generate report | 8 | 1 |  | 75
5 | News listing(News + videos) -news feed, filter news by dates, search news | 16 | 2
6 | News details page - add multiple images, interactive images | 20 | 2.5
7 | Vacancies listing | 4 | 0.5
8 | Vacancies details page | 4 | 0.5
9 | Benefits listing | 4 | 0.5
10 | benefits details page | 4 | 0.5
11 | Training listing | 4 | 0.5
12 | Training details page | 4 | 0.5
13 | Profile page | 8 | 1
14 | Profile search and review | 12 | 1.5
15 | Private chat | 40 | 5
16 | Google analytics | 12 | 1.5
17 | Add Ethics hotline contact details | 6 | 0.75
18 | Push notifications | 16 | 2
19 | Survey listing and view | 8 | 1
20 | Notification list page | 10 | 1.25
21 | Notification detail page | 6 | 0.75
22 | Innovation - post innovation, anonymous posting, comment, like, dislike, search by keyword | 40 | 5
23 | Campaign listing page - General/special, pop up when closed | 8 | 1
24 | Special Campaign - list , post | 8 | 1
25 | Logout | 4 | 0.5
PHASE 2
26 | Prescheduled posts | 8 | 1
27 | 360 video player | 24 | 3
Api Integration
| Api Integration | 87 | 10.875
Unit Test
| Unit test Cases | 144 | 18
Testing
| QA | 159.3 | 19.9125
| Total effort |  | 107.2875
Assumption
This application will support Sdk version 19(kitkat) and above, iOS 10 and above, iPhone 5s and above
This application designed for mobiles in portrait mode(video- landscape)
Video player details needed

## Web App
SaadaConnect
Sl. No | Web App Development | Design |  | Project Management | 1 | 4.08
|  | Hours | Man Days | Design | 1 | 6
| Initiation |  |  | Developer 1 | 1 | 20 | 40.8 | 40
1 | Requirements gathering and documentation | 4 | 0.5 | Developer 2 | 1 | 20
2 | Functional Specification | 8 | 1 | BA | 1 | 1.5
3 | Project Management | 32.64 | 4.08 | QA | 1 | 14.28
4 | Functional Prototype | 48 | 6 |  |  | 65.86
Design Development
Web Development
1 | Basic Setup | 4 | 0.5 | Delivery days | 40.28
| Phase 1 |  |  | Man Days | 65.86
2 | Report to measure the overall happiness | 8 | 1
3 | News
4 | Option to add multiple images/ videos | 12 | 1.5
5 | Vacancies
6 | Add, Edit, List & Delete | 24 | 3
7 | Benefits
8 | Add, Edit, List & Delete | 24 | 3
9 | Training feature to be added | 28 | 3.5
10 | Dashboard | 24 | 3
11 | Ethics Hotline contact details | 8 | 1
12 | Survey
13 | Add, Edit, List, Delete, | 16 | 2
14 | Report | 8 | 1
15 | Excel Export | 8 | 1
16 | Push Notification | 4 | 0.5
17 | Innovation
18 | View innovation | 8 | 1
19 | Reports | 8 | 1
20 | Campaigns
21 | Add, Edit, List, Delete, | 20 | 2.5
24 | Unit test | 40.8 | 5.1
Phase 2
22 | Pre scheduled posts | 20 | 2.5
23 | Integrate more systems with app | 48 | 6
24 | Unit test | 13.6 | 1.7
25 | QA | 114.24 | 14.28
| Total Effort | 533.28 | 66.66
Assumption & Dependancies
Integration with more system can be estimated based on the details of the systems to be integrated. Necessary details like integration document, test access and APIs will be provided by the client
Details of the training feature will be provided by the client
Vimeo account will be used for Video uploads
The performance of the upload will depend on the performance of the third party services like Vimeo and internet connectivity and speed

## Web Api
SaadaConnect
Sl. No | Web Api Development | Design
|  | Hours | Man Days
| Web Development |  |  | Project Management | 1 | 0
1 | Basic Setup | 4 | 0.5 | Design | 1 | 0
2 | Users login | 8 | 1 | Developer 1 | 1 | 9 | 18 | 18
3 | Happiness measurements | 4 | 0.5 | Developer 2 | 1 | 9
4 | News |  |  | BA | 1 | 0
5 | News feeds with the ability to scroll down to see older | 8 | 1 | QA | 1 | 0
6 | Filter the news by dates | 4 | 0.5 |  |  | 18
7 | Search option | 4 | 0.5
8 | User’s profiles
9 | View | 8 | 1 | Delivery days | 9
10 | Update | 4 | 0.5 | Man Days | 18
11 | Employees’ profiles search and review | 16 | 2
12 | Ethics Hotline contact details | 8 | 1
13 | Innovation
14 | Post an innovation | 8 | 1
15 | Users can comment, like, dislike | 8 | 1
16 | Search by keyword | 4 | 0.5
17 | Campaigns |  | 0
18 | General or Special campaigns | 24 | 3
19 | Post Campaign | 8 | 1
| Unit test | 24 | 3
| Total Effort | 144 | 18

## iOS
SaadaConnect - iOS
# | Modules | Hours | Days
| Ui Design |  |  | Activity | # | days | Total
|  |  |  | Design | 1 | 21 | 21
| Page Design | 168 | 21 | Developer 1 | 1 | 45 | 45 | 66.375 | 66
|  |  |  | Developer 2 | 0.5 | 42 | 21
| Development |  |  | QA | 1 | 14.5125 | 14.5125
| PHASE 1 |  |  |  |  | Total | 101.5125
1 | Basic Setup | 8 | 1 | Delivery Days | 80.5125
2 | Splash Screen | 8 | 1 | total effort | 101.5125
3 | Login- Single Sign On Mechanism, auto password change/reset | 6 | 0.75
4 | Happiness page - comment , generate report | 8 | 1
5 | News listing(News + videos) -news feed, filter news by dates, search news | 16 | 2
6 | News details page - add multiple images, interactive images | 20 | 2.5
7 | Vacancies listing | 4 | 0.5
8 | Vacancies details page | 4 | 0.5
9 | Benefits listing | 4 | 0.5
10 | benefits details page | 4 | 0.5
11 | Training listing | 4 | 0.5
12 | Training details page | 4 | 0.5
13 | Profile page | 8 | 1
14 | Profile search and review | 12 | 1.5
15 | Private chat | 40 | 5
16 | Google analytics | 12 | 1.5
17 | Add Ethics hotline contact details | 6 | 0.75
18 | Push notifications | 16 | 2
19 | Survey listing and view | 8 | 1
20 | Notification list page | 10 | 1.25
21 | Notification detail page | 6 | 0.75
22 | Innovation - post innovation, anonymous posting, comment, like, dislike, search by keyword | 40 | 5
23 | Campaign listing page - General/special, pop up when closed | 8 | 1
24 | Special Campaign - list , post | 8 | 1
25 | Logout | 4 | 0.5
PHASE 2
26 | Prescheduled posts | 8 | 1
27 | 360 video player | 24 | 3
Api Integration
| Api Integration | 87 | 10.875
Unit Test
| Unit test Cases | 144 | 18
Testing
| QA | 116.1 | 14.5125
| Total effort |  | 101.8875
Assumption
This application will support Sdk version 19(kitkat) and above, iOS 10 and above, iPhone 5s and above
This application designed for mobiles in portrait mode(video- landscape)
Video player details needed