## Estimates
SaadaConnect
Estimation for Web and Android Development
Total Effort | Man Days
Web App | 34
Web Api Dev | 15
SRS+FS | 1.5
Project Management | 2
QA | 13.6
UAT | 2
Deployment | 2
Total | 70.1
|  |  | No. | Man Days | Total Effort
|  | Designer | 0 | 0 | 0
|  | Project Management | 1 | 2 | 2
|  | Sr Developer(Android) | 1 | 5 | 5
|  | Jr Developer(Android) | 1 | 6 | 6
|  | Sr Developer(Web & API) | 1 | 26.5 | 26.5
|  | Jr Developer(Web & API) | 1 | 26.5 | 26.5
|  | SRS+FS | 1 | 1.5 | 1.5
|  | Sr. Tester | 1 | 5 | 5
|  | Jr. Tester | 1 | 3.4 | 3.4
|  | Total |  |  | 75.9
|  | Total Delivery Timeline | 43
|  | Total Effort | 75.9

## Web APP
| SaadaConnect |  | 2018-04-10
Sl. No | Web App Development | Design |  | Project Management | 1 | 2
|  | Hours | Man Days | Design | 1 | 6
| Initiation |  |  | Developer 1 | 1 | 25 | 49 | 49
1 | Requirements gathering and documentation | 4 | 0.5 | Developer 2 | 1 | 24
2 | Functional Specification | 8 | 1 | BA | 1 | 1.5
3 | Project Management | 16 | 2 | QA | 2 | 5.8625
4 | Functional Prototype | 48 | 6 |  |  | 64.3625
Design Development
Web Development
1 | Basic Setup | 4 | 0.5 | Delivery days | 35.8625
| Phase 1 |  |  | Man Days | 64.3625
2 | Report to measure the overall happiness | 8 | 1
3 | News
4 | Option to add multiple images/ videos | 12 | 1.5
5 | Vacancies
6 | Add, Edit, List & Delete | 24 | 3
7 | Benefits
8 | Add, Edit, List & Delete | 24 | 3
9 | Training feature to be added | 28 | 3.5
10 | Dashboard | 24 | 3
11 | Ethics Hotline contact details | 8 | 1
12 | Survey
13 | Add, Edit, List, Delete, | 16 | 2
14 | Report | 8 | 1
15 | Excel Export | 8 | 1
16 | Push Notification | 4 | 0.5
17 | Innovation
18 | View innovation | 8 | 1
19 | Reports | 8 | 1
20 | Campaigns
21 | Add, Edit, List, Delete, | 20 | 2.5
Phase 2
22 | Pre scheduled posts | 20 | 2.5
23 | Integrate more systems with app | 48 | 6
| Testing | 93.8 | 11.725
| Total Effort | 348 | 45.725
Assumption & Dependancies
Integration with more system can be estimated based on the details of the systems to be integrated. Necessary details like integration document, test access and APIs will be provided by the client
Details of the training feature will be provided by the client
Vimeo account will be used for Video uploads
The performance of the upload will depend on the performance of the third party services like Vimeo and internet connectivity and speed

## Web Api
| SaadaConnect |  | 2018-04-10
Sl. No | Web Api Development | Design
|  | Hours | Man Days
Web Development
1 | Basic Setup | 4 | 0.5
2 | Users login | 8 | 1
3 | Happiness measurements | 4 | 0.5
4 | News
5 | News feeds with the ability to scroll down to see older | 8 | 1
6 | Filter the news by dates | 4 | 0.5
7 | Search option | 4 | 0.5
8 | User’s profiles
9 | View | 8 | 1
10 | Update | 4 | 0.5
11 | Employees’ profiles search and review | 16 | 2
12 | Ethics Hotline contact details | 8 | 1
13 | Innovation
14 | Post an innovation | 8 | 1
15 | Users can comment, like, dislike | 8 | 1
16 | Search by keyword | 4 | 0.5
17 | Campaigns |  | 0
18 | General or Special campaigns | 24 | 3
19 | Post Campaign | 8 | 1
| Total Effort | 120 | 15