## Android
SaadaConnect
# | Modules | Hours | Days | Resource | # | Man Days | Total
|  |  |  | design | 1 | 21 | 21
| Ui Design |  |  | developer 1 | 1 | 34 | 34 | 51.375 | 51
|  |  |  | developer 1 | 0.5 | 34 | 17
| Page Design | 168 | 21 | testing | 2 | 9 | 18
90
| Development |  |  | Delivery Days | 64
| PHASE 1 |  |  | man days | 90
1 | Basic Setup | 8 | 1
2 | Splash Screen | 8 | 1
3 | Login- Single Sign On Mechanism, auto password change/reset | 6 | 0.75
4 | Happiness page - comment , generate report | 8 | 1
5 | News listing(News + videos) -news feed, filter news by dates, search news | 16 | 2
6 | News details page - add multiple images, interactive images | 20 | 2.5
7 | Vacancies listing | 4 | 0.5
8 | Vacancies details page | 4 | 0.5
9 | Benefits listing | 4 | 0.5
10 | benefits details page | 4 | 0.5
11 | Training listing | 4 | 0.5
12 | Training details page | 4 | 0.5
13 | Profile page | 8 | 1
14 | Profile search and review | 12 | 1.5
15 | Private chat | 40 | 5
16 | Google analytics | 12 | 1.5
17 | Add Ethics hotline contact details | 6 | 0.75
18 | Push notifications | 16 | 2
19 | Survey listing and view | 8 | 1
20 | Notification list page | 10 | 1.25
21 | Notification detail page | 6 | 0.75
22 | Innovation - post innovation, anonymous posting, comment, like, dislike, search by keyword | 40 | 5
23 | Campaign listing page - General/special, pop up when closed | 8 | 1
24 | Special Campaign - list , post | 8 | 1
25 | Logout | 4 | 0.5
PHASE 2
26 | Prescheduled posts | 8 | 1
27 | 360 video player | 24 | 3
Api Integration
| Api Integration | 87 | 10.875
Testing
| Developer side testing | 24 | 3
| QA | 143.85 | 17.9812
| Total effort |  | 90.3563
Assumption
This application will support Sdk version 19(kitkat) and above, iOS 10 and above, iPhone 5s and above
This application designed for mobiles in portrait mode(video- landscape)
Video player details needed