## SCTDA
| SCTDA - TSD |  | 15/01/2018
Monday
| Module | Hours | Man Days |  | No | Man Days | Total Effort |  |  | Total Hours | Hours/3 phases
| Initiation |  |  | Designer | 1 | 12 | 12 |  |  | 96 | 32
| Business analysis | 32 | 4 | Sr Developer | 1 | 35 | 35 | 1 | 110 | 280 | 93.3333
| Project Management | 3.56 | 0.445 | Jr Developer | 1 | 50 | 50 |  |  | 400 | 133.3333
| Design and Prototype | 96 | 12 | IOS (TSD Inspector) | 1 | 25 | 25 |  |  | 200 | 66.6667
| Development |  |  | PM | 1 | #REF! | #REF! |  |  | #REF! | #REF!
| Application basic setup | 8 | 1 | BA | 1 | #REF! | #REF! |  |  | #REF! | #REF!
| Annex A Workflows |  |  | Tech writer | 1 | 3 | 3 |  |  | 24 | 8
1 | 01-02 (Re)New Approval for Trade License for Hotel |  | 0 | QA | 2 | 1.225 | 2.45 |  |  | 19.6 | 6.5333
2 | 03-07 Approval for Modification in the building plans |  | 0 | Total |  |  | #REF!
3 | 08-09 Primary Approval for Trade License Renewal of hotel |  | 0
4 | 10-11 Primary Approval to Obtain/change Official Trade Name |  | 0
5 | 12-15 Approval to Change in Hotel/Apartment Owner |  | 0 | Total Delivery days | 63.225
6 | 16 Approval for Hotel/Apartment Operation Resumption |  | 0 | Total Effort | #REF! | (+1 Day deployment)
7 | 17 Approval for Trade License Cancellation of the Hotel/Apartment |  | 0
8 | 18-19 Approval to Obtain a (Re)New Hotel Management License |  | 0
9 | 20-21 Approval to obtain a (Re)New Tour Operator Trade License |  | 0
10 | 22-23 (re)New Tour Guide License |  | 0 | Resource Loading
11 | 24 Reprinting/Replacement of Issued Tour Guide License Card |  | 0 | Resource/Skill | Phase 1 | Phase 2 | Phase 3
12 | 25 Fines Issuance and Collection/Payment |  | 0 | Project Manager | 52 | 40 | 40
| Annex B Workflows |  |  | Business Analyst | 48 | 32 | 32
13 | 01 Hotel/Hotel Apartment Inspection |  | 0 | User Experience | 52 | 32 | 32
14 | 02 Hotel/Hotel Apartment Classification |  | 0 | Application Architect | 24 | 8 | 8
15 | 03 Tour Guide Inspection |  | 0 | Lead Developer | 94 | 94 | 94
| Annex C Forms |  |  | Developer | 134 | 134 | 134
16 | SCTDA-TS-SRV-1 |  | 0 | Database Architect | 24 | 8 | 8
17 | SCTDA-TS-A001 |  | 0 | IOS Developer | 67 | 67 | 67
18 | SCTDA-TS-A002 |  | 0 | QA | 111 | 111 | 111
19 | SCTDA-TS-A003 |  | 0 | Tech Writer | 12 | 8 | 8
20 | SCTDA-TS-A004 |  | 0 | Total Effort | 210.75 |  | 1686 | 200.75
21 | SCTDA-TS-A005 |  | 0 |  | sum(
22 | SCTDA-TS-A006 |  | 0
23 | SCTDA-TS-A007 |  | 0
24 | SCTDA-TS-A008 |  | 0 | lekshmi's Phase wise split
25 | SCTDA-TS-A009 |  | 0 | phase start | Phase end | Days
26 | SCTDA-TS-B001 |  | 0 | 22-06-2017 | 2017-10-08 | 35
27 | SCTDA-TS-B002 |  | 0 | 2017-10-08 | 25/09/2017 | 33
28 | SCTDA-TS-B003 |  | 0 | 26/09/2017 | 2017-02-11 | 31
29 | SCTDA-TS-B004 |  | 0
30 | SCTDA-TS-B005 |  | 0
31 | SCTDA-TS-B006 |  | 0
32 | SCTDA-TS-B007 |  | 0
33 | SCTDA-TS-B008 |  | 0
34 | SCTDA-TS-B009 |  | 0
35 | SCTDA-TS-B010 |  | 0
36 | SCTDA-TS-B011 |  | 0
37 | SCTDA-TS-B012 |  | 0
38 | SCTDA-TS-B013 |  | 0
39 | SCTDA-TS-B014 |  | 0
40 | SCTDA-TS-C001 |  | 0
41 | SCTDA-TS-C002 |  | 0
42 | SCTDA-TS-C003 |  | 0
43 | SCTDA-TS-C004 |  | 0
Admin
Master Data Management
44 | Licensing services List (Workflows) |  | 0
45 | Licensing service Fees |  | 0
46 | Licensing service fines |  | 0
47 | Licensing service periods (From - To) |  | 0
48 | Document Upload List |  | 0
49 | Document Requirements per service |  | 0
50 | User Types List (Role) |  | 0
51 | Reject reason codes & descriptions |  | 0
52 | Star Classification list |  | 0 |  | Onsite inspection (mobile App)
53 | Inspection criteria list |  | 0
54 | Criteria per Service |  | 0
55 | Forms List |  | 0
56 | Inspection Report types / List |  | 0
57 | Violations list |  | 0
58 | User management |  | 0
59 | Manage documents |  | 0
60 | Manage videos |  | 0
61 | Archive Videos |  | 0
62 | Roles and Services (workflow) mappings |  | 0
Main Modules
Applicant
63 | Login, Forgot password, Remember Password |  | 0
64 | Registration (basic profile) |  | 0
65 | Multi factor Authentication |  | 0
66 | Email verification |  | 0
67 | Select Service |  | 0
68 | Upload documents |  | 0
69 | Fill Application form |  | 0
70 | Display required documents list |  | 0
71 | Check Violations and Fines (potential Government site integration required) |  | 0
72 | Pay application Fees (Separate from fines) |  | 0
73 | Pay fines (Tahseel integration) |  | 0
74 | Download Documents |  | 0
75 | Receive Star ratings (UI Updates) |  | 0
76 | Receive Notifications |  | 0
77 | Dashboard Updates |  | 0
78 | Raise Disputes |  | 0
TSD Licensing Staff
79 | Verify document list |  | 0
80 | Manual verification of uploaded documents via visual inspection |  | 0
81 | Approve / Reject Application |  | 0
82 | Send SMS & Email |  | 0
83 | Request Additional Documents |  | 0
84 | Capture comments and results of the verification process |  | 0
85 | Create Inspection report based on results |  | 0
86 | Recommend Initial star ratings |  | 0
TSD Inspector
87 | Create Classification Criteria |  | 0
88 | Create Inspection report |  | 0
89 | Onsite Inspection results |  | 0
90 | Collect evidence |  | 0
91 | Retrieve inspection list |  | 0
92 | Obtain Score for Hotel Designator |  | 0
Head Of Inspection
93 | Review Inspector Report |  | 0
94 | Approve / Reject based on inspector Report |  | 0
95 | Schedule On Site inspection |  | 0
96 | Review Requirements based on Video Conference |  | 0
97 | Approval / Rejection Recommendation for Primary Approval |  | 0
98 | Update Inspection Calendar |  | 0
TSD Manager
99 | Reassign Tasks |  | 0
100 | Approve / Reject Issue of Primary Approval |  | 0
101 | Approve / Reject Tour Guide License |  | 0
102 | Approve / Reject reprint of Tour Guide ID |  | 0
103 | Approve / Reject recommendation for adjusting star rating |  | 0
Head Of Licensing
104 | Recommend to TSD Manager for the issuance of Approval to Obtain/Change Trade Name |  | 0
105 | Recommend to TSD Manager for the issuance of Approval to Renew/new Hotel Management License |  | 0
106 | Recommend to TSD Manager for the issuance of Approval to Renew/new Tour Operator License |  | 0
107 | Recommend to TSD Manager for the issuance of Approval to Reprint Tour Guide ID |  | 0
Mobile App
108 | Mobile App API |  | 0
System features
108 | Authentication & authorization |  | 0
109 | Auditing & logging |  | 0
110 | Exception handling |  | 0
111 | Manage files and folders |  | 0
112 | Generate thumbnail for videos and images |  | 0
113 | SMS & Email |  | 0
114 | Tahseel Integration |  | 0
115 | Zajel Integration |  | 0
116 | Payment Gateway Integration |  | 0
117 | QR Code Generation |  | 0
English and Arabic
Data migration
integration with hotel statistics system
Reports
Quality Assurance
| QA & Bug Fixing | 3.6 | 0.45
| UAT | 16 | 2
| Deployment per instance | 8 | 1
| Total Effort | 167.16 | 20.895
Assumptions
Pre defined format for print and format will designed in HTML and print in plain paper
Need clarification
Mobile App For TSD Inspector. App should work offline
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118