## SCTDA - Web & API
| SCTDA - TSD |  | 22/05/2018
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 12 | 12
| Business analysis | 32 | 4 | Sr Developer | 1 | 109 | 109 | 207.25 | 259.475 | 216.5 | 217
| Project Management | 235.94 | 29.4925 | Jr Developer | 1 | 108 | 108
| Design and Prototype | 96 | 12 | IOS (TSD Inspector) | 1.5 | 28.3167 | 42.475
| Development |  |  | PM | 1 | 29.4925 | 29.4925
| Application basic setup | 8 | 1 | BA | 1 | 4 | 4
| Annex A Workflows |  |  | Tech writer | 1 | 3 | 3
1 | 01-02 (Re)New Approval for Trade License for Hotel | 20 | 2.5 | QA | 2 | 38.7125 | 77.425
2 | 03-07 Approval for Modification in the building plans | 32 | 4 | Total |  |  | 385.3925
3 | 08-09 Primary Approval for Trade License Renewal of hotel | 16 | 2
4 | 10-11 Primary Approval to Obtain/change Official Trade Name | 16 | 2
5 | 12-15 Approval to Change in Hotel/Apartment Owner | 24 | 3 | Total Delivery days | 158.7125 | 7.9356
6 | 16 Approval for Hotel/Apartment Operation Resumption | 12 | 1.5 | Total Effort | 385.3925 | (+1 Day deployment)
7 | 17 Approval for Trade License Cancellation of the Hotel/Apartment | 12 | 1.5
8 | 18-19 Approval to Obtain a (Re)New Hotel Management License | 16 | 2
9 | 20-21 Approval to obtain a (Re)New Tour Operator Trade License | 16 | 2
10 | 22-23 (re)New Tour Guide License | 16 | 2
11 | 24 Reprinting/Replacement of Issued Tour Guide License Card | 12 | 1.5
12 | 25 Fines Issuance and Collection/Payment | 12 | 1.5
Annex B Workflows
13 | 01 Hotel/Hotel Apartment Inspection | 12 | 1.5
14 | 02 Hotel/Hotel Apartment Classification | 16 | 2
15 | 03 Tour Guide Inspection | 24 | 3
Annex C Forms
16 | SCTDA-TS-SRV-1 | 20 | 2.5
17 | SCTDA-TS-A001 | 20 | 2.5
18 | SCTDA-TS-A002 | 20 | 2.5
19 | SCTDA-TS-A003 | 20 | 2.5
20 | SCTDA-TS-A004 | 20 | 2.5
21 | SCTDA-TS-A005 | 20 | 2.5
22 | SCTDA-TS-A006 | 20 | 2.5
23 | SCTDA-TS-A007 | 20 | 2.5
24 | SCTDA-TS-A008 | 20 | 2.5
25 | SCTDA-TS-A009 | 20 | 2.5
26 | SCTDA-TS-B001 | 20 | 2.5
27 | SCTDA-TS-B002 | 20 | 2.5
28 | SCTDA-TS-B003 | 20 | 2.5
29 | SCTDA-TS-B004 | 20 | 2.5
30 | SCTDA-TS-B005 | 20 | 2.5
31 | SCTDA-TS-B006 | 20 | 2.5
32 | SCTDA-TS-B007 | 20 | 2.5
33 | SCTDA-TS-B008 | 20 | 2.5
34 | SCTDA-TS-B009 | 20 | 2.5
35 | SCTDA-TS-B010 | 20 | 2.5
36 | SCTDA-TS-B011 | 20 | 2.5
37 | SCTDA-TS-B012 | 20 | 2.5
38 | SCTDA-TS-B013 | 20 | 2.5
39 | SCTDA-TS-B014 | 20 | 2.5
40 | SCTDA-TS-C001 | 20 | 2.5
41 | SCTDA-TS-C002 | 20 | 2.5
42 | SCTDA-TS-C003 | 20 | 2.5
43 | SCTDA-TS-C004 | 20 | 2.5
Admin
Master Data Management
44 | Licensing services List | 4 | 0.5
45 | Licensing service Fees | 8 | 1
46 | Licensing service fines | 8 | 1
47 | Licensing service periods (From - To) | 4 | 0.5
48 | Document Upload List | 8 | 1
49 | Document Requirements per service | 8 | 1
50 | User Types List (Role) | 8 | 1
51 | Reject reason codes & descriptions | 4 | 0.5
52 | Star Classification list | 8 | 1 |  | Onsite inspection (mobile App)
53 | Inspection criteria list (Create Checklist with weightage) | 20 | 2.5
54 | Criteria per Service | 12 | 1.5
55 | Forms List | 4 | 0.5
56 | Integration with Vehicle licensing | 8 | 1
57 | Inspection Report types / List | 8 | 1
58 | Violations list | 8 | 1
59 | User management | 16 | 2
60 | Manage documents | 12 | 1.5
61 | Roles and Services (workflow) mappings | 24 | 3
Main Modules
Applicant
61 | Login, Forgot password, Remember Password | 8 | 1
62 | Registration (basic profile) | 12 | 1.5
63 | Multi factor Authentication | 16 | 2
64 | Email verification | 4 | 0.5
65 | Select Service | 8 | 1
66 | Upload documents (Attach Meta tags to the documents for searchability) | 12 | 1.5
67 | Application form | 16 | 2
68 | Display required documents list | 4 | 0.5
69 | Check Violations and Fines (potential Government site integration required) | 24 | 3
70 | Pay application Fees (Separate from fines) | 12 | 1.5
71 | Pay fines (Tahseel integration) | 20 | 2.5
72 | Download Documents | 12 | 1.5
73 | Receive Star ratings (UI Updates) | 4 | 0.5
74 | Receive Notifications | 20 | 2.5
75 | Dashboard Updates | 16 | 2
76 | Raise Disputes | 4 | 0.5
TSD Licensing Staff
77 | Verify document list | 12 | 1.5
78 | Manual verification of uploaded documents via visual inspection | 8 | 1
79 | Approve / Reject Application | 12 | 1.5
80 | Send SMS & Email | 16 | 2
81 | Request Additional Documents | 16 | 2
82 | Capture comments and results of the verification process | 8 | 1
83 | Create Inspection report based on results | 8 | 1
84 | Recommend Initial star ratings | 8 | 1
Head Of Inspection
85 | Review Inspector Report | 12 | 1.5
86 | Approve / Reject based on inspector Report | 8 | 1
87 | Schedule On Site inspection | 12 | 1.5
88 | Review Requirements based on Video Conference | 4 | 0.5
89 | Approval / Rejection Recommendation for Primary Approval | 16 | 2
90 | Update Inspection Calendar | 8 | 1
TSD Manager
91 | Reassign Tasks | 8 | 1
92 | Approve / Reject Issue of Primary Approval | 12 | 1.5
93 | Approve / Reject Tour Guide License | 12 | 1.5
94 | Approve / Reject reprint of Tour Guide ID | 16 | 2
95 | Approve / Reject recommendation for adjusting star rating | 20 | 2.5
Head Of Licensing
96 | Recommend to TSD Manager for the issuance of Approval to Obtain/Change Trade Name | 8 | 1
97 | Recommend to TSD Manager for the issuance of Approval to Renew/new Hotel Management License | 8 | 1
98 | Recommend to TSD Manager for the issuance of Approval to Renew/new Tour Operator License | 8 | 1
99 | Recommend to TSD Manager for the issuance of Approval to Reprint Tour Guide ID | 8 | 1
Tour Guide
100 | Tour Guide Registration | 8 | 1
101 | Pay Tour Guide Training Fees | 6 | 0.75
102 | Register For Exam / Classes | 6 | 0.75
IPTD Staff
103 | Review Tour Guide Registration (Approve /Reject) | 6 | 0.75
104 | Verify Training (Pass / Fail)\ | 6 | 0.75
105 | Pass or Fail Exam | 6 | 0.75
Mobile App
106 | Mobile App API | 112 | 14
System features
107 | Authentication & authorization | 8 | 1
108 | Auditing & logging | 8 | 1
109 | Exception handling | 8 | 1
110 | Manage files and folders | 24 | 3
111 | Meta tags for documents and images | 16 | 2
112 | SMS & Email | 8 | 1
113 | Tahseel Integration | 8 | 1
115 | Payment Gateway Integration | 20 | 2.5
116 | Empost Integration | 16 | 2
117 | Hotel Statistics System | 16 | 2
118 | Request pool for all actors | 6 | 0.75
119 | QR Code Generation | 8 | 1
Quality Assurance
120 | QA & Bug Fixing | 603.4 | 75.425
121 | UAT | 16 | 2
122 | Deployment per instance | 8 | 1
| Total Effort | 2723.34 | 340.4175
Assumptions
Pre defined format for print and format will designed in HTML and print in plain paper
Need clarification
Mobile App For TSD Inspector?
For video management, client would share the details of Vimeo or Youtube
Uploading Mobile App to App store will be taken care of by the client.
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118

## iOS App
Sharjah Tourism App- TSD Inspector
# | Modules | Hours | Days
Ui Design
| Page Design | 63 | 7.875
Development
1 | Basic Setup | 8 | 1
2 | Splash | 4 | 0.5
3 | Login | 2 | 0.25
4 | Forgotpassword | 1 | 0.125
5 | Dashbaord | 1 | 0.125
6 | QR code library integration | 4 | 0.5
Scanning
7 | Create Classification Criteria | 1 | 0.125
8 | Create Inspection report | 1 | 0.125
9 | Onsite Inspection results | 4 | 0.5
10 | Collect evidence 8 forms | 12 | 1.5
11 | Retrieve inspection list | 4 | 0.5
12 | Obtain Score for Hotel Designator | 8 | 1
13 | View Assignment | 8 | 1
14 | Take photo | 4 | 0.5
15 | Upload photo | 4 | 0.5
16 | Upload docuemnts | 2 | 0.25
17 | Submit inspection details | 72 | 9
0
Api Integration
| Api Integration | 40 | 5
Testing
| Developer side testing | 20 | 2.5
| Testing | 76.8 | 9.6
| Total effort |  | 42.475
Assumption
This application will iOS version 9 and above
This application designed for mobiles in portrait mode