## Project Planner
High Level Plan
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Project Inception | 1 | 3 |  |  | 0%
Requirement Gathering | 4 | 8 |  |  | 0%
User Experience | 6 | 8 |  |  | 0%
Running Prototype | 8 | 12 |  |  | 0%
Technical Architecture | 11 | 5 |  |  | 0%
Database Architecture | 11 | 5 |  |  | 0%
Web Development | 16 | 31 |  |  | 0%
Site Admin | 16 | 10 |  |  | 0%
General Pages | 22 | 4 |  |  | 0%
New Permits | 26 | 8 |  |  | 0%
Permit Renewal | 30 | 4 |  |  | 0%
Reprint Sticker | 34 | 8 |  |  | 0%
Cancel Permit | 39 | 3 |  |  | 0%
Inspection & Fines | 42 | 5 |  |  | 0%
System Features | 16 | 14 |  |  | 0%
Application Features | 16 | 9 |  |  | 0%
Android App | 16 | 30 |  |  | 0%
Android API | 16 | 15 |  |  | 0%
QA & Bug Fixing | 30 | 25 |  |  | 0%
UAT | 53 | 7 |  |  | 0%
Deployment | 59 | 2 |  |  | 0%