## SCTDA
| SCTDA |  | 2017-05-23
Tuesday
| Module | Hours | Man Days
Initiation
1 | Requirements gathering and documentation (SRS) | 24 | 3
2 | Functional Specification | 36 | 4.5
3 | Project Management | 112 | 14
4 | Finalize and purchase Responsive HTML Theme
5 | Complete running prototype | 96 | 12
Development
1 | Admin
2 | Admin Dashboard | 8 | 1
3 | Manage Users | 16 | 2
4 | Manage Fees | 12 | 1.5
| Manage Permits | 16 | 2
5 | Multi Language (english & Arabic) | 48 | 6
General Pages
12 | Privacy Policy | 8 | 1
13 | Patient T&C | 8 | 1
14 | Provider T&C | 8 | 1
15 | Moderation Guidelines | 8 | 1
16 | Sitemap | 8 | 1
17 | About | 8 | 1
| New Permit | 64 | 8
| Reissue Permit | 12 | 1.5
| Re print - Permit issuance and printing or reprinting | 40 | 5
| Cancel Permit | 24 | 3
| Inspection and Fines | 40 | 5
| Mobile App development (Android) | 200 | 25
| API Development | 80 | 10
| Reports (3 reports) | 56 | 7
| Third party API Integration (SMS, Muroor, Tahseel) | 64 | 8
| Quality Assurance | 224 | 28
QA & Bug Fixing
UAT
| Deployment | 8 | 1
| Total Effort | 1228 | 153.5
Assumptions
Pre defined format for print and format will designed in HTML and print in plain paper
Need clarification
Inspection -> Route map recording
Permissions of all usertypes
Inspection -> Inspection process should be recorded?
Mobile Devices - Android device with scanner and required SKD need to provide
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118