## SCTDA
| SCTDA |  | 2017-05-23
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 12 | 12
1 | Business analysis | 72 | 9 | Sr Developer | 1 | 35 | 35 | 113 | 110
3 | Project Management | 96 | 12 | Jr Developer | 1 | 50 | 50
| Project Documentation (SRS, Scope, WBS etc.) | 48 | 6 | Android | 1 | 25 | 25
5 | Complete running prototype | 96 | 12 | PM | 1 | 15 | 15
| Development |  |  | BA | 1 | 12 | 12
1 | Admin |  |  | Tech writer | 1 | 3 | 3
2 | Assign roles | 8 | 1 | QA | 2 | 20.775 | 41.55
3 | Manage Users | 16 | 2 | Total |  |  | 193.55
4 | Manage Fees | 12 | 1.5
| Manage inspection check list | 16 | 2
| Manage Fines | 8 | 1 | Total Delivery days | 82.775
| Configure scheduler, gateways etc | 8 | 1 | Total Effort | 193.55 | (+1 Day deployment)
| Upload documents as proxy | 8 | 1
General Pages
12 | Privacy Policy | 8 | 1
| Announcements | 8 | 1 | Resource Loading
| About | 4 | 0.5 | Resource/Skill | Month 1 | Month 2 | Month 3
| Help | 16 | 2 | Project Manager | 48 | 40 | 32
| New Permit |  |  | Business Analyst | 80 | 8 | 8
| Submit Documents | 12 | 1.5 | User Experience | 64 | 16 | 16
| Documents Review | 12 | 1.5 | Application Architect | 24 | 8 | 8
| Vehicle inspection results validation | 16 | 2 | Lead Developer | 80 | 160 | 80
| Pay fees and fines | 12 | 1.5 | Developer | 80 | 160 | 120
| Print Permits and sticker | 12 | 1.5 | Database Architect | 24 | 8 | 8
| Permit Renewal |  |  | IOS Developer | 40 | 160 | 120
| Workflow adjustment for renewal | 12 | 1.5 | QA | 40 | 40 | 240
| Re print Sticker |  |  | Tech Writer |  |  | 24
| Submit request with required documents | 6 | 0.75 | Total Effort | 217 Man Days |  | 1736
| Review Documents | 6 | 0.75
| Review Fines and complaints | 6 | 0.75 | Total Effort Variation : | 180 - 200 days
| Approve or reject | 6 | 0.75
| Pay fees and fines | 6 | 0.75
| disable previous permit no | 6 | 0.75
| Notify results | 6 | 0.75 |  |  | 1736/8
| Issue new sticker | 4 | 0.5
Cancel Permit
| Verify and review current permit | 6 | 0.75
| Review pending fees or fines | 6 | 0.75
| Pay fines | 4 | 0.5
| approve / reject request | 4 | 0.5
| Notify permit holder | 4 | 0.5
Inspection and Fines
| Assign Inspector , inspection date and time | 6 | 0.75
| Retrieve inspection list for vehicle and vehicle history | 6 | 0.75
| Record inspection results | 6 | 0.75 | 40
| Add inspection evidence via photos | 6 | 0.75
| Determine fines based on inspection results | 6 | 0.75
| print fines per vehicle | 6 | 0.75
| Send sms and emails to permit holder | 4 | 0.5
| Mobile App development (IOS) | 200 | 25
| Mobile API Development | 80 | 10
| Reports (3 reports) | 56 | 7
Report template cutomizations for printing
| Third party API Integration (SMS, Muroor, Tahseel) | 64 | 8
| General application features |  | 0
| search | 8 | 1
| dashboard for applicants, Permit holder, TSD Staff, TSD Manager & inspector | 40 | 5
| application tracking | 6 | 0.75
| Complaints management | 16 | 2
| System features |  | 0
| Authentication & authorization | 6 | 0.75
| Auditing & logging | 6 | 0.75
| Exception handling | 6 | 0.75
| Scheduled jobs | 6 | 0.75
| On Screen guides | 16 | 2
| Workflow management | 16 | 2
| Localization (english & Arabic) | 48 | 6
| User Manual | 24 | 3
| Document Archival | 8 | 1
Quality Assurance
| QA & Bug Fixing | 316.4 | 39.55
| UAT | 16 | 2
| Deployment | 8 | 1
| Total Effort | 1556.4 | 194.55
Assumptions
Pre defined format for print and format will designed in HTML and print in plain paper
Need clarification
Inspection -> Route map recording
Permissions of all usertypes
54 | Inspection -> Inspection process should be recorded?
Mobile Devices - Android device with scanner and required SKD need to provide
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118

## Resource Loading
Resource/Skill | Month 1 | Month 2 | Month 3 | total
Proj. Manager | 48 | 40 | 32 | 15 | 27
Business Analyst | 80 | 8 | 8 | 12
User Experience | 64 | 16 | 16 | 12
Architect | 24 | 8 | 8 | 5 | 120
Lead Developer | 80 | 160 | 80 | 40
Developer | 80 | 160 | 120 | 45
DB Architect | 24 | 8 | 8 | 5
Android Developer | 0 | 120 | 80 | 25
QA | 40 | 40 | 240 | 40
Total Effort | 199 |  | 1592
Resource/Skill | Month 1 | Month 2 | Month 3
Project Manager | 48 | 40 | 32
Business Analyst | 80 | 8 | 8
User Experience | 64 | 16 | 16
Application Architect | 24 | 8 | 8
Lead Developer | 80 | 160 | 80
Developer | 80 | 160 | 120
Database Architect | 24 | 8 | 8
IOS Developer | 40 | 160 | 120
QA | 40 | 40 | 240
Tech Writer |  |  | 24
Total Effort | 217 |  | 1736

## Sheet1
Level 1 | Level 2 | Level 3
Initiation | Business Analysis