## Web & WebAPI
| Food Ordering Mobile App and Admin |  | 2018-10-05
Friday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 8 | 8
1 | Business analysis | 20 | 2.5 | Sr Developer | 1 | 35 | 35 | 45.5 | 46
2 | Project Management | 62.16 | 7.77 | Jr Developer | 1 | 11 | 11
3 | Project Documentation (SRS, Scope, WBS etc.) | 32 | 4 | PM | 1 | 7.77 | 7.77
4 | Prototype | 64 | 8 | BA | 1 | 2.5 | 2.5
| Development |  |  | Tech writer | 1 | 4 | 4
| Admin |  |  | QA | 1 | 19.2 | 19.2
| User Management | 24 | 3 | Total |  |  | 87.47
| Dashboard | 40 | 5 | Total Delivery days | 62.2 |  |  | <--- This would be the minimum time required
| Master Data |  |  | Total Effort | 87.47 | (+1 Day deployment)
| Food time Category (Day, night etc) | 6 | 0.75
| Special Diet Categories | 6 | 0.75
| Menu Type (Breakfast, Lunch, Brunch, Snacks etc) | 6 | 0.75 | Total Effort Web | 87.47
| Meal Types (Indian, Chineese, Italian etc) | 6 | 0.75 | Total effort Android | 40
| Food Categories (Chicken, rice, soup, mutton, vegetable, vegan) | 6 | 0.75 | Total Effort IOS | 40
| Menu Items | 6 | 0.75 | Total effort | 167.47
| Combo Category | 6 | 0.75
| Combo Items | 6 | 0.75 | Total Delivery Days | 60
| Accompaniment (Sugar, Ketchup, Garlic dip) | 6 | 0.75
| Food options (No sugar, Oil free, No garlic) | 6 | 0.75
| Location (With mapping facility) | 8 | 1
| Hours of Operation | 6 | 0.75
| Related food category | 6 | 0.75
| Kitchen | 6 | 0.75
| Manage Customers (individuals, corporates) | 8 | 1
View Orders
| View Order details | 6 | 0.75 | Total Effort Variation : | -- days
| Kitchen mapping with location, delivery time, food availability | 8 | 1
| Help [FAQ] | 12 | 1.5
Reports
| Customer/Coprporate wise | 6 | 0.75
| Menu wise | 6 | 0.75
| Income wise | 6 | 0.75
| location wise | 6 | 0.75
| Order quantity wise | 6 | 0.75
| Customer feedback | 8 | 1
Web API
| Basic Setup | 8 | 1
| Login Page | 3 | 0.375
| Sign up Page(User and corporate) | 3 | 0.375
| Forgot password | 3 | 0.375
| Logout | 3 | 0.375
| Profile page | 8 | 1
| Your orders List(Pending order and Delivered order) | 6 | 0.75
| Contact us | 3 | 0.375
| Cart page | 6 | 0.75
| Address Page | 3 | 0.375
| Checkout page | 6 | 0.75
| Order Confirmation page | 6 | 0.75
| Notification | 4 | 0.5
| Rating page | 4 | 0.5
| Sub Category | 2 | 0.25
| Filter | 4 | 0.5
| Food list page(Search) | 8 | 1
| food detail page | 8 | 1
| Option list page | 2 | 0.25
| Schedule page | 6 | 0.75
| Help [FAQ] | 6 | 0.75
System features
1 | Auditing & logging | 6 | 0.75
2 | Exception handling | 6 | 0.75
3 | User Manual | 16 | 2
4 | Document Archival | 12 | 1.5
Quality Assurance
1 | QA & Bug Fixing | 129.6 | 16.2
2 | UAT | 24 | 3
3 | Deployment | 8 | 1
| Total Effort | 703.76 | 87.97
Assumptions
The application will be a responsive web application
There is no web interphase for customers and corporate users

## Android&iOS
|  | SaudiMess |  |  | 2018-10-04
Thursday
|  | Android |  | iOS
# | Module | Hours | Man Days | Hours | Man Days
Ui Design
| Page Design | 86.5 | 10.8125 | 86.5 | 10.8125
Development
1 | Basic Setup | 8 | 1 | 8 | 1
2 | Splash | 3 | 0.375 | 3 | 0.375
3 | Login Page | 3 | 0.375 | 3 | 0.375
4 | Sign up Page(User and corporate) | 4 | 0.5 | 4 | 0.5
5 | Forgot password | 3 | 0.375 | 3 | 0.375
6 | Logout | 1 | 0.125 | 1 | 0.125
7 | Profile page | 4 | 0.5 | 4 | 0.5
8 | Your orders List(Pending order and Delivered order) | 8 | 1 | 8 | 1
9 | Contact us | 1 | 0.125 | 1 | 0.125
10 | Help | 1 | 0.125 | 1 | 0.125
11 | Cart page | 12 | 1.5 | 12 | 1.5
12 | Address Page | 4 | 0.5 | 4 | 0.5
13 | Checkout page | 6 | 0.75 | 6 | 0.75
14 | Order Confirmation page | 6 | 0.75 | 6 | 0.75
15 | Notification | 6 | 0.75 | 6 | 0.75
16 | Rating page | 6 | 0.75 | 6 | 0.75
User page
17 | Home page | 4 | 0.5 | 4 | 0.5
18 | Sub Category | 6 | 0.75 | 6 | 0.75
19 | Filter | 6 | 0.75 | 6 | 0.75
20 | Food list page(Search) | 6 | 0.75 | 6 | 0.75
21 | food detail page | 6 | 0.75 | 6 | 0.75
22 | Option list page | 6 | 0.75 | 6 | 0.75
23 | Schedule page | 6 | 0.75 | 6 | 0.75
Corporate user page
24 | Home page | 8 | 1 | 8 | 1
25 | Sub Category | 6 | 0.75 | 6 | 0.75
26 | Filter | 6 | 0.75 | 6 | 0.75
27 | Food list page | 6 | 0.75 | 6 | 0.75
28 | food detail page | 6 | 0.75 | 6 | 0.75
29 | Option list page | 6 | 0.75 | 6 | 0.75
30 | Schedule page | 8 | 1 | 8 | 1
Api Integration
| Api integration | 38.5 | 4.8125 | 38.5 | 4.8125
Testing
| testing Developer | 32 | 4 | 32 | 4
| Total effort |  | 39.875 |  | 39.875