## Employee Satisfaction Effort
Jet Ski Registration |  | November 17 2017
Friday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 40 | 5 | 5
Functional Specification | 12 | 1.5 | BA | 1 | 20 | 2.5 | 2.5 | 13.25 | 13.25
Project Management | 8 | 1 | Sr.Developer | 1 | 56 | 7 | 7 |  |  | 0
Graphic Design | 4 | 0.5 | Jr Developer | 1 | 50 | 6.25 | 6.25
Working Prototype | 36 | 4.5 | PM | 1 | 8 | 1 | 1
Development |  |  | QA | 1 | 46.4 | 5.8 | 5.8 | 220.4
|  |  | Total |  | 220.4 |  | 27.55
Login | 4 | 0.5
Forgot password | 2 | 0.25 | Total Delivery days | 20.3
Customer Module - Registration Form | 20 | 2.5 | Total Man day Effort | 27.55
Customer Module - Registration Review & Edit | 8 | 1
Customer Module - Registration notification (email) | 4 | 0.5
Customer Module - View Registration status | 4 | 0.5
Payment Gateway Integration | 24 | 3
Client Module - User Management | 8 | 1
Client Module - Manage Approval Level[Permission] | 4 | 0.5
Client Module - List, Search (based on date) Registration submitted | 4 | 0.5
Client Module - View Registration submitted details | 4 | 0.5
Client Module - Approve Registration | 8 | 1
Client Module - Approval email to client | 4 | 0.5
Client Module - 1 Tabular report with two search fields | 8 | 1
Testing & Deployment
Testing | 42.4 | 5.3
UAT | 4 | 0.5
Deployment Support | 8 | 1
Total Effort | 228.4 | 28.55
Assumptions
Payment gateway details will be shared before starting the project
Mail server details for sending notification emails will be shared
Branding guidelines & logo will be shared