## WordPress
| WordPress |  | Nov 11 2016
Tuesday
Sl. No. | Module | Man Hours | Man Days | Phase 1 | No | Man Days | Total
| Phase 1 |  |  | Sr. PHP developer | 0.5 | 8 | 4
1 | Finalising and purchase of Wordpress Theme & Images |  | 1 | Junior PHP Developer | 1 | 11 | 11
2 | Customization of theme (up to 15%) |  | 2 | QA | 1 | 2 | 2
3 | Theme Integration & Page Creations |  | 2 | Sub Total |  |  | 17
4 | Page Creation |  |  | Phase 2
| Home Page |  | 1 | Sr. PHP developer | 1 | 4 | 4
| Product |  | 3 | Junior PHP Developer | 1 | 4 | 4
| Product Search |  |  | QA | 1 | 2 | 2
| Product Category |  |  | sub total |  |  | 10
| Category Listing (Dynamic) |  |  | Total |  |  | 27
Product Details (Dynamic)
Brochures
| About Sharp |  | 2
Sharp History
Corporate profile
Philosophy
MD Message
Environment & CSR
| News Release |  | 1
News & Events
| Contact Us |  | 2
Regional Headquarters
Careers
Why Work for sharp
Culture at sharp
Service center location (search)
Feedback
| News & Events |  | 1
| Sitemap |  | 2
SitePolicy
Global policy for information security
News Letter subscription
Integration with Social Media
Muti Platform & multi device support
Quick Response and loading
Blog with case studies
Phase 2
| Customer Portal |  | 3
Customer Registration
Product Registration
Product Support (search)
| Partners Login |  | 3
Online File sharing
Training videos
5 | Quality Analysis (QA) |  | 4
6 | UAT Support & Implementation
7 | Live
| Total Effort |  | 27
Assumption
Client will purchase appropriate theme
Client will purchase plugins for - Customer Portal, Partners Login