## Shopping Cart
| ShoppingCart |  | 2017-02-21
Tuesday
Sl. No. | Module | Man Hours | Man Days
1 | Low Level Design (Milestone 1) | 24 | 3
2 | HTML Design - Theme | 8 | 1
3 | Documentation (SRS) | 16 | 2
4 | Development & Testing (Milestone 2) | 96 | 12
5 | Creating Developemt Environment PHP - Opencart | 0 | 0
| Theme Integration & Configuration | 32 | 4
| Theme Customization (upto 20%) | 48 | 6
6 | Features
Web Module
Responsive Design
User Registration
Authentication and Authorization
Related products, suggestions & wish list
Shopping cart
7 | Product Comments and ratings
16 | Unlimited product categories, products and manufacturers
17 | Intelligent product search with filters
21 | Integration with payment gateway
23 | Promotions and special offers
33 | Social media integration
Admin Features:
Add new Categories and Products (Product uploads)
Create discounts for customers (special offers & discounts)
Analytics, event notification system and reporting
Manage Site content
Manage user groups, User & Roles ( Site admins, Store managers)
7 | Manage Stock, Orders, Returns & Prices
| Testing & Bug fixing | 16 | 2
35 | Project Management | 8 | 1
36 | TOTAL | 128 | 16
Assumption
Open Cart theme & Extension need to be purchased
Out of Scope
Data Entry