## Android
Pages | Hours | Days
Pages Design |  | 0
Basic setup | 8 | 1
Login Screen | 4 | 0.5
User Registration | 4 | 0.5
Welcome screen | 8 | 1
Dashboard | 8 | 1
Category Menu | 6 | 0.75
Related products | 6 | 0.75
suggestions | 6 | 0.75
wish list | 6 | 0.75
Shopping cart | 16 | 2
Product list | 6 | 0.75
(a) Intelligent product search with filters | 12 | 1.5
Product Detail Page | 6 | 0.75
(a)Product Comments and ratings | 6 | 0.75
Integration with payment gateway | 32 | 4
Promotions and special offers | 8 | 1
Social media integration (Depends) | 16 | 2
Billing information | 6 | 0.75
Shipping information | 6 | 0.75
Shipping tracking page | 8 | 1
Order history | 6 | 0.75
user details Page | 6 | 0.75
Settings |  | 0
(a) change password | 3 | 0.375
Notification page | 6 | 0.75
Api Integration | 64 | 8
Play store integration setup | 16 | 2
Basic testing | 16 | 2
| 295 | 36.875