## Obaid
| Obaid |  | 21/06/2018
Thursday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 5 | 5
| Business analysis (SRS,FS, Weekly Reports, User Manual, MOM etc.) | 24 | 3 | Sr Developer | 1.5 | 20 | 30 | 29.5 | 34 | 29.5 | 30
| Project Management | 22.8 | 2.85 | SEO & Marketing | 1 | 4 | 4
| Design and Prototype | 40 | 5 | PM | 1 | 2.85 | 2.85
| Marketing and SEO | 32 | 4 | BA | 1 | 3 | 3
| Development |  |  | QA | 1.5 | 6.3667 | 9.55
| Application Basic Setup | 8 | 1 | Total |  |  | 54.4
Admin
1 | Manage Shops | 12 | 1.5
2 | Approve Shop | 4 | 0.5 | Total Delivery days | 31.3667 | 6.2733
3 | Manage RFQ | 6 | 0.75 | Total Effort | 54.4 | (+1 Day deployment)
4 | Create Car List | 8 | 1
5 | Manage Spare Parts list | 8 | 1
6 | Google Analytics Dashboard + Reports based on Site Statistics | 16 | 2
7 | Create spare parts & Car list based on RFQ (upload pdf, car images, spare parts images) | 12 | 1.5 | Contingency: +/- 15%
| Seller | [5 empty] | SEO
8 | Update Shop Profile or Register Shop Profile | 16 | 2
9 | CAPTCHA for profile update | 6 | 0.75
10 | Email Validation | 4 | 0.5
11 | Register Seller | 6 | 0.75
| Customer (Buyer) |  | 0
12 | Create RFQ | 12 | 1.5
13 | Shop directory listing | 8 | 1
15 | Advanced search (By shop, spare parts, region, Car Models etc) | 12 | 1.5
16 | Filter by distance, rating, alphabetical | 6 | 0.75
17 | Click to call shop | 6 | 0.75
18 | email to shop | 6 | 0.75
19 | Find shop on map | 6 | 0.75
20 | Home page | 32 | 4
System features
20 | Bilingual Site (Arabic + English) | 24 | 3
21 | Authentication & authorization | 6 | 0.75
22 | Auditing & logging | 6 | 0.75
23 | Exception handling | 6 | 0.75
Quality Assurance
25 | QA & Bug Fixing | 68.4 | 8.55
26 | UAT | 8 | 1
27 | Deployment | 8 | 1
| Total Effort | 439.2 | 54.9
Assumptions
WhatsApp Automation is not practical