## Obaid
| Obaid |  | 21/06/2018
Thursday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 2.5 | 2.5
| Business analysis (SRS,FS, Weekly Reports, User Manual, MOM etc.) | 16 | 2 | Sr Developer | 1.5 | 11 | 16.5 | 17.75 | 17.25 | 17.75 | 16.5
| Project Management | 13.8 | 1.725 | SEO & Marketing | 1 | 0.75 | 0.75
| Design and Prototype (Primarily focused on homepage and forms) | 20 | 2.5 | PM | 1 | 1.725 | 1.725
| Marketing and SEO (Site is SEO ready, No SEO activities included) | 6 | 0.75 | BA | 1 | 2 | 2
| Development |  |  | QA | 1.5 | 3.7833 | 5.675
| Application Basic Setup | 4 | 0.5 | Total |  |  | 29.15
Admin
1 | Manage Shops | 8 | 1
2 | Approve Shop | 2 | 0.25 | Total Delivery days | 17.2833 | 3.4567
3 | Manage RFQ | 6 | 0.75 | Total Effort | 29.15 | (+1 Day deployment)
4 | Create Car List | 8 | 1
5 | Manage Spare Parts list | 8 | 1
6 | Google Analytics Dashboard + Reports based on Site Statistics (minimal, to setup the framework and base) | 8 | 1
7 | Create spare parts & Car list based on RFQ (upload pdf, car images, spare parts images) | 8 | 1 | Contingency: +/- 15%
| Seller | [5 empty] | SEO
8 | Update Shop Profile or Register Shop Profile | 8 | 1
9 | CAPTCHA for profile update | 6 | 0.75
10 | Email Validation | 4 | 0.5
11 | Register Seller | 6 | 0.75
| Customer (Buyer) |  | 0
12 | Create RFQ | 8 | 1
13 | Shop directory listing | 8 | 1
15 | Advanced search (By shop, spare parts, region, Car Models etc) | 8 | 1
16 | Filter by distance, rating, alphabetical | 6 | 0.75
17 | Click to call shop ( Reveal number not the actual click to call implementation) | 1 | 0.125
18 | email to shop (Opens up mail client when you click the email address) | 1 | 0.125
19 | Find shop on map (Open up Google maps with the given cordinates) | 2 | 0.25
20 | Home page (Build only, no room for redesign or expiriments) | 8 | 1
System features
20 | Bilingual Site (Arabic + English) | 12 | 1.5
21 | Authentication & authorization | 4 | 0.5
22 | Auditing & logging | 4 | 0.5
23 | Exception handling | 4 | 0.5
Quality Assurance
25 | QA & Bug Fixing | 41.4 | 5.175
26 | UAT | 4 | 0.5
27 | Deployment | 4 | 0.5
| Total Effort | 247.2 | 30.9
Assumptions
WhatsApp Automation is not practical