## Transguard PRO Services-18 May
Si No | Feature List | Assumptions/Notes | Days | Hours
1.1 | User Registration to the system | Using a unique userId/email Id and Password | 2.5 | 20
1.2 | user logs in though the online system (User ID, Password) | Login application with created userID and password, logout button for safe exit from profile, Forgot password option to reset the password. | 1 | 8
1.3 | Dashboard listing with Current ongoing transactions, New Service Requests, Check Status, Request Quote, Cancel Request (Subject to acceptance from PRO Admin) - Under Service Request (New Employment Visa requests, Cancellations, NOC Access Cards, Pass Request, Business Visas, Attestations, Dependent & other PRO service request) |  | 2.5 | 20
1.4 | Flexibility to add more elements into the drop down for Service requests. | User will be able to add more service request as wish | 1 | 8
1.5 | Able to attach documents/download checklist after user links on certain request types | Certain request had an option to provide documents so that users can download those docs. Please specify doc types. | 1.5 | 12
1.6 | Dashboard to carry information on all (Historical) previous & existing transactions |  | 2.5 | 20
1.7 | All information pertaining to the list of employees with client to be available on the dashboard (Name, PP details, Visa info, OHC info and similar information) |  | 1.5 | 12
1.8 | PRO Requests page with -Request for Salary Certificate with language option with any English/Hindi or Both along with Generic or Addressed as provided -Request NOC for Liquor License, Embassy/Consulate with country specified, RTA (Application for Driving License), specify license type (private car, motorcycle,) - Employment/Service Certificate Request -NOC for new employer - Other Requests |  | 2.5 | 20
1.9 | Business Visa checklist for download and Option to attach required docs. Also able to send the same to PRO team | Specify doc Types | 3 | 24
1.1 | For all transactions, an option to update action and email sent to client with reminder set for next action |  | 3 | 24
1.11 | Reports – Active transactions, cost incurred, TG fees, current status |  | 3.5 | 28
1.12 | Able to Request for document collection by TG |  | 2.5 | 20
1.13 | An option to add special notes (to add anything specific to the case) | Text field | 0.5 | 4
1.14 | Feedback page With predefined categories (PRO Requests, Business Visa, Access Card,Attestations,Dependent Visa,Consulate,Other Queries | User select a category and provide the feedback | 2 | 16
1.15 | Notification page with pending notifications with a red circle and the number of notifications pending. Which also highlight the last action taken. |  | 2.5 | 20
1.16 | An option to extract a report on total bills associated with the transactions upon closure of case / month |  | 2.5 | 20
1.17 | Request for Quote Option |  | 2 | 16
1.18 | On submission of request – client should receive an acknowledgement confirming acceptance, additional docs required/ other comments | With a Request for Quote Option and by submitting the same user receive acknowledgement confirming acceptance, additional docs required/ other comments | 1.5 | 12
1.19 | Log out feature to allow user to return to login page.` |  | 0.5 | 4
1.2 | Case ID to be generated for every new request | Unique track ID for all request | 1 | 8
0
| Customer Web portal |  |  | 0
2.1 | Accessible through desktop web browser or mobile web browser | Compatible with Chrome, Mozilla and IE. | 0.5 | 4
2.2 | Can integrate login portal on Transguard Workforce Solutions web page | A link will be given in the website to the application | 0.5 | 4
2.3 |  |  |  | 0
2.4 | Guest option | Guest user can navigate through the website | 4 | 32
0
| WFS Dashboard/Back End System |  |  | 0
3.1 | Pro Admin can view requests from clients under different categories |  | 1 | 8
3.2 | Super Admin can manage rights and access permission of users including Admin |  | 3 | 24
3.3 | Logged Admin can review all ‘open requests’ received from employees with oldest request visible on top(highlighting the days the case has taken ) |  | 2.5 | 20
3.4 | Request lines summarizes Name, Client, Type of request, contact number, email ID |  | 1.5 | 12
3.5 | Super User can assign request to each Admin member. |  | 1 | 8
3.6 | PRO Admin member can select a request to action. Once selected request is moved to ‘Request in process’ list |  | 1.5 | 12
3.7 | PRO Admin can upload document and send to requester. |  | 0.5 | 4
3.8 | PRO admin can select close request once completed. When the request is closed, it will move to ‘Request close list’ |  | 1 | 8
3.9 | Dashboard to be divided into 3 segments. Client wise 1. Open requests 2. Requests in Process 3. Requests closed in current month Summary of all transactions |  | 1.5 | 12
3.1 | SLA configuration |  | 3 | 24
3.11 | User profile/role configuration |  | 1 | 8
3.12 | Request type to have associated SLA turnaround time. If 50% of the SLA Time has passed the request should display green. If 75% of the SLA time has passed the request should display amber. If 100% of the SLA time has passed the request should display red. |  | 3 | 24
3.13 | Reporting feature in the dashboard to analyze data. • Report by request type • Time taken from request start to close • PRO Admin performance based on SLA • Total number of requests by date period • Report by contract |  | 3.5 | 28
3.14 | Ticket history |  | 1 | 8
4.1 | Additional page for transaction costs (cash / Portal /Card) – should be linked to a reimburse claim form for submission of claims. |  | 3.5 | 28
4.2 | Application hosting model as cloud or on-premise |  | 1 | 8
4.3 | Office 365 integration for email communication |  | 4.5 | 36
0
| Future(Nice to have) |  |  | 0
5.1 | Functionality to store employee document details such as: • Passport • Visa • Medical Insurance • Business visa copies • Pass Information (JAFZA, DIFC, TECOM) | The application will allow to store the employee document as part of their profile. | 1.5 | 12
5.2 | Automatic reminders for renewals |  | 1 | 8
5.3 | Inputs for invoice generation |  | 2 | 16
5.4 | Scheduling of PRO |  | 2 | 16
5.5 | Float management (recording cash transactions against the case), claim |  | 1 | 8
5.6 | Option to add multiple bills to one case |  | 1 | 8
5.7 | Possibility that its connected to the PORTAL for JAFZA, DIFC |  |  | 0
5.8 | ERP integration for PRO requests | Details should be provided | 5 | 40
0
| Security |  |  | 0
| Basic Security Features including Access Control Requirements, System and data integrity, privacy and confidentiality, & Application security. |  |  | 0
|  | Web |  |  | Delivery Time | Resources
|  | HTML | 10 |  | 10 | 1
|  | Design | 3 |  | 3 | 1
|  | SRS | 3
|  | Functional Spec | 3
|  | Development | 92 |  | 50 | 2 | (1 Senior + 1 Junior)
|  | Testing | 27.6 |  | 15 | 2 | (1 Senior + 1 Junior)
|  | Effort in Man Days | 138.6
Mobile (Cutomers)
|  | iOS Effort | 28
|  | Android | 26
|  | Effort in Man Days | 54 |  | 28 | 1
|  | Total Effort in Man Days (Web + Mobile) | 192.6 |  | 26 | 1
|  | Delivery Time Line in Man Days | 78

## Sheet1
Attestation Services
MOFA
MOJ
Dubai Court
POA Attestations
House Contract Ejari
Global Education
Marriage Certificate
Birth Certificate
Typing services
Entry Permit
Residence Permit
Medical
Emirates ID
Change Status
Cancellations
UAE Legal Translations
ProServices
Issuing Entry Permit for dependents
Medical & EID typing and Full assistance with both these services (pick up and drop off available)
Visa Stamping & Change Status’s for dependents
Passport and EID tracking & Delivery
Visa Cancellation for dependents
Labour Card Cancellation support
English to Arabic NOC’s
Holding the dependents (to avoid visa cancellations of dependents when the sponsor is switching jobs)
Family Visit and Tourist Visas
Visit Visa for family and Friends
Tourist Visa for Family and Friends
On Arrival Visa Extensions Inside UAE
Tourist Visa Extensions
Visa Types: 14 days, 30 days, 90 days
Oman Border – New Visa for On Arrival Passports
Marhaba Service (we need 24 hours’ notice)
DMCC, DAFZA, JAFZA & Tecom PRO Service
New Employment Visa
Govt to Govt Transfer
Internal Transfers
Visa Cancellations and Transfers
Medical & EID typing and Full assistance with both these services (pick up and drop off available)
Holding the dependents (to avoid visa cancellations of dependents when the sponsor is switching jobs)
Access Cards
Job Title Amendment
NOC’s
Updating employee salary details with JAFZA
DMCC, DAFZA, JAFZA & Tecom: Secretarial Services (per hour basis, please request for a quote)
New Company Business Setups
Trade License Renewals, Concordia
Liquidation of companies who wish to close their Businesses
De-registration Support Services.
Consulates Support in Dubai & Embassy Support in Abu Dhabi
Document Checklists for Business and Tourist Visit Visa
PRO Assistance in Pick up and drop off available.
PRO Assistance in Interviews at consulates.
To name a few: (KSA, Nigeria, Schengen, Angola, South Africa, China, Brazil, Egypt, Ethiopia, Ghana, Russia, India, Pakistan, Morocco)
Abu Dhabi Immigration (All Services: Immigration, Labour, Dependents, Attestations, Employee Visa, Office Inspections etc)
Quota Creation & Work Contract approval online for employees
Visa Applications for Employees (Signatory attendance will be required)
Visa Cancellation for dependents
Issuing Entry Permit for dependents
Visa Stamping & Change Status’s for dependents
Medical & EID typing and Full assistance with both these services (pick up and drop off available)
Passport and EID tracking & Delivery