## Transguard PRO Services-18 May
Si No | Feature List | Assumptions/Notes | Days | Hours
1.1 | User Registration to the system | Using a unique userId/email Id and Password | 2.5 | 20
1.2 | user logs in though the online system (User ID, Password) | Login application with created userID and password, logout button for safe exit from profile, Forgot password option to reset the password. | 1 | 8
1.3 | Dashboard listing with Current ongoing transactions, New Service Requests, Check Status, Request Quote, Cancel Request (Subject to acceptance from PRO Admin) - Under Service Request (New Employment Visa requests, Cancellations, NOC Access Cards, Pass Request, Business Visas, Attestations, Dependent & other PRO service request) |  | 2.5 | 20
1.4 | Flexibility to add more elements into the drop down for Service requests. | User will be able to add more service request as wish | 1 | 8
1.5 | Able to attach documents/download checklist after user links on certain request types | Certain request had an option to provide documents so that users can download those docs. Please specify doc types. | 1.5 | 12
1.6 | Dashboard to carry information on all (Historical) previous & existing transactions |  | 2.5 | 20
1.7 | All information pertaining to the list of employees with client to be available on the dashboard (Name, PP details, Visa info, OHC info and similar information) |  | 1.5 | 12
1.8 | PRO Requests page with -Request for Salary Certificate or Addressed as provided -Request NOC for Liquor License, Embassy/Consulate with country specified, RTA (Application for Driving License), specify license type (private car, motorcycle,) - Employment/Service Certificate Request -NOC for new employer - Other Requests |  | 28 | 224
| Forms (Please refer sheet "Forms" |  | 99 | 792
| LDAP integration |  | 3 | 24
1.9 | Business Visa checklist for download and Option to attach required docs. Also able to send the same to PRO team | Specify doc Types | 3 | 24
1.1 | For all transactions, an option to update action and email sent to client with reminder set for next action |  | 3 | 24
1.11 | Reports – Active transactions, cost incurred, TG fees, current status |  | 3.5 | 28
1.12 | Able to Request for document collection by TG |  | 2.5 | 20
1.13 | An option to add special notes (to add anything specific to the case) | Text field | 0.5 | 4
1.14 | Feedback page With predefined categories (PRO Requests, Business Visa, Access Card,Attestations,Dependent Visa,Consulate,Other Queries | User select a category and provide the feedback | 2 | 16
1.15 | Notification page with pending notifications with a red circle and the number of notifications pending. Which also highlight the last action taken. |  | 2.5 | 20
1.16 | An option to extract a report on total bills associated with the transactions upon closure of case / month |  | 2.5 | 20
1.17 | Request for Quote Option |  | 2 | 16
1.18 | On submission of request – client should receive an acknowledgement confirming acceptance, additional docs required/ other comments | With a Request for Quote Option and by submitting the same user receive acknowledgement confirming acceptance, additional docs required/ other comments | 1.5 | 12
1.19 | Log out feature to allow user to return to login page.` |  | 0.5 | 4
1.2 | Case ID to be generated for every new request | Unique track ID for all request | 1 | 8
0
| Customer Web portal |  |  | 0
2.1 | Accessible through desktop web browser or mobile web browser | Compatible with Chrome, Mozilla and IE. | 0.5 | 4
2.2 | Can integrate login portal on Transguard Workforce Solutions web page | A link will be given in the website to the application | 0.5 | 4
2.3 |  |  |  | 0
2.4 | Guest option | Guest user can navigate through the website | 4 | 32
0
| WFS Dashboard/Back End System |  |  | 0
3.1 | Pro Admin can view requests from clients under different categories |  | 1 | 8
3.2 | Super Admin can manage rights and access permission of users including Admin |  | 3 | 24
3.3 | Logged Admin can review all ‘open requests’ received from employees with oldest request visible on top(highlighting the days the case has taken ) |  | 2.5 | 20
3.4 | Request lines summarizes Name, Client, Type of request, contact number, email ID |  | 1.5 | 12
3.5 | Super User can assign request to each Admin member. |  | 1 | 8
3.6 | PRO Admin member can select a request to action. Once selected request is moved to ‘Request in process’ list |  | 1.5 | 12
3.7 | PRO Admin can upload document and send to requester. |  | 0.5 | 4
3.8 | PRO admin can select close request once completed. When the request is closed, it will move to ‘Request close list’ |  | 1 | 8
3.9 | Dashboard to be divided into 3 segments. Client wise 1. Open requests 2. Requests in Process 3. Requests closed in current month Summary of all transactions |  | 1.5 | 12
3.1 | SLA configuration |  | 3 | 24
3.11 | User profile/role configuration |  | 1 | 8
3.12 | Request type to have associated SLA turnaround time. If 50% of the SLA Time has passed the request should display green. If 75% of the SLA time has passed the request should display amber. If 100% of the SLA time has passed the request should display red. |  | 3 | 24
3.13 | Reporting feature in the dashboard to analyze data. • Report by request type • Time taken from request start to close • PRO Admin performance based on SLA • Total number of requests by date period • Report by contract |  | 3.5 | 28
3.14 | Ticket history |  | 1 | 8
4.1 | Additional page for transaction costs (cash / Portal /Card) – should be linked to a reimburse claim form for submission of claims. |  | 3.5 | 28
4.2 | Application hosting model as cloud or on-premise |  | 1 | 8
4.3 | Office 365 integration for email communication |  | 4.5 | 36
0
| Future(Nice to have) |  |  | 0
5.1 | Functionality to store employee document details such as: • Passport • Visa • Medical Insurance • Business visa copies • Pass Information (JAFZA, DIFC, TECOM) | The application will allow to store the employee document as part of their profile. | 1.5 | 12
5.2 | Automatic reminders for renewals |  | 1 | 8
5.3 | Inputs for invoice generation |  | 2 | 16
5.4 | Scheduling of PRO |  | 2 | 16
5.5 | Float management (recording cash transactions against the case), claim |  | 1 | 8
5.6 | Option to add multiple bills to one case |  | 1 | 8
5.7 | Possibility that its connected to the PORTAL for JAFZA, DIFC |  |  | 0
5.8 | ERP integration for PRO requests | Details should be provided | 5 | 40
0
| Security |  |  | 0
| Basic Security Features including Access Control Requirements, System and data integrity, privacy and confidentiality, & Application security. |  |  | 0
|  | Web |  |  | Delivery Time | Resources
|  | HTML | 11 |  | 10 | 1
|  | Design | 3 |  | 3 | 1
|  | SRS | 3
|  | Functional Spec | 3
|  | Development | 219.5 |  | 100 | 2 | (1 Senior + 1 Junior)
|  | Testing | 65.85 |  | 30 | 2 | (1 Senior + 1 Junior)
|  | Effort in Man Days | 305.35
Mobile (Cutomers)
|  | iOS Effort | 90
|  | Android | 85
|  | Effort in Man Days | 175 |  | 45 | 1
|  | Total Effort in Man Days (Web + Mobile) | 480.35 |  | 40 | 1
|  | Delivery Time Line in Man Days | 200

## Forms
Forms | Effort
a. Attestation services Local and Global: -
a. Attestations from MOFA, MOJ, Dubai Court, POA Attestations, House Contract Ejari | 3
b. Global Education, Marriage, Birth Certificate Attestations | 2
c. UAE Legal Translations | 2
d. General Online - Typing Services: (you don’t need to visit the Typing Centers)
o Entry Permit | 2
o Residence Permit | 2
o Medical | 2
o Emirates ID | 2
o Change Status | 2
o Cancellations | 2
b. Pro Service in Main Immigration & MOL: - *Dependents Include: Parents, Husband, Wife, Kids, Maids, Drivers
a. Issuing Entry Permit for dependents | 2
b. Medical & EID typing and Full assistance with both these services (pick up and drop off available) | 2
c. Visa Stamping & Change Status’s for dependents | 2
d. Passport and EID tracking & Delivery | 2
e. Visa Cancellation for dependents | 2
f. Labour Card Cancellation support | 2
g. English to Arabic NOC’s | 4
h. Holding the dependents (to avoid visa cancellations of dependents when the sponsor is switching jobs) | 2
c. Family Visit and Tourist Visas
a. Visit Visa for family and Friends | 2
b. Tourist Visa for Family and Friends | 2
c. On Arrival Visa Extensions Inside UAE | 2
d. Tourist Visa Extensions | 2
e. Visa Types: 14 days, 30 days, 90 days | 2
f. Oman Border – New Visa for On Arrival Passports | 2
g. Marhaba Service (we need 24 hours’ notice) | 2
d. DMCC, DAFZA, JAFZA & Tecom PRO Service
a. New Employment Visa | 2
b. Govt to Govt Transfer | 2
c. Internal Transfers | 2
d. Visa Cancellations and Transfers | 2
e. Medical & EID typing and Full assistance with both these services (pick up and drop off available) | 2
f. Holding the dependents (to avoid visa cancellations of dependents when the sponsor is switching jobs) | 2
g. Access Cards | 2
h. Job Title Amendment | 2
i. NOC’s | 2
j. Updating employee salary details with JAFZA | 2
e. DMCC, DAFZA, JAFZA & Tecom: Secretarial Services (per hour basis, please request for a quote)
a. New Company Business Setups | 2
b. Trade License Renewals, Concordia | 2
c. Liquidation of companies who wish to close their Businesses | 2
d. De-registration Support Services. | 2
f. Consulates Support in Dubai & Embassy Support in Abu Dhabi
a. Document Checklists for Business and Tourist Visit Visa | 2
b. PRO Assistance in Pick up and drop off available. | 2
c. PRO Assistance in Interviews at consulates. | 2
To name a few: (KSA, Nigeria, Schengen, Angola, South Africa, China, Brazil, Egypt, Ethiopia, Ghana, Russia, India, Pakistan, Morocco)
g. Abu Dhabi Immigration (All Services: Immigration, Labour, Dependents, Attestations, Employee Visa, Office Inspections etc)
a. Quota Creation & Work Contract approval online for employees | 2
b. Visa Applications for Employees (Signatory attendance will be required) | 2
c. Visa Cancellation for dependents | 2
d. Issuing Entry Permit for dependents | 2
e. Visa Stamping & Change Status’s for dependents | 2
f. Medical & EID typing and Full assistance with both these services (pick up and drop off available) | 2
g. Passport and EID tracking & Delivery | 2
99