## Proticketing
| Transguard Proticketing System |  | 15/01/2018
Monday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 5 | 5
| Business analysis | 32 | 4 | Sr Developer | 1 | 50 | 50 | 76 | 125 | 100.5 | 100
| Project Management | 81 | 10.125 | Jr Developer | 1 | 50 | 50
| Design and Prototype | 40 | 5 | IOS | 1 | 25 | 25
| Development |  |  | PM | 1 | 10.125 | 10.125
| Application Basic Setup | 8 | 1 | BA | 1 | 4 | 4
| Proticketing System |  |  | Tech writer | 1 | 3 | 3
1 | Client Registration, Email Validation, Forgot Password, Login, Logout, Remember Password | 12 | 1.5 | QA | 2 | 23.7812 | 47.5625
2 | Dashboard Services |  | 0 | Total |  |  | 194.6875
3 | Expandable tabs or similar to select different forms and services | 12 | 1.5
4 | Filter Criteria to sort and search service requests | 12 | 1.5
5 | Display requests received with status and urgency | 12 | 1.5 | Total Delivery days | 78.7812
6 | View cancellations and amendments | 12 | 1.5 | Total Effort | 194.6875 | (+1 Day deployment)
7 | Ability to add additional information to request (Like attachments) | 8 | 1
8 | Historical reports | 24 | 3
9 | Configure SLA | 8 | 1
10 | Create users, roles and clients | 8 | 1
11 | Reassign tasks | 8 | 1
12 | Notifications | 8 | 1
Forms
| Attestation Services |  | 0
13 | MOFA | 6 | 0.75
14 | MOJ | 6 | 0.75
16 | Dubai Court | 6
17 | POA Attestations | 6 | 0.75
18 | House Contract Ejari | 6 | 0.75
19 | Global Education | 6 | 0.75
20 | Marriage Certificate | 6 | 0.75
21 | Birth Certificate | 6 | 0.75
22 | Typing services |  | 0
23 | Entry Permit | 6 | 0.75
24 | Residence Permit | 6 | 0.75
25 | Medical | 6 | 0.75
26 | Emirates ID | 6 | 0.75
27 | Change Status | 6 | 0.75
28 | Cancellations | 6 | 0.75
29 | UAE Legal Translations | 6 | 0.75
30 | ProServices |  | 0
31 | Issuing Entry Permit for dependents | 6 | 0.75
32 | Medical & EID typing and Full assistance with both these services (pick up and drop off available) | 6 | 0.75
33 | Visa Stamping & Change Status’s for dependents | 6 | 0.75
34 | Passport and EID tracking & Delivery | 6 | 0.75
35 | Visa Cancellation for dependents | 6 | 0.75
36 | Labour Card Cancellation support | 6 | 0.75
37 | English to Arabic NOC’s | 6 | 0.75
38 | Holding the dependents (to avoid visa cancellations of dependents when the sponsor is switching jobs) | 6 | 0.75
39 | Family Visit and Tourist Visas |  | 0
40 | Visit Visa for family and Friends | 6 | 0.75
41 | Tourist Visa for Family and Friends | 6 | 0.75
42 | On Arrival Visa Extensions Inside UAE | 6 | 0.75
43 | Tourist Visa Extensions | 6 | 0.75
44 | Visa Types: 14 days, 30 days, 90 days | 6 | 0.75
45 | Oman Border – New Visa for On Arrival Passports | 6 | 0.75
46 | Marhaba Service (we need 24 hours’ notice) | 6 | 0.75
47 | DMCC, DAFZA, JAFZA & Tecom PRO Service |  | 0
48 | New Employment Visa | 6 | 0.75
49 | Govt to Govt Transfer | 6 | 0.75
50 | Internal Transfers | 6 | 0.75
51 | Visa Cancellations and Transfers | 6 | 0.75
52 | Medical & EID typing and Full assistance with both these services (pick up and drop off available) | 6 | 0.75
53 | Holding the dependents (to avoid visa cancellations of dependents when the sponsor is switching jobs) | 6 | 0.75
54 | Access Cards | 6 | 0.75
55 | Job Title Amendment | 6 | 0.75 |  | Onsite inspection (mobile App)
56 | NOC’s | 6 | 0.75
57 | Updating employee salary details with JAFZA | 6 | 0.75
58 | DMCC, DAFZA, JAFZA & Tecom: Secretarial Services (per hour basis, please request for a quote) |  | 0
59 | New Company Business Setups | 6 | 0.75
60 | Trade License Renewals, Concordia | 6 | 0.75
61 | Liquidation of companies who wish to close their Businesses | 6 | 0.75
62 | De-registration Support Services. | 6 | 0.75
63 | Consulates Support in Dubai & Embassy Support in Abu Dhabi |  | 0
64 | Document Checklists for Business and Tourist Visit Visa | 6 | 0.75
65 | PRO Assistance in Pick up and drop off available. | 6 | 0.75
66 | PRO Assistance in Interviews at consulates. | 6 | 0.75
67 | To name a few: (KSA, Nigeria, Schengen, Angola, South Africa, China, Brazil, Egypt, Ethiopia, Ghana, Russia, India, Pakistan, Morocco) | 6 | 0.75
68 | Abu Dhabi Immigration (All Services: Immigration, Labour, Dependents, Attestations, Employee Visa, Office Inspections etc) |  | 0
69 | Quota Creation & Work Contract approval online for employees | 6 | 0.75
70 | Visa Applications for Employees (Signatory attendance will be required) | 6 | 0.75
71 | Visa Cancellation for dependents | 6 | 0.75
72 | Issuing Entry Permit for dependents | 6 | 0.75
73 | Visa Stamping & Change Status’s for dependents | 6 | 0.75
74 | Medical & EID typing and Full assistance with both these services (pick up and drop off available) | 6 | 0.75
75 | Passport and EID tracking & Delivery | 6 | 0.75
76 | Other Services |  | 0
77 | Salary Certificate (English & Arabic) | 6 | 0.75
78 | NOC for Liquor License | 6 | 0.75
79 | NOC from Consulates | 6 | 0.75
80 | Application for driving license (RTA) | 6 | 0.75
81 | Employment Certificate | 6 | 0.75
82 | NOC for New employer | 6 | 0.75
Misc Features
79 | send email | 8 | 1
80 | Reports | 8 | 1
81 | send email to admin | 8 | 1
82 | notification page | 8 | 1
83 | Extract reports fro billing purposes | 8 | 1
84 | request for quote option | 8 | 1
85 | caseID for every request | 8 | 1
System features
108 | Authentication & authorization | 8 | 1
109 | Auditing & logging | 8 | 1
110 | Exception handling | 8 | 1
111 | Manage files and folders | 12 | 1.5
112 | LDAP Integration | 12 | 1.5
113 | SMS & Email | 12 | 1.5
114 | ERP integration for PRO requests | 40 | 5
115 | Scheduling | 12 | 1.5
116 | Payment Gateway Integration |  | 0
117 | Invoice Generation | 16 | 2
| English and Arabic | 40 | 5
| Office 365 integration for email communication | 24 | 3
| Application hosting model as cloud or on-premise | 24 | 3
| Reports | 40 | 5
Quality Assurance
| QA & Bug Fixing | 364.5 | 45.5625
| UAT | 16 | 2
| Deployment per instance | 8 | 1
| Total Effort | 1351.5 | 168.1875
Assumptions
Pre defined format for print and format will designed in HTML and print in plain paper
Need clarification
Mobile App For TSD Inspector. App should work offline
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118