## Android
Employee smart app
# | Modules | Hours | Days
UI Design
| Page Design | 108 | 13.5
Development
1 | Basic Setup | 8 | 1
2 | Splash Screen | 2 | 0.25
3 | Employee login through TG ID and password | 4 | 0.5
4 | Mobile App Home page | 6 | 0.75
5 | Employee photo taken from HR360 | 32 | 4
6 | Upload photo if picture unavailable from HR 360 | 16 | 2
7 | Log Out | 1 | 0.125
8 | Personal Information | 2 | 0.25
9 | HR Requests | 2 | 0.25
10 | Payroll | 2 | 0.25
11 | Leave Management | 10 | 1.25
12 | Feedback | 2 | 0.25
13 | Notifications | 8 | 1
14 | Personal Information edit page | 4 | 0.5
15 | Request Salary Certificate | 10 | 1.25
16 | Request NOC for the following | 2 | 0.25
17 | Request Salary Transfer Letter | 4 | 0.5
18 | Employment/Service Certificate Request | 6 | 0.75
19 | NOC for new employer | 6 | 0.75
Api Integration
| Api Integration | 25.5 | 3.1875
Testing
| Developer side testing | 16 | 2
| Total effort |  | 34.5625
Assumption
This application will support Sdk version 19(kitkat) and above
This application designed for mobiles in portrait mode
HR360 Android SDK and Documentation will be provide

## Web
| Employee Smart App |  | 2018-02-20 | Original Effort | 98
|  |  | Tuesday | delivery | 48
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 5 | 5
1 | Business analysis | 24 | 3 | Sr Developer | 1 | 28.5 | 28.5 | 59 | 57
2 | Project Management | 47.2 | 5.9 | Jr Developer | 1 | 28.5 | 28.5
3 | Project Documentation (SRS, Scope, WBS etc.) | 8 | 1 | PM | 1 | 5.9 | 5.9
4 | Complete running prototype | 40 | 5 | BA | 1 | 3 | 3
| Development |  |  | Tech writer | 0 | 4 | 0
| General |  |  | QA | 2 | 10.65 | 21.3
1 | Employee login / Password Reset | 6 | 0.75 | Total |  |  | 92.2
2 | Employee dashboard with pic from HR360 (including personal details) | 8 | 1
2 | upload Photo if absent | 4 | 0.5 |  |  |  |  | <--- This would be the minimum time required
3 | Home page links (Personal Information, HR Requests, Payroll, Leave Management, Feedback, Notifications, Log Out) | 4 | 0.5 | Delivery Days | 44.15
4 | Update Personal Information | 8 | 1 | Total Effort | 92.2
5 | HR Requests
| Salary Certificate (English, Arabic or both) with addressed to | 12 | 1.5 | API to Oracle
6 | NOC |  | 0 | login
7 | Liquor licensce | 12 | 1.5 | employee details with pic
8 | Embassy / counsellate | 12 | 1.5 | update emp details
9 | RTA with licensce type | 12 | 1.5 | payslips
10 | NOC for new employer | 12 | 1.5 | leave management
11 | Salaray Transfer letter | 12 | 1.5 | user roles
12 | Control measures for salary transfer | 16 | 2 | document management
13 | Payroll
| Access payslips by month | 12 | 1.5
14 | Save / Print / Email payslip | 8 | 1
Leave Management
| Leave balance | 6 | 0.75
16 | Line manager | 6 | 0.75
17 | Annual Leave request | 6 | 0.75
| unpaid leave request | 6 | 0.75
| sick leave request with sick leave certificate upload functionality | 12 | 1.5
| approval status for leaves | 6 | 0.75
| Air ticket request | 6 | 0.75
| Flight Information (from to date, destination, departure & return date) | 12 | 1.5
Feedback
| Feedback to admin | 12 | 1.5
| Categories (Payroll, Leave, Visa, Medical Insurance, Place of Work, Contract, Others) | 4 | 0.5
Notifications page
| Response from HR to requests | 6 | 0.75
| General updates on plan changes etc | 12 | 1.5
Back End Systems
| manage users (Employee, HR managers) | 12 | 1.5
| Dashboard view of all open requests (sorted) + in process + closed | 12 | 1.5
| reassign requests appropriate hr admins | 12 | 1.5
| HR admin acknowledges request (request status changed to in process or closed) | 12 | 1.5
| HRADMIN upload response docs against employee requests | 8 | 1
| Assign SLA to requests | 8 | 1
| Reports (by request type, time taken to process, HR ADMIN SLA, total processed by time period) | 24 | 3
| Assign HR manager to employee (manage hierarchy via application- NOT ORACLE) | 16 | 2
| Store employee documents (passport, visa, insurance, contracts, pass info) | 16 | 2
| ORACLE API Access | 24 | 3
| API access for mobile App | 40 | 5
System features
| Auditing & logging | 6 | 0.75
| Exception handling | 6 | 0.75
| Security | 8 | 1
| Bilingual | 20 | 2.5
| Document management | 16 | 2
Quality Assurance
| QA & Bug Fixing | 166.4 | 20.8
| UAT | 4 | 0.5
| Deployment | 4 | 0.5
| Total Effort | 765.6 | 95.7