## Hydraulic Flow Model
| HydraulicFlow Model |  | 2017-11-05
Thursday
| Module | Hours | Man Days | Web Development
| Initiation |  |  |  | No | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 4 | 4
2 | Functional Specification | 8 | 1 | Sr Developer | 1 |  | 0 | 15 | 15
3 | Project Management | 16 | 2 | Jr Developer | 1 | 15 | 15
4 | Finalize and purchase Responsive Umbraco Theme |  | 0 | PM | 1 | 2 | 2 | [6 empty] | 12.5
5 | Complete running prototype | 32 | 4 | BA | 1 | 2 | 2
| Development |  |  | QA | 1 | 7 | 7
1 | Home Page | 8 | 1 | Total |  |  | 30
2 | Contact us | 4 | 0.5
3 | About | 4 | 0.5
4 | workflow | 16 | 2 | Total Delivery days | 26 |  |  |  | Resource/Skill | Month 1 | Month 2 | Month 3
| Input page | 4 | 0.5 | Total Effort | 30 | (+1 Day deployment) |  |  | Proj. Manager | 16 | 0 | 0 | 16 | 16
5 | Calculate of plastic velocity (PV) | 4 | 0.5 | [5 empty] | Architect | 8 | 0 | 0
6 | calculate of Yeild Point (Dependency 1) | 4 | 0.5 | [5 empty] | Business Analyst | 16 | 0 | 0 | 16 | 16
7 | Calculate Power Law 'n' (1,2) | 4 | 0.5 |  |  | 240 |  |  | User Experience | 32 | 0 | 0 | 32 | 32
8 | Calculate Power Law 'K' ( 3,2) | 4 | 0.5 | [5 empty] | Team Lead Web | 8 | 0 | 0 | 112 | 120
9 | Step 1 : Calculate Flow Velocity | 2 | 0.25 | [5 empty] | Web Developer | 104 | 0 | 0
10 | Step 2 : Calculate Total Flow Area | 2 | 0.25 | [5 empty] | QA | 56 | 0 | 0 | 56 | 56
11 | Step 2 : Calculate Pressure loss at Bit | 2 | 0.25 | [5 empty] | Total Effort | 240 |  | 240 | 30
12 | Step 3 : Calculate Critical Velocity | 2 | 0.25 | [8 empty] | 30
13 | Step 3 : Determine Turbulent or Laminar for BPM | 4 | 0.5
14 | Step 3 : calculate Ps, P1, P2 (laminar) | 4 | 0.5 | [5 empty] | 0
15 | Step 3 : calculate ps, P1, P2 (Turbulent) | 4 | 0.5
16 | Step 3 : Determine Turbulent or Laminar for Power Law Fluid | 2 | 0.25
17 | Step 3 : Calculate Wall Sheer Rate Correction | 2 | 0.25
18 | Step 3 : Calculate Viscometer Shear Rate Correction | 4 | 0.5
19 | Step 3 : Calculate Geometry correction factor | 4 | 0.5
20 | Step 3 : Calculate Shear Rate at Wall | 4 | 0.5
21 | Step 3 : Calculate Shear Stress at Wall | 4 | 0.5
22 | Step 3 : Calculate Reynolds Number | 4 | 0.5
23 | Step 3 : Calculate Critical Reynolds Number (Laminar to Transitional) | 2 | 0.25
24 | Step 3 : Calculate Critical Reynolds Number (Transitional to Turbulent) | 2 | 0.25
25 | Step 3 : Determine Frictional Factor | 2 | 0.25
26 | Step 3 : Calculate Frictional Factor ( 𝑁_𝑅𝑒𝐺 ≤ 〖𝑁_𝐶𝑅𝑒〗^𝐿𝑇) | 2 | 0.25
27 | Step 3 : Calculate Frictional Factor (〖𝑁_𝐶𝑅𝑒〗^𝐿𝑇≤ 𝑁_𝑅𝑒𝐺≤ 〖𝑁_𝐶𝑅𝑒〗^𝑇𝑇 ) | 4 | 0.5
28 | Step 3 : Calculate Frictional Factor ( 𝑁_𝑅𝑒𝐺≥ 〖𝑁_𝐶𝑅𝑒〗^𝑇𝑇 ) | 4 | 0.5
29 | Step 3 : Calculate PS, P1, P2 | 4 | 0.5
30 | Step 4 : Ignored | 0 | 0
31 | Step 5 : calculate Pump Pressure | 4 | 0.5
Quality Assurance
34 | QA & Bug Fixing | 48 | 6
35 | UAT | 8 | 1
36 | Deployment | 8 | 1
| Total Effort |  | 31
Estimate Assumptions. Effort does not include languages other than English Creatives will be supplied by Client Development Contingent upon timely feedback from client Does not include hardware or software integration with third party applications or software Determination of fluid models based on deviation of the curve from the Viscometer Data not included AnnularPressure Loss calculation in Conduits P3 and P4 not included because the calculation was ignored
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118

## Sheet1
Determine Recommended Fluid Model |  | Well Data
Calculate Pressure Loss at Surface Flowlines Ps |  | Hole Size
Calculate Pressure Loss inside Pipes P1 and P2 |  | Hole Depth
Calculate Pressure Loss at Bit Nozzle Pb | The total pressure loss is equated as the Pump Pressure ‘Pp’=Ps+P1+P2+Pb+P3+P4 | Casing Inner Diameter
Calculate Pressure Loss in Conduits P3 and P4 | Surface Pressure Loss – Ps | Casing Depth
| Drillstring Pressure Loss – P1 and P2 | Drilling Fluid Parameters
| Annular Pressure Loss – P3 and P4 | Mud Weight
| Bit Pressure Loss – Pb | Viscometer Data
Pipe Data
| Hole Size (Dh) | Outer Diameter
| Hole Depth (MDh) | Inner Diameter
| Casing Inner Diameter (Dc) | Length
| Casing Depth (MDc) | Flowrate
1. Flowrate
Bit Data
Nozzle Size
Number of Nozzles
| Bingham Plastic Model procedure is described from Slide B-8 to Slide B-9 | Coefficient of Discharge
Power Law Model procedure is described from Slide B-10 to Slide B-14

## Sheet2
Pump Pressure (Pp)=Ps+P1+P2+Pb+P3+P4 |  | Q |  | Q=Flow Rate
|  | ID |  | ID=Pipe Inner Diameter
|  | PV |  | Plastic Velocity (PV) | = | Dial Value @ 600 RPM – Dial Value @ 300 RPM
|  | YP |  | Yield Point (YP) | = | Dial Value @ 300 RPM – Plastic Viscosity
|  | n |  | Power Law ‘n’ | = | 3.32×〖𝑙𝑜𝑔〗_10 (〖𝐷𝑖𝑎𝑙〗_(600 𝑅𝑃𝑀)/〖𝐷𝑖𝑎𝑙〗_(300 𝑅𝑃𝑀) )
|  | K |  | power Law ‘K’ | = | 𝐾=(1.066×〖𝐷𝑖𝑎𝑙〗_(300 𝑅𝑃𝑀))/〖511〗^𝑛
|  | Ps |  | Surface Loss Pressure (Ps)
|  | P1,P2 |  | Drill String Pressure Loss
|  | P3,P4 |  | Annular Pressure Loss
|  | Pb |  | Bit Pressure Loss
|  | Dh |  | Hole Size
|  | MDh |  | Hole Depth
|  | Dc |  | Casing Inner Diameter
|  | MDc |  | Casing Depth
|  | 𝜌 |  | 𝜌 - Mud Weight
|  | RPM, DIAL |  | Viscometer Data
|  | OD |  | Pipe Diameter
|  | L |  | Pipe Length
|  | Nd |  | Nozzle Size
Number of Nozzles
|  | Cd |  | Coefficient of Discharge
| Step 1 | V |  | Flow Velocity (V) | = | (24.51*Q)/ID
| Step 2 | TFA |  | Total Flow Area (TFA) | = | (𝑁𝑜 𝑜𝑓 𝑁𝑜𝑧𝑧𝑙𝑒𝑠)/4×𝜋×((𝑁𝑜𝑧𝑧𝑙𝑒 𝑆𝑖𝑧𝑒)/32)^2
|  | Pb |  | Pressure loss at bit (P_b) | = | (𝜌×𝑄)/(12042×〖𝐶_𝑑〗^2×〖𝑇𝐹𝐴〗^2 )
𝜌 - Mud Weight
Q – Flowrate
Cd – Coefficient of Discharge
No of Nozzles
Nozzle Size
| Step 3 | Vc |  | Critical Velocity Vc | = | 67.86/𝜌 [𝑃𝑉/𝐼𝐷+√((𝑃𝑉/𝐼𝐷)^2+9.42×𝜌×𝑌𝑃(4/3) )]
| Bingham Plastic Model |  |  |  |  | 𝜌 - Mud Weight
Plastic Velocity (PV)
ID=Pipe Inner Diameter
Yield Point (YP)
|  |  |  | If V>Vc |  | Turbulent
|  |  |  | If V<Vc |  | Laminar
|  | Ps,P1,P2 |  | Laminar | = | [(𝑃𝑉×𝑉)/(90000×〖𝐼𝐷〗^2 )+𝑌𝑃/(225×𝐼𝐷)]𝐿
Plastic Velocity (PV)
Flow Velacity(V)
ID- Pipe Inner Dia
YP-Yield Point
L-Pipe Length
|  | Ps,P1,P2 |  | Turbulent | = | (𝜌^0.75 𝑉^1.75 〖𝑃𝑉〗^0.25 𝐿)/(2328290.646×〖𝐼𝐷〗^1.25 )
Plastic Velocity (PV)
L-Pipe Length
ID- Pipe Inner Dia
Flow Velocity (V)
𝜌 - Mud Weight
| Power Law Fluid | Ba |  | Wall Sheer Rate Correction | = | [(3𝑛+1)/4𝑛]
Power Law ‘n’
|  | Bx |  | Viscometer Shear Rate Correction |  | [𝑋^(2⁄𝑛)/(𝑛 𝑋^2 )][(𝑋^2−1)/(𝑋^(2⁄𝑛)−1)]
X=1.0678
|  | G |  | Geometry correction factor |  | 𝐵_𝑎/𝐵_𝑥
|  | Yw |  | Shear Rate at Wall |  | (1.6 𝐺 𝑉)/𝐼𝐷
|  | T_w |  | Shear Stress at Wall |  | 1.066×𝐾〖𝛾_𝑤〗^𝑛
Power Law ('K')
|  | Re | N_ReG | Reynolds Number |  | (𝜌𝑉^2)/(19.36 𝜏_𝑤 )
|  | 〖𝑵_𝑪𝑹𝒆〗^𝑳𝑻 |  | Critical Reynolds Number |  | 3470−1370𝑛 | Laminar to Transitional
|  | 〖𝑁_𝐶𝑅𝑒〗^𝑇𝑇 |  | Critical Reynolds Number |  | 4150−1150𝑛^10 | Transitional to Turbulent
|  | f |  | Friction Factor
|  | f |  |  | 𝑁_𝑅𝑒𝐺 ≤ 〖𝑁_𝐶𝑅𝑒〗^𝐿𝑇 | 16/𝑁_𝑅𝑒𝐺
|  | f |  |  | 〖𝑁_𝐶𝑅𝑒〗^𝐿𝑇≤ 𝑁_𝑅𝑒𝐺≤ 〖𝑁_𝐶𝑅𝑒〗^𝑇𝑇 | 〖𝑁_𝐶𝑅𝑒〗^𝐿𝑇≤ 𝑁_𝑅𝑒𝐺≤ 〖𝑁_𝐶𝑅𝑒〗^𝑇𝑇
|  | f |  |  | 𝑁_𝑅𝑒𝐺≥ 〖𝑁_𝐶𝑅𝑒〗^𝑇𝑇 | 𝑎/〖𝑁_𝑅𝑒𝐺〗^𝑏
[5 empty] | a | (〖𝑙𝑜𝑔〗_10 (𝑛)+3.93)/50
[5 empty] | b | (1.75−〖𝑙𝑜𝑔〗_10 (𝑛))/7
|  | Ps,P1,P2 |  | Frictional Pressure Loss |  | (1.076 𝜌 𝑉^2 𝑓 𝐿)/(〖10〗^5 𝐼𝐷)
| Pp |  |  | Pump Pressure |  | Ps+P1+P2+Pb+P3+P4

## Sheet3
Features | Zoom | TokBox | Comments
Base Price (Per minute) | 0.025 | 0.004
Archive (Audio / Video) / Minute | Included | 0.035 | Using ToBox services. Client should also use Amazon to archive for permanent storage
Technical Support / Customer Service (Min per month) | Included | 3000
Screen Sharing (documents, photo & video Clips) | yes | Developer cost | TokBox: Browser extensions need to be developed and they need to be installed on the client browser Zoom: Out of the box implementation
Mobile Phione Screen sharing | Yes | Yes
White Board | Yes | No
API & Mobile SDK | Yes | yes | Zoom Web App opens up in s separate window
Collaboration | Native | Plugin Support | Through Firepad
Scheduling | Yes | Partial | Zoom : Browser extensions as well as integration with microsoft outlook TokBox: Provides a URL which can be mailed to the participants
Annotation & Co-Annotation | Yes | No
Video & Audio Performance | Excellent | Poor | https://vsee.com/videoconference/
TokBox Versus Zoom Market Analysis |  |  | see https://www.datanyze.com/market-share/web-presentation-tools/tokbox-vs-zoom/