## Derby
| Derby |  | 15/01/2018
Monday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 3 | 3
| Business analysis | 12 | 1.5 | Sr Developer | 1 | 24 | 24 | 21.75 | 24 | 25.75 | 24
| Project Management | 18.2 | 2.275 | PM | 1 | 2.275 | 2.275
| Design and Prototype | 24 | 3 | QA | 2 | 3.7875 | 7.575
| Development |  |  | Total |  |  | 36.85
| Application Basic Setup | 8 | 1
Derby Employee Dashboard
1 | Loggedin User Details | 4 | 0.5 | Total Delivery days | 30.7875
2 | Logout / Forgot / Reset Password | 8 | 1 | Total Effort | 36.85 | (+1 Day deployment)
3 | Jobs Assigned (Job Summary) | 6 | 0.75
4 | Alerts based on underestimated job efforts | 6 | 0.75 | Without Extra Effort | 22.5375
5 | TimeSheet Summary | 6 | 0.75 | Extra Effort | 8.25
6 | Time Sheet Report Links | 2 | 0.25
| Employee Assignments |  |  |  | Extra Effort
7 | Fill Time Sheets With Start and End Time | 8 | 1 |  | Alerts based on underestimated job efforts
8 | Timesheet Reports | 8 | 1 |  | Fill Time Sheets With Start and End Time
9 | Accept Jobs | 4 | 0.5 |  | Explanation for alerts on the Dashboard
10 | Apply for leave (or Mark Leave hours) | 12 | 1.5 |  | Add Listing (CSV upload)
11 | Explanation for alerts on the Dashboard | 6 | 0.75 |  | SMS & Email
| ADMIN |  | 0 |  | Reports
12 | Maintain Masters( Leave Type, Drawing Type, Category, Status, Sub Status, Payment Types) | 12 | 1.5 |  | Export to CSV, PDF, DOC
13 | Manage Jobs (Add / Delete / Update) | 8 | 1
14 | Add Listings (Copy Paste): (Add / Delete / Update) | 8 | 1
15 | Add Listing (CSV upload) | 6 | 0.75
16 | View Jobs | 4 | 0.5
17 | View Job Lists | 4 | 0.5
18 | Manage Revisions (Jobs & Job Listings) | 6 | 0.75
19 | Create Invoices (Against Job & Job Listings) | 8 | 1
20 | Manage Invoices (Add / Delete) | 6 | 0.75
21 | Document Transmittal | 8 | 1
System features
22 | Authentication & authorization | 6 | 0.75
23 | Auditing & logging | 6 | 0.75
24 | Exception handling | 6 | 0.75
25 | SMS & Email | 8 | 1
26 | Reports | 8 | 1
27 | Export to CSV, PDF, DOC | 24 | 3
Quality Assurance
| QA & Bug Fixing | 54.6 | 6.825
| UAT | 6 | 0.75
| Deployment per instance | 6 | 0.75
| Total Effort | 326.8 | 40.85
Assumptions
Pre defined format for print and format will designed in HTML and print in plain paper
Need clarification
Mobile App For TSD Inspector. App should work offline
Onsite inspection (mobile App)
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118

## Sheet1
Derby Employee Dashboard
Loggedin User Details
Logout / Forgot / Reset Password
Jobs Assigned (Job Summary)
TimeSheet Summary
Time Sheet Report Links
Employee Assignments
Timesheet Reports
Accept Jobs
Apply for leave (or Mark Leave hours)
ADMIN
Maintain Masters( Leave Type, Drawing Type, Category, Status, Sub Status, Payment Types)
Manage Jobs (Add / Delete / Update)
Add Listings (Copy Paste): (Add / Delete / Update)
View Jobs
View Job Lists
Manage Revisions (Jobs & Job Listings)
Create Invoices (Against Job & Job Listings)
Manage Invoices (Add / Delete)
Document Transmittal
System features
Authentication & authorization
Auditing & logging
Exception handling
Extra Effort
Alerts based on underestimated job efforts
Fill Time Sheets With Start and End Time
Explanation for alerts on the Dashboard
Add Listing (CSV upload)
SMS & Email
Reports
Export to CSV, PDF, DOC