## Derby
| Derby |  | 15/01/2018
Monday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 3 | 3
| Business analysis | 12 | 1.5 | Sr Developer | 1 | 28.5 | 28.5 | 24.5 | 28.5 | 28.5 | 28.5
| Project Management | 20.4 | 2.55 | PM | 1 | 2.55 | 2.55
| Design and Prototype | 24 | 3 | BA | 1 | 1.5 | 1.5
| Development |  |  | QA | 2 | 4.2 | 8.4
| Application Basic Setup | 8 | 1 | Total |  |  | 43.95
Derby Employee Dashboard
1 | Loggedin User Details | 4 | 0.5
2 | Logout / Forgot / Reset Password | 8 | 1 | Total Delivery days | 35.7
3 | Jobs Assigned (Job Summary) | 6 | 0.75 | Total Effort | 44.7 | (+1 Day deployment)
4 | Alerts based on underestimated job efforts | 6 | 0.75
5 | TimeSheet Summary | 6 | 0.75 | Without Extra Effort | 27.45
6 | Time Sheet Report Links | 2 | 0.25 | Extra Effort | 8.25
Employee Assignments
7 | Fill Time Sheets With Start and End Time | 8 | 1 |  | Extra Effort
8 | Timesheet Reports | 8 | 1 |  | Alerts based on underestimated job efforts
9 | Accept Jobs | 4 | 0.5 |  | Fill Time Sheets With Start and End Time
10 | Apply for leave (or Mark Leave hours) | 12 | 1.5 |  | Explanation for alerts on the Dashboard
11 | Explanation for alerts on the Dashboard | 6 | 0.75 |  | Add Listing (CSV upload)
| ADMIN |  |  |  | SMS & Email
12 | Maintain Masters( Leave Type, Drawing Type, Category, Status, Sub Status, Payment Types) | 12 | 1.5 |  | Reports
13 | Manage Jobs (Add / Delete / Update) | 8 | 1 |  | Export to CSV, PDF, DOC
14 | Add Listings (Copy Paste): (Add / Delete / Update) | 12 | 1.5
15 | Add Listing (CSV upload) | 6 | 0.75
16 | View Jobs | 4 | 0.5
17 | View Job Lists | 4 | 0.5
18 | Manage Revisions (Jobs & Job Listings) | 6 | 0.75
19 | Create Invoices (Against Job & Job Listings) | 8 | 1
20 | Manage Invoices (Add / Delete) | 6 | 0.75
21 | Valuation and weightage | 8 | 1
22 | Document Transmittal | 8 | 1
Manager
| Report for total no of hours spent | 6 | 0.75
| Filter results | 4 | 0.5
System features
22 | Authentication & authorization | 6 | 0.75
23 | Auditing & logging | 6 | 0.75
24 | Exception handling | 6 | 0.75
25 | SMS & Email | 8 | 1
26 | Reports | 8 | 1
27 | Export to CSV, PDF, DOC | 24 | 3
Quality Assurance
| QA & Bug Fixing | 61.2 | 7.65
| UAT | 6 | 0.75
| Deployment per instance | 6 | 0.75
| Total Effort | 357.6 | 44.7
Assumptions
Pre defined format for print and format will designed in HTML and print in plain paper
Need clarification
Mobile App For TSD Inspector. App should work offline
Onsite inspection (mobile App)
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118

## Sheet1
Derby Employee Dashboard
Loggedin User Details
Logout / Forgot / Reset Password
Jobs Assigned (Job Summary)
TimeSheet Summary
Time Sheet Report Links
Employee Assignments
Timesheet Reports
Accept Jobs
Apply for leave (or Mark Leave hours)
ADMIN
Maintain Masters( Leave Type, Drawing Type, Category, Status, Sub Status, Payment Types)
Manage Jobs (Add / Delete / Update)
Add Listings (Copy Paste): (Add / Delete / Update)
View Jobs
View Job Lists
Manage Revisions (Jobs & Job Listings)
Create Invoices (Against Job & Job Listings)
Manage Invoices (Add / Delete)
Document Transmittal
System features
Authentication & authorization
Auditing & logging
Exception handling
Extra Effort
Alerts based on underestimated job efforts
Fill Time Sheets With Start and End Time
Explanation for alerts on the Dashboard
Add Listing (CSV upload)
SMS & Email
Reports
Export to CSV, PDF, DOC