## GoldMark Real Estate
| GoldMark Real Estate | 2017-04-07
Friday
Sl | Module | Man Hours | Man Days
Initiation
1 | System Study | 8 | 1 | Resource | No | Man hours | Man Days
1 | Low Level Design (Milestone 1) |  |  | Designer | 1 | 64 | 8
| UI Design (HTML Complete Running prototype) | 64 | 8 | Sr Developer | 1 | 40 | 5 | 21 | 21
| Design Sign Off (2 Working Day) |  |  | Jr Developer | 1 | 128 | 16
2 | Documentations (Milestone 2) |  |  | PM | 1 | 44 | 5.5
| SRS | 20 | 2.5 | QA | 2 | 44 | 11
| SRS Sign Off (2 Working Day) |  |  | Total |  |  | 45.5
| Functional Specification | 16 | 2 | Total Delivery days | 35
| Functional Specification Sign Off (2 Working Day) |  |  | Total Effort | 45.5
3 | Development & Testing (Milestone 3)
| Creating Development Environment PHP & DB | 8 | 1
4 | Common
| Login, Forgot Password, Reset Password | 8 | 1
| Change Password | 0 | 0
5 | Admin
| Manage Properies Sell, Buy | 20 | 2.5
| Manage Communities | 12 | 1.5
| Our Team | 4 | 0.5
| Manage master Data | 12 | 1.5
| Manage Content | 16 | 2
| Manage Newsletters | 4 | 0.5
| Manage Testmonials | 4 | 0.5
6 | Client
| Home | 16 | 2
Search (Buy, Rent & Sell)
Hot Properties (For Rent & Sell )
Testimonial
Video
News
Channel Partner
Banner
Newsletter (Don't miss out)
| Search Result | 20 | 2.5
Advanced Search (Buy & Rent)
Property Listing with pagination & Sort
| Property Details | 12 | 1.5
Property Details (Aminities, images, details)
Agent Info
| Member Details | 8 | 1
Member Details (Aminities, images, details)
Agent Info
| Meet Our Team | 8 | 1
| Careers | 4 | 0.5
| Communities | 8 | 1
| Contact US | 4 | 0.5
7 | Testing and Fixes
| Internal Testing (Cycle 1) & Fixing | 64 | 8
| UAT Support & Implementation | 24 | 3
8 | Project Management | 0 | 0
9 | TOTAL | 364 | 45.5
Assumption
HTML template need to be purchased
No Login and Registration on client side
Only one admin user
No ROLE based permissions
Data migration not considered in the above estimation
Usermanual & Test cases development not included in above estimation