## GUHMA
2018-07-06
Thursday
GUHMA
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 16 | 2 | Designer | 1 | 24 | 3 | 3
Functional Specification | 0 | 0 | WPF Developer | 1 | 56 | 7 | 7 | 7 | 7
Project Management | 5 | 0.625 | PM | 1 | 21 | 2.625 | 2.625
Graphic Design (WPF application) | 24 | 3 | QA | 1 | 21 | 2.625 | 2.625
Development |  |  | Technical Writer | 0 | 0 | 0 | 0
DashBoard |  |  | Total |  | 122 |  | 15.25 | 122
Load Files | 6 | 0.75
Read File | 8 | 1 | Total Delivery days | 15 | 0.75
Generate Graph | 24 | 3 | Total Man day Effort | 15.25
Print Graph & Summary | 8 | 1
Export to PDF | 6 | 0.75
Zoom in / Zoom Out of Graph | 4 | 0.5
Testing & Deployment
Testing | 15 | 1.875
UAT | 6 | 0.75
Deployment Support | 6 | 0.75
Total Effort | 128 | 16