## Intranet
| Intranet |  | Jan 11 2017
Wednesday
Sl. No. | Module | Man Hours | Man Days |  | No | Man Days | Total Effort
| Phase 1 |  |  | Designer | 2 | 6 | 12
1 | Finalising and purchase of HTML Theme & Images | 0 | 0 | Sr. Developer | 1 | 10 | 10
2 | Complete running prototype | 96 | 12 | Junior Developer | 2 | 27.5 | 55
3 | Development & Testing |  |  | QA | 2 | 11 | 22
4 | Admin |  |  | Total |  |  | 99
5 | Manage Users & permission | 24 | 3
6 | Manage Company | 4 | 0.5 | Total Delivery days | 44.5
7 | Manage Human Resources | 12 | 1.5 | Total Effort | 89
8 | Manage Information Technology | 8 | 1
9 | Manage Resources | 8 | 1
10 | Manage Infocus | 8 | 1
11 | Manage My Contents | 16 | 2
12 | Site
13 | Login
14 | Login Page | 4 | 0.5
15 | Home Page | 8 | 1
16 | -Submit a Form. | 0 | 0
17 | -Book a Meeting Room. | 48 | 6
18 | -Find a Staff. | 8 | 1
19 | Company
20 | -Company Profile - View | 2 | 0.25
21 | -Management Team - View | 2 | 0.25
22 | -Department - View [Operations,HR,IT,Sales] | 4 | 0.5
23 | -Locations with address and map - View | 4 | 0.5
24 | Human Resources
25 | -About HR-View | 2 | 0.25
26 | -HR Policy Manual->View | 2 | 0.25
27 | -New Employee Induction | 4 | 0.5
28 | -Staff Feedback - Form | 4 | 0.5
29 | -HR Team - View List and Profiles | 8 | 1
30 | Information Technology
31 | -About IT ->View | 2 | 0.25
32 | -IT Policy Manual ->View | 2 | 0.25
33 | -Training Videos ->View | 2 | 0.25
34 | -Staff Contact ->View | 2 | 0.25
35 | -IT Team ->View | 2 | 0.25
36 | Resources
37 | -Company Policies -> View | 2 | 0.25
38 | -Document Library -> View | 2 | 0.25
39 | -Photo Gallery ->View | 2 | 0.25
40 | My Contents
41 | -Notifications -> Submitted form status | 4 | 0.5
42 | -Notifications -> common notifications | 4 | 0.5
43 | -Online Forms -> Online forms for Leave Application | 56 | 7
44 | -Online Forms -> Business Trip advise | 40 | 5
45 | -Online Forms -> Expense Claim | 40 | 5
46 | -Online Forms -> Passport Release | 24 | 3
47 | -HR Forms -> Common HR Forms in PDF Formats | 2 | 0.25
48 | -My Profile [Profile details like Staff No, Dept, Reporting Manager, Change Password, Activity] | 12 | 1.5
49 | Infocus
50 | -E-Magazine | 8 | 1
51 | -Upload Picture | 4 | 0.5
52 | -Post Vacation/ Team Trip Pictures | 2 | 0.25
53 | Office 365 Integration (Outlook Integration) | 16 | 2
54 | Yammer Integration | 16 | 2
55 | AD Integration | 8 | 1
56 | Quality Analysis (QA) | 172.8 | 21.6
57 | UAT Support & Implementation
58 | Live
59 | Total Effort | 700.8 | 87.6
60
Assumption
Client will purchase HTML theme
Only one language - English
R&D / Challenges
Integrated with “Outlook Office365”
Active Directory Integration
single sign on PHP