## ASP.NET
| Intranet |  | Jan 11 2017
Wednesday
Sl. No. | Module | Man Hours | Man Days
Phase 1
1 | Finalising and purchase of HTML Theme & Images | 0 | 0
2 | Complete running prototype | 96 | 12
4 | Development & Testing (ASP.NET)
Admin
| Manage Users & permission | 24 | 3
| Manage Company | 4 | 0.5
| Manage Human Resources | 12 | 1.5
| Manage Information Technology | 8 | 1
| Manage Resources | 8 | 1
| Manage Infocus | 8 | 1
| Manage My Contents | 16 | 2
Site
Login
| Login Page | 4 | 0.5
| Home Page | 8 | 1
-Submit a Form.
| -Book a Meeting Room. | 0
| -Find a Staff. | 0
| Company |  |  |  | No | Man Days | Total
| -Company Profile - View | 2 | 0.25 | Designer | 0.5 | 12 | 12
| -Management Team - View | 2 | 0.25 | Sr. PHP developer | 1 | 6.5 | 6.5
| -Department - View [Operations,HR,IT,Sales] | 4 | 0.5 | Junior PHP Developer | 1 | 20 | 20
| -Locations with address and map - View | 4 | 0.5 | QA | 1 | 10.5 | 10.5
| Human Resources |  |  | Total |  |  | 49
| -About HR-View | 2 | 0.25
| -HR Policy Manual->View | 2 | 0.25
| -New Employee Induction | 0
| -Staff Feedback - Form | 4 | 0.5
| -HR Team - View List and Profiles | 8 | 1
Information Technology
| -About IT ->View | 2 | 0.25
| -IT Policy Manual ->View | 2 | 0.25
| -Training Videos ->View | 2 | 0.25
| -Staff Contact ->View | 2 | 0.25
| -IT Team ->View | 2 | 0.25
Resources
| -Company Policies -> View | 2 | 0.25
| -Document Library -> View | 2 | 0.25
| -Photo Gallery ->View | 2 | 0.25
My Contents
| -Notifications -> Submitted form status | 4 | 0.5
| -Notifications -> common notifications | 4 | 0.5
| -Online Forms -> Online forms for Leave Application | 0
| -Online Forms -> Business Trip advise | 0 | 0
| -Online Forms -> Expense Claim | 0 | 0
| -Online Forms -> Passport Release | 0 | 0
| -HR Forms -> Common HR Forms in PDF Formats | 2 | 0.25
| -My Profile [Profile details like Staff No, Dept, Reporting Manager, Change Password, Activity] | 12 | 1.5
Infocus
| -E-Magazine | 8 | 1
| -Upload Picture | 4 | 0.5
| -Post Vacation/ Team Trip Pictures | 2 | 0.25
| Office 365 Integration | 16 | 2
| Yammer Integration | 16 | 2
| AD Integration | 8 | 1 | Single sign in not possible
5 | Quality Analysis (QA) | 84.8 | 10.6
6 | UAT Support & Implementation
7 | Live
| Total Effort | 392.8 | 49.1
single sign on exception (PHP)
Assumption
Client will purchase HTML theme
Only one language - English
R&D / Challenges
Integrated with “Outlook Office365”
Active Directory Integration