## Survey Application
| Survey Application |  | 2017-05-23
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 4 | 4
1 | Business analysis | 8 | 1 | Sr Developer | 1 | 9 | 9 | 24 | 24
2 | Project Management | 21.6 | 2.7 | Jr Developer | 1 | 15 | 15
3 | Project Documentation (SRS, Scope, WBS etc.) | 16 | 2 | PM | 1 | 2.7 | 2.7
4 | Complete running prototype | 32 | 4 | BA | 1 | 3 | 3
| Development |  |  | QA | 1 | 7.6 | 7.6
| Admin |  |  | Total |  |  | 41.3
1 | Assign roles | 8 | 1
2 | Manage Users (Surveyors) | 8 | 1
3 | Assign Component to Surveyor | 8 | 1 | Total Delivery days | 26.6
4 | Manage application components (8 components) | 32 | 4 | Total Effort | 41.3 | (+1 Day deployment)
5 | Manage Questions [Hard-coded questions for components] | 24 | 3
6 | Reports (1 reports) | 8 | 1
Surveyor
1 | Manage login for Surveyors | 8 | 1 | Resource Loading
2 | Feature to draw shapes | 32 | 4 | Resource/Skill | Month 1 | Month 2 | Month 3
3 | Implement google map for component | 16 | 2 | Project Manager | 1.5 | 1.5
4 | Attend survey by surveyors (Components,Questions, Answers, Maps,Comments) | 32 | 4 | Business Analyst | 3 | 0
| System features |  |  | User Experience | 4 | 0.5
1 | Auditing & logging | 4 | 0.5 | Application Architect
2 | Exception handling | 4 | 0.5 | Lead Developer | 80 | 160
3 | User Manual | 8 | 1 | Developer | 80 | 160
4 | Quality Assurance |  |  | Database Architect
| QA & Bug Fixing | 52.8 | 6.6 | IOS Developer
1 | UAT | 8 | 1 | QA | 40 | 40
2 | Deployment | 8 | 1 | Tech Writer
3 | Total Effort | 338.4 | 42.3 | Total Effort | 217 Man Days |  | 570.5
|  |  |  | Total Effort Variation : | 180 - 200 days
Assumptions
The application will be a responsive web application
#REF!