## Law Portal
| Law Portal |  | 13/8/2018
Monday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 12 | 12
| SRS, FRS, Project Plan, Weekly Status | 32 | 4 | Sr Developer | 1 | 34 | 34 | 260 | 134 | 260 | 134
| Project Management | 47.3 | 5.9125 | Jr Developer | 1 | 100 | 100
| Design and Prototype | 96 | 12 | PM | 1 | 13 | 13
| Workflows |  |  | BA | 1 | 4 | 4
| Application Basic Setup | 4 | 0.5 | Tech writer | 1 | 5 | 5
| Intake Process Workflow | 148 | 18.5 | QA | 2 | 27 | 54
1 | First Level Registration (Client) | 6 | 0.75 | Total |  |  | 222
2 | Detailed Company Registration (Client) | 10 | 1.25
3 | Add employees (Client) | 8 | 1
4 | Send employee questionairre link (Client) | 6 | 0.75 | Total Effort | 222
5 | Employee fills questionaire (http://ims.rnlawgroup.com/h1bemployee#close) | 22 | 2.75 | Delivery Time Line | 139
6 | Review documents and submit after amendments (Client) | 10 | 1.25
7 | Front office login | 6 | 0.75
8 | Upload documents (front office User) | 6 | 0.75
9 | Review and register with case # (FO) | 10 | 1.25
10 | Assign case to paralegal (FO) | 8 | 1
11 | Submit to supervisor (FO) | 6 | 0.75
12 | Send email to client witrh status (SYSTEM) | 6 | 0.75
13 | Supervisor login | 6 | 0.75
14 | Review Case | 10 | 1.25
15 | Approve Paralegal | 6 | 0.75
16 | Assign new paralegal | 6 | 0.75
17 | Submit documents to paralegal with notes | 10 | 1.25
18 | Send email to client with status | 6 | 0.75
| Case Preparation Process | 336 | 42
1 | Paralegal Login | 6 | 0.75
2 | Review case and documents | 6 | 0.75
3 | Identify missing documents | 18 | 2.25
4 | Change status to documents received | 4 | 0.5
5 | Send status to client | 4 | 0.5
6 | Submit document to offshore | 6 | 0.75
7 | Send documents required email | 6 | 0.75
8 | Auto reminder after 48 hours | 18 | 2.25
9 | change status to documents missing | 6 | 0.75
10 | Upload user login | 18 | 2.25
11 | Check LCA filled by client and download | 10 | 1.25
12 | Submit LCA to DOL site & update LCA # in system | 18 | 2.25
13 | Change status to LCA submitted and generate email for client | 6 | 0.75
14 | Offshore Login | 6 | 0.75
15 | Review case and documents | 10 | 1.25
16 | prepare forms and letters | 18 | 2.25
17 | submit to paralegal with comments | 10 | 1.25
18 | Paralegal logs in | 6 | 0.75
19 | review comments from offshore user | 10 | 1.25
20 | upload additional documents or request documents from client | 18 | 2.25
21 | Automated email after 48 hours | 18 | 2.25
22 | submit to attorney / supervisor | 6 | 0.75
23 | Attorney Login | 6 | 0.75
24 | Review case and documents | 10 | 1.25
25 | send documents for signature to client | 6 | 0.75
26 | Enter filing fees | 10 | 1.25
27 | Send email to client requesting filing fees | 6 | 0.75
28 | Enter invoice details in the system | 6 | 0.75
29 | send invoice to client | 6 | 0.75
30 | Upload Signed LCA to System | 10 | 1.25
31 | Send LCA document to client for signature | 6 | 0.75
32 | Send email to client with all receipts | 6 | 0.75
33 | Generate Qrcode, Send email to client with fedX # | 18 | 2.25
34 | Capture Tracking # and change status of the case to Filed | 18 | 2.25
| POST FILING PROCESS | 80 | 10
1 | Front office login | 6 | 0.75
2 | Upload scanned receipt notice | 8 | 1
3 | Attach receipt notice to case | 8 | 1
4 | Send Email to client- receipt notice received | 8 | 1
5 | Client Can view receipt notice | 4 | 0.5
6 | System changes status to receipt notice received | 8 | 1
7 | Upload USICS Approval notice | 8 | 1
8 | update case as approved | 6 | 0.75
9 | record tracking details | 10 | 1.25
10 | Close case | 6 | 0.75
11 | System generated email to client with tracking # of approval (also by FO | 8 | 1
| Request for Evidence - Prefiling Process | 370 | 46.25
1 | FO Checks for RFE | 10 | 1.25
2 | Create a subcase for RFE | 10 | 1.25
3 | Assign case to evidence supervisor | 4 | 0.5
4 | Evidence Supervisor logs in and reviews RFE details and assigns case to paralegal | 10 | 1.25
5 | Paralegal logs in and uploads new documents to system | 10 | 1.25
6 | Paralegal checks for new RFE and downloads it | 10 | 1.25
7 | Paralegal sneds email to client to fillout the RFE | 6 | 0.75
8 | System autogenerates days to the case | 10 | 1.25
9 | Client uploads the RFE documents requested by paralegal | 3 | 0.375
10 | Paralegal reviews the documents and marks it as received | 3 | 0.375
11 | Send email to client and chnages the status of the case | 3 | 0.375
12 | Calendar notification and autogenerated email to client if document not received in the stipulated time | 26 | 3.25
13 | Paralegal submits the case to offshore | 4 | 0.5
14 | Offshore Login | 6 | 0.75
15 | Review case and RFE documents | 10 | 1.25
16 | Prepare forms and letters | 18 | 2.25
17 | Offshore submits to paralegal with comments | 6 | 0.75
18 | Paralegal reviews documents submitted by offshore | 18 | 2.25
19 | Send mail to client for additional documents | 6 | 0.75
20 | System generates notifications after 48 hours if no communication received from client | 10 | 1.25
21 | Submit case to attorney | 6 | 0.75
22 | System generates notification if the attorney did not check the case in 48 hours | 10 | 1.25
23 | Attorney login | 6 | 0.75
24 | Reveiews case and documents | 10 | 1.25
25 | send documents for signature to client | 10 | 1.25
26 | Send invoice to client | 4 | 0.5
27 | enter invoice details in the system | 6 | 0.75
28 | Paralegal login | 6 | 0.75
29 | Send confirmation email to client on receipt of the documents | 6 | 0.75
30 | Print QR code sticker with employee name and service center | 18 | 2.25
31 | upload scanned documents to system | 10 | 1.25
32 | confirm invoice received | 6 | 0.75
33 | record tracking # and date fedexed for the case | 18 | 2.25
34 | Email client with tracking #, Date, case # etc | 10 | 1.25
35 | Change status of case to RFE Filed | 6 | 0.75
36 | Upload scanned receipt notice from USICS and log it against the case | 6 | 0.75
37 | Send Email to client- receipt notice received | 6 | 0.75
38 | Client can view recept notice | 3 | 0.375
39 | Autogenerate status for case "receipt notice received" | 10 | 1.25
40 | Upload scanned approval notice | 6 | 0.75
41 | Change status of case to approved | 4 | 0.5
42 | Enter tracking details of shipment | 10 | 1.25
43 | Close case | 4 | 0.5
44 | Email client with tracking # | 6 | 0.75
| Admin | 40 | 5
1 | Manage users | 8 | 1
2 | Manage roles | 8 | 1
3 | Upload document templates to create evidence library | 18 | 2.25
4 | Manage Statuses | 6 | 0.75
| System features | 104 | 13
1 | Authentication & authorization | 8 | 1
2 | Auditing & logging | 8 | 1
3 | Exception handling | 8 | 1
4 | System generated emails | 8 | 1
5 | System generated calendar notifications | 16 | 2
6 | Automatic status changes | 8 | 1
7 | QR code generation | 16 | 2
8 | Printing services | 8 | 1
9 | Evidence library | 8 | 1
10 | Document Management | 8 | 1
11 | Forgot Password, remember password | 8 | 1
Quality Assurance
31 | QA & Bug Fixing | 431.2 | 53.9
32 | UAT | 4 | 0.5
32 | PM | 104 | 13
33 | Deployment | 4 | 0.5
| Total Effort | 1796.5 | 224.5625