## Law Portal
| Law Portal |  | 13/8/2018
Monday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 6 | 6
| SRS, FRS, Project Plan, Weekly Status | 32 | 4 | Sr Developer | 1 | 10.5 | 10.5 | 3.5 | 10.5 | 3.5 | 10.5
| Project Management | 2.4 | 0.3 | Jr Developer |  |  | 0
| Design and Prototype | 48 | 6 | PM | 1 | 0.3 | 0.3
| Workflows |  |  | BA | 1 | 4 | 4
| Application Basic Setup | 4 | 0.5 | Tech writer | 0 | 0 | 0
| Intake Process Workflow |  |  | QA | 1 | 1.725 | 1.725
1 | First Level Registration (Client) |  |  | Total |  |  | 22.525
2 | Detailed Company Registration (Client)
3 | Add employees (Client)
4 | Send employee questionairre link (Client) |  |  | Total Effort | 22.525
5 | Employee fills questionaire (http://ims.rnlawgroup.com/h1bemployee#close) |  |  | Delivery Time Line | 18.225
6 | Review documents and submit after amendments (Client)
7 | Front office login
8 | Upload documents (front office User)
9 | Review and register with case # (FO)
10 | Assign case to paralegal (FO)
11 | Submit to supervisor (FO)
12 | Send email to client witrh status (SYSTEM)
13 | Supervisor login
14 | Review Case
15 | Approve Paralegal
16 | Assign new paralegal
17 | Submit documents to paralegal with notes
18 | Send email to client with status
Case Preparation Process
Paralegal Login
Review case and documents
Identify missing documents
Change status to documents received
Send status to client
Submit document to offshore
Send documents required email
Auto reminder after 48 hours
change status to documents missing
Upload user login
Check LCA filled by client and download
Submit LCA to DOL site & update LCA # in system
Change status to LCA submitted and generate email for client
Offshore Login
Review case and documents
prepare forms and letters
submit to paralegal with comments
Paralegal login
review comments from offshore user
upload additional documents or request documents from client
Automated email after 48 hours
submit to attorney / supervisor
Attorney Login
Review case and documents
send documents for signature to client
Enter filing fees
Send email to client requesting filing fees
Enter invoice details in the system
send invoice to client
Upload Signed LCA to System
Send LCA document to client for signature
Send email to client with all receipts
Generate Qrcode, Send email to client with fedX #
Capture Tracking # and change status of the case to Filed
POST FILING PROCESS
Front office login
Upload scanned receipt notice
Attach receipt notice to case
Send Email to client- receipt notice received
Client Can view receipt notice
System changes status to receipt notice received
Upload USICS Approval notice
update case as approved
record tracking details
Close case
System generated email to client with tracking # of approval (also by FO
Request for Evidence - Prefiling Process
FO Checks for RFE
Create a subcase for RFE
Assign case to evidence supervisor
Evidence Supervisor logs in and reviews RFE details and assigns case to paralegal
Paralegal logs in and uploads new documents to system
Paralegal checks for new RFE and downloads it
Paralegal sneds email to client to fillout the RFE
System autogenerates days to the case
Client uploads the RFE documents requested by paralegal
Paralegal reviews the documents and marks it as received
Send email to client and chnages the status of the case
Calendar notification and autogenerated email to client if document not received in the stipulated time
Paralegal submits the case to offshore
Offshore Login
Review case and RFE documents
Prepare forms and letters
Offshore submits to paralegal with comments
Paralegal reviews documents submitted by offshore
Send mail to client for additional documents
System generates notifications after 48 hours if no communication received from client
Submit case to attorney
System generates notification if the attorney did not check the case in 48 hours
Attorney login
Reveiews case and documents
send documents for signature to client
Send invoice to client
enter invoice details in the system
Paralegal login
Send confirmation email to client on receipt of the documents
Print QR code sticker with employee name and service center
upload scanned documents to system
confirm invoice received
record tracking # and date fedexed for the case
Email client with tracking #, Date, case # etc
Change status of case to RFE Filed
Upload scanned receipt notice from USICS and log it against the case
Send Email to client- receipt notice received
Client can view recept notice
Autogenerate status for case "receipt notice received"
Upload scanned approval notice
Change status of case to approved
Enter tracking details of shipment
Close case
Email client with tracking #
Admin
Manage users
Manage roles
Upload document templates to create evidence library
Manage Statuses
Manage Beneficiary
Manage Case Types
System features
27 | Authentication & authorization | 8 | 1
28 | Auditing & logging | 8 | 1
29 | Exception handling | 8 | 1
System generated emails
System generated calendar notifications
Automatic status changes
QR code generation
Printing services
Evidence library
Document Management
Forgot Password, remember password
Quality Assurance
31 | QA & Bug Fixing | 9.8 | 1.225
32 | UAT | 4 | 0.5
33 | Deployment | 4 | 0.5
| Total Effort | 128.2 | 16.025