## Total Estimate
Project Name : Crowd Invest Mobile Development Estimate ( Android )
Inputs |  | Estimation Summary (Hours and Business days)
Risk and/or "unknown" (25% ; 50% ; 25% ; 10%) | 10 | Optimistic hours | 409.2 | 29.2286 |  | 34.1
Project Complexity scale Extreme(100%); high(50%) ; medium(25%) ; low(10%) | 10 | Most likely hours** | 470.58 | 33.6129 | 192000 | 34.1
Average productive hours per day | 7 | Pessimistic hours* | 531.96 | 37.9971 |  | 122.76
Estimation parameters | Hours | [5 empty] | Holidays in 2016 | Date
Requirement gathering | 8 | Expected Duration |  | Hours |  |  | New Year's Day | 2016-01-01
Research and analysis | 8 | Triangular distribution method |  | 33.6129 |  |  | Republic Day | 2016-01-26
Development | 220 | Beta distribution (PERT technique) |  | 33.6129 |  |  | Monty Thursday | 2016-03-24
Design | 20 | [5 empty] | Good Friday | 2016-03-25
Testing | 44 | Finish Date |  |  |  |  | Vishu | 2016-04-14
Training | 0 | Earliest start date | 5/2/2016 |  |  |  | May Day | 2016-05-01
Documentation | 8 | Earliest completion date | #VALUE! | Optimistic |  |  | Assembly Elections | 2016-05-16
Meetings | 16 | Earliest completion date | #VALUE! | Most likely |  |  | Onam | 2016-09-13
Migration (data or content) | 0 | Earliest completion date | #VALUE! | Pessimistic |  |  | Onam | 2016-09-14
Project management | 11 | [5 empty] | Onam | 2016-09-15
Reports | 0 | Latest start date | 2016-05-09 |  |  |  | Gandhu Jayanthi | 2016-10-02
UAT | 0 | Latest completion date | #VALUE! | Optimistic |  |  | Deepavali | 2016-10-29
Accessibility test | 0 | Latest completion date | #VALUE! | Most likely |  |  | Christmas | 2016-12-26
Pre deployment process | 1 | Latest completion date | #VALUE! | Pessimistic
Deployment | 4
Post production testing | 0 | Pessimistic case buffer (in percentage) |  | 30
Knowledge transfer/ Service transition | 1 | No of resources (This will impact the number of business days to complete and finish date calculation.) on average |  | 2
Marketing | 0
Project retrospective | 0
* Pessimistic hours= Best case hours+ Pessimistic case buffer **Most likely=(Optimistic + Pessimistic )/2 ***Excluded Saturdays, Sundays and state holidays
Total | 341
Note on E13: Prashant Thomas: Please enter your estimated start date here

## Effort
| Mentis Loyalty Application |  | 2016-06-01
Sl. No. | Product Log | Phase | Man Days | Comments
1 | SignRequirement Gathering Complete and Sign -Off | Design | 10 | Effort may vary depending on the time spend in requirement gathering and confirmation
2 | System Study, SRS & HLD
Theme selection & HTML Prototype with responsive design
HTML Prototype Approval
Create & Integrate plugins, extensions etc.
Database design
3 | Administration | Development |  | Reports need to be defined and the number of reports may cause varainces in the effort mentioned
Users and roles, products, categories
Entitlements (page access rights etc.)
administer loyalty programs
Create and raise invoices
Report generation
System maintenance scripts and mitigation scripts
4 | Customer Support & Service | Development & Campaign Models |  | Since this is a TBD activity (customer service), the activities listed here are capabilities that Verbat can deliver in enabling business continuity, business process defenition & customoer retention
Lead generation, oppurtunity management, Account management
strategic Sales and market analysis
campaign management, inbound marketing
Analytics
5 | Customers | Development
Registration
Loyalty program selection
Coupon & discount redemptions
Reports
6 | Mentis Core Engine Services | Development
Basic application framework (includes authentication, authorization, logging & auditing
Payment gateway integration
Loyalty Program engine(Loyalty card integration service, Loyalty program management, Loyalty customer onboarding, Rule based account management)
Information management (Reports, analytics, business intelligence)
7 | General Pages |  | 1
Home
Contact Us
About Us
Social media plugins
Search
8 | Code Review + QA + Bugfix | Testing
QA
UAT
11 | Deployment | Release
SSL Implementation and other security features such as CORS (if required)
Go Live
| Total |  | 11
| Cumulative Total |  | 88