## Slide 1
We Engineer your Digital Success
Proposal for Development of a Loyalty Program for Mentis
Aug 2016
© 2016. All Rights Reserved / www.verbat.com

## Slide 2
Contents
Background & Scope
Solution Overview & Application Workflow
Application Functionality
Discovery Phase
Application Delivery
Technology Specification
Project Timeline & Deliverables
1
2
3
4
5
6
7
Commercials
8
Assumptions
Out of scope
Terms & Conditions
9
10
11

## Slide 3
Background & Scope
Mentis specializes in world-class assessment, training, coaching and development programs - offering targeted solutions to meet your needs. Our services cover all organizational levels, from designing and delivering graduate development to coaching and advising at CEO and Board level. It’s all about predicting performance and identifying potential. Mentis values long-term client relationships. We believe that with an in-depth understanding of your requirements we can provide meaningful results. Our services are available throughout the UK, Europe and the Middle East and ASEAN regions
Scope
Verbat is proposing to develop a Loyalty Program for Mentis that will facilitate Mentis to provide an incentive based discount program to customers based on their service tiers. The loyalty program will enable customers to have advanced access to make discount purchase off of products as well as avail offers to receive free merchandise.

## Slide 4
Scope
The proposed application will consist of the following modules
Administration
  Users and user groups
  Roles and Entitlements
  Raise Invoices
  Generate reports
Support
  Application Maintenance
  Customer & Technical Support
  Application configuration
  Lead Generation & inbound marketing
  Other functions TBD
Customer
  View transactions
  Redeem vouchers & offers
  Choose Loyalty program (Platinum, Gold, Silver)

## Slide 5
Solution Overview & Application Workflow

## Slide 6
Solution Overview
Customer Registers and opts for loyalty program
Mentis Management engine is comprised of
  Application Framework
  Loyalty Program Management (LPM)
  Information management
Application Framework consist of User authentication, authorization, application auditing & logging with payment processor integration
LPM manages the Loyalty card issuance & tracking, Gift voucher redemption and voucher management, Customer onboarding for the loyalty program and rule based account management of the loyalty program
Information management provides business intelligence, reporting services and the analysis supports through decision support systems
Customer service activities including sales and marketing automation are capabilities that Verbat has a proven track record and can provide value added services (optional)
System administrator manages the general operation of the site. Verbat will provide all the necessary utilities and scripts to ensure business continuity and smooth day to day operations

## Slide 7
Application Work Flow
START
Portal registration and program Selection
View Transactions and redeem offers & vouchers
Purchase products and receive coupons and discounts based on Loyalty group
Customer
Customer Service
Support
STOP
START
Opportunity Management
Inbound marketing & lead generation
Market analysis & campaign Management
STOP
START
Application Management
(users, products etc.)
Technical Support
&
System Maintenance
Manage loyalty programs and generate Management reports
STOP
Administrator

## Slide 8
Application Functionality

## Slide 9
Mentis Core Engine Services
  Core services : Authentication, Authorization, Logging, Auditing, Payment Gateway Integration
  Loyalty program Engine: Loyalty card Issuer, Loyalty program management, Loyalty Onboarding, Rule based account management
  Information Management: Reports, Analytics, Business Intelligence
Customer Service (Optional)
  Sales Automation: Lead Generation, Opportunity Management, Account Management, Sales Analytics
  Marketing Automation: Campaign Management, Market Analysis, inbound marketing
Administration
  Manage: categories, products, customers, back office users, Loyalty programs
  System maintenance, Technical support, Reports
Customers
  Registration, Loyalty program selection, coupon redemption, Reports,
Feature Details

## Slide 10
Discovery Phase

## Slide 11
Requirements Gathering
On signing the contract, Verbat will deploy a senior Business Analyst to discuss the business and technical requirements, define the solution approach, deliverables during each phases of execution, documentation and sign-off
Deliverables
  Detailed requirement specification document
  Wireframes for the key screens for the proposed application
Dependencies
  The client to nominate a Point of contact to coordinate with our team
  Availability of key stakeholders for meetings to discuss requirements and validate findings and deliverables
  Written sign-off on the deliverables prior to commencement of the development phase

## Slide 12
Application Delivery

## Slide 13
Application Delivery
Application will be delivered in three phases. Development will start post approval and sign-off of the Software Requirements Specification (SRS) by the client. The deliverables for each phase is listed below.
Phase 1 Design
Project plan
SRS & Functional Specification
Wire frames for key screens
Phase 2 Development
Mentis core engine
Administration module
Customer registration and loyalty onboarding
Customer support and services (optional)
General pages
Phase 3 Testing
QA
UAT
Phase 4 Go Live
Application deployment
Application configuration

## Slide 14
Technology Specification

## Slide 15
Technology Specifications
Recommended System Requirements
  Database – MS SQL 2008 and above
  Operating System – Windows 7 & above with .Net Framework 3.5 and above

## Slide 16
Project Timeline & Deliverables

## Slide 17
Activity | Phase | Effort (Man Days)
Initiation | Phase 1 | 9
Requirement Gathering Complete and Sign-Off |  | 
Software requirement Specification & functional Specification |  | 
UI Design |  | 
Database Design |  | 
Development Start | Phase 2 | 19
Application Framework |  | 
Administration |  | 
Customer registration and on boarding |  | 
General information pages |  | 
Mentis Core Engine Services |  | 
Code Review |  | 
QA & Deployment | Phase 3 | 11
QA |  | 
UAT |  | 
Deployment & Go Live |  | 
The time estimated for delivering the application is 39 working man days
Deliverables
  Software Requirement Specification (SRS)
  Functional Specification
  Low level design
  Wireframes for the key screens
  Fully developed and tested application for deployment
Project Timeline & Deliverables

## Slide 18
Commercials

## Slide 19
Commercials
Sl. | Description | Cost
01. | Development of Mentis Loyalty Program (MLP) | USD 00,000

## Slide 20
Assumptions

## Slide 21
Web Services for the following will be provided by the client
Web Services/API and the detailed documentation for
  User Authentication
  Payment Request Initiation
  Payment Authentication & Authorization
The client will also provide
Logo
UI Design Guidelines
Testing Cards and the PIN number.
Required working device with SDK
Assumptions

## Slide 22
Out of Scope

## Slide 23
Any other language other than English
Manual data entry
Integration with other payment processors
Integration with any other systems other than those specified in the Scope
Physical installation at the client site
Out of Scope

## Slide 24
Terms & Conditions

## Slide 25
Offer Valid for 30 calendar days from the date of submission of the Proposal
An average of 20 working days are assumed in a month
This proposal and all technical/ functional specifications have been derived or concluded from the data shared via email / information's transferred during the initial requirement analysis meetings and conversations. Verbat reserves the right to amend the terms of this proposal, should the SOW terms, functional features and functionalities change during the course of the project
The applications will be built as per the specifications agreed mutually. Any changes will be executed through a deﬁned change management process between both parties
All Source Code and other project artefacts would adhere to the Verbat document templates and internal coding standards
Verbat will provide a bug ﬁx warranty at no additional cost for 30 days from the date of acceptance of the project, for correction of any errors in the developed application that may be attributed to Verbat
Acceptance criteria will be based on the clauses which were mutually discussed between Verbat and client at the Requirement Analysis phase and the same will be documented and approved by both parties through official emails
Terms & Conditions

## Slide 26
+971 04 2973236
Lekshmi.krishna@verbat.com
India
Verbat Technologies (India) Pvt. Ltd. Level 3, PTC Tower Trivandrum, Kerala
USA 2033 Gateway Place
Suite 500
San Jose , CA- 95110
Contact Us
217, Sheikh Rashid Bldg
P.O Box 56272, Dubai United Arab Emirates

## Slide 27
Thank You
© 2016. All Rights Reserved Verbanet Technologies LLC www.verbat.com