## Sheet1
DAM Project |  | 2018-12-04
Thursday
Module | Hours | Man Days |  | No | Man Days | Total Effort |  |  | Total Hours | Hours/3 phases
Initiation |  |  | Designer | 1 | 12 | 12 |  |  | 96 | 32
Business analysis | 56 | 7 | Sr Developer | 2 | 35 | 70 | 128 | 220 | 560 | 186.6667
Project Management | 226.56 | 28.32 | Jr Developer | 3 | 50 | 150 |  |  | 1200 | 400
Design and Prototype | 96 | 12 | Android | 0 | 25 | 0 |  |  | 0 | 0
Development |  |  | PM | 1 | 7 | 7 |  |  | 56 | 18.6667
Application basic setup | 16 | 2 | BA | 1 | 3 | 3 |  |  | 24 | 8
Admin Module |  |  | Tech Writer | 1 | 5 | 5 |  |  | 40 | 13.3333
Login, Forgot password | 16 | 2 | QA | 2 | 38.1 | 76.2 |  |  | 609.6 | 203.2
Backup Manager | 64 | 8 | Total |  |  | 323.2
Mail Manager | 72 | 9
Report Manager | 56 | 7
User Manager | 40 | 5 | Total Delivery days | 100.1
Web Client Configuration | 48 | 6 | Total Effort | 323.2 | (+1 Day deployment)
Dashboard | 64 | 8
DAM Sites
Login, Forgot password | 8 | 1
Dashboard | 24 | 3
Information | 40 | 5
Relation | 40 | 5
History | 40 | 5
Comments | 64 | 8
Actions
Preview
Download
Share
Add to basket
Edit
Check In
Check Out
Delete
DAM Clients
Login, Forgot password | 8 | 1
Dashboard | 24 | 3
Actions
Download | 24 | 3
Print | 40 | 5
General application features
Simple search & advanced search | 16 | 2
Send Feedback | 16 | 2
dashboard for staff, receptionist, admins (Fav, Viewed, History, Shared, recommended excersises, Excersice charts etc.) | 32 | 4
Intranet Manual | 24 | 3
System features
Single Sign on (SSO) | 24 | 3
Supports all well-Known file formats | 56 | 7
SharePoint Integration | 64 | 8
Dynamic filtering | 40 | 5
Image and video editing | 64 | 8
Bulk editing of media | 64 | 8
Statistics and Reporting | 64 | 8
Preview of media files | 48 | 6
Version management | 48 | 6
Auto-tagging | 56 | 7
Encryption | 48 | 6
Multilingual | 64 | 8
API/Developer access | 96 | 12
Automatic thumbnail conversion | 56 | 7
Create a Collection and Sharing | 64 | 8
Quality Assurance
QA & Bug Fixing | 489.6 | 61.2
UAT | 120 | 15
Deployment per instance | 24 | 3
Total Effort | 2644.16 | 330.52