## Educational Material
| Educational Material |  | 2019-10-04
Wednesday
| Module | Hours | Man Days |  | No of resources | Man Days | Adjusted Del Days | Total Effort
| Initiation |  |  | Designer | 1 | 4 | 4 | 4
1 | Business analysis | 24 | 3 | Developer | 1 | 17 | 17 | 17 | #REF! | 18.675 | 16.75
2 | SRS | 16 | 2 | PM | 1 | 1.675 | 1.675 | 1.675
| UI/UX | 32 | 4 | BA | 1 | 5 | 5 | 5
3 | Project Management | 13.4 | 1.675 | QA | 1 | 5.5 | 5.5 | 5.5
| Design and Development |  |  | SUM |  |  |  | 33.175
| ADMIN | [6 empty] | 33.175
1 | Login (hard coded) | 6 | 0.75
2 | Manage Cities | 6 | 0.75 | Delivery Days | 26.5
3 | Manage Category | 6 | 0.75 | Total Effort | 33.175
4 | Manage Classes | 6 | 0.75 | Training & Deployment | 112
5 | Manage subjects | 6 | 0.75
6 | Manage Teachers | 6 | 0.75
7 | Manage educational material (upload / download) | 6 | 0.75
8 | Dashboard ( recent activity, uploads, subjects, classes etc) | 16 | 2
Teacher
| Update profile | 6 | 0.75
| Login / reset password | 6 | 0.75
| Manage educational material (upload / download) | 6 | 0.75
| Search | 6 | 0.75
| View download material | 4 | 0.5
| View download statistics | 4 | 0.5
Guest / Student
| Search with filters | 6 | 0.75
| Download files | 4 | 0.5
| File statistics | 4 | 0.5
System Features
| Authentication & Authorization | 6 | 0.75
| Auditing and logging | 6 | 0.75
| Exception management | 6 | 0.75
| File management | 6 | 0.75
| Email / SMTP integration | 6 | 0.75
| QA & Bug Fixing | 44 | 5.5
| Total Effort | 263.4 | 32.925

## Sheet1
1. Admin Functionality
Login / Reset Password. (A pre-defined / hard coded user name will be available in the system and the password can be changed any time).
Manage master data.
List of Cities
Category List (Material category – e.g. marks, homework, revision material)
Classes List
Subject List (e.g. Mathematics, Geography etc. etc. )
View Dashboard: Provide satellite view of all key activities with visually appealing charts and graphs. (E.g Statistics about uploaded files, per category, per class, per geography, number of registered
teachers , number of visitors/ viewers, number of downloads)
Upload / Edit / Delete Educational material (pdf, word, excel, jpeg etc.). To Upload the educational material, Admin needs to select the category from a pre-defined drop down list and should select under which class the material belongs. Example, Grade 1, 2……..12. (To Note: Admin can edit / delete any files )
The admin should be able to view the uploaded files
Uploaded by himself
Uploaded by Others.
View the number of downloads per file
Admin can download any uploaded files.
2. Teacher Functionality:
Register as a Teacher. (name, E-mail, location what level the teacher is teaching , teachers level, name of school and other profile details) + Teacher can update the profile
Login / Reset Password.
Upload / Edit / Delete Educational material (pdf, word, excel, jpeg etc.). To Upload the educational material, the teacher needs to select the category from a pre-defined drop down list and should select under which class the material belongs. Example, Grade 1, 2……..12. (To Note: Teacher can edit / delete only their own files )
The Teachers should be able to search / filter by category / filter by class / view the uploaded files
The teacher should be able to view the uploaded files
Uploaded by the Teacher
Uploaded by Others.
View the number of downloads per file
Teachers can download any uploaded files.
3. Guest / Student Functionality
The Guests should be able to search / filter by category / filter by class / view the uploaded files
View the number of downloads per file
Guests / Students can download any uploaded files.