## Future gate
| Future Gate development |  | 2019-10-05
Friday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 5 | 5
| Business Analysis | 32 | 4 | Sr Developer | 1 | 45 | 45 | 104 | 115.2 | 104 | 105
| Project Management | 81.6 | 10.2 | Jr Developer | 1 | 60 | 60
| Design and Prototype | 40 | 5 | PM | 1 | 10.2 | 10.2
| Documentation (SRS, FS, Weekly Reports,User Manual) | 32 | 4 | BA | 1 | 4 | 4
| Development |  |  | TechWriter | 1 | 4 | 4
| Application Basic Setup | 16 | 2 | QA | 1 | 49.8 | 49.8
| Future Gate Events Portal |  |  | Total |  |  | 178
| Home page banner | 6 | 0.75
| Success Story Display | 8 | 1 | Total Delivery days | 114.8
| Survey | 16 | 2 | Total Effort | 178
| Ad management | 40 | 5
| Registration | 8 | 1
| Login | 6 | 0.75
| Add Success Story | 16 | 2
| Academic Calendar | 32 | 4
| Events | 40 | 5
| Useful links | 4 | 0.5
Backend/control Panel
| Login/Logout | 8 | 1
| Home page banner | 8 | 1
| Type of questionnaire | 8 | 1
| Manage Survey & Questioners | 120 | 15
| manange Success Stories | 56 | 7
| Ad management | 40 | 5
| Manage Events | 40 | 5
| Useful links | 6 | 0.75
| Manage Agents | 4 | 0.5
Dashboard with graphical reports
Extract Reports
Portal for the Future Gate Award for Excellence - Super Admin
| Login/Logout | 8 | 1
| Dashboard | 32 | 4
| User Management | 24 | 3
| Form Design | 120 | 15
| View Evaluation Report | 40 | 5
Portal for the Future Gate Award for Excellence - Candidate
| Registration | 8 | 1
| Login/Logout | 6 | 0.75
| Form submission process | 40 | 5
Portal for the Future Gate Award for Excellence - Supervisor
| Login/Logout | 8 | 1
| Sorting and review by supervisors, assigning to evaluators | 24 | 3
Portal for the Future Gate Award for Excellence - Supervisor
| Login/Logout | 8 | 1
| Evaluation | 32 | 4
Quality Assurance
31 | QA & Bug Fixing | 342.4 | 42.8
32 | UAT | 40 | 5
33 | Deployment per instance | 16 | 2
| Total Effort | 1416 | 177
Assumptions
The effort might change after a detailed system study
Scope2
Live chat solution - 3rd party integration
Scope2
Web page designing will be on pre defined template
The controls in the webpage will be predefined only visibility will be done by Admin
Values to the controls can be added by admin