## Sheet1
HAJT |  | 28/08/2018
Tuesday
Initiation | Hours | Days
Business Analysis | 16 | 2 | Resource | No | Man Days | Total Effort
Project Management | 0 | 0 | Designer | 1 | 3 | 3
UI/UX | 24 | 3 | Sr Developer | 1 | 0 | 0 | 0 | 0
Documentation | 8 | 1 | Jr Developer | 1 | 0 | 0
Development |  |  | PM | 1 | 0 | 0
Marine Services |  |  | BA | 1 | 2 | 2
Vessel Berthing |  | 0 | Tech writer | 1 | 1 | 1
Identify required Docs ( Each workflow has separate document requirments) |  | 0 | QA | 2 | 0 | 0
Online Form |  | 0 | Total |  |  | 6
Vessel Berthing W/F (2 level Approvals: From Pilot and Port Officer) |  | 0 | Total Delivery days | 3
NOC (Fixed Format) Issued by Pilot and Marine Office) |  | 0 | Total Effort | 6 | (+1 Day deployment)
Option to resubmit Documents |  | 0
Preformatted emails (Submit, Approve, Reject) |  | 0
Permit emailed (PDF version created and mailed) |  | 0
Sail Out Permit (Activities similar to 1) |  | 0
Extend Vessel Berthing (Activities similar to 1) |  | 0
Vessel Permit to enter Ajman Port (Activities similar to 1) |  | 0
Safety Services (All activities similar to 1)
Bunker Permit |  | 0 | Requirement docs for services
Hotwork Permit |  | 0
Diving Permit |  | 0
Diesel discharge permit |  | 0
General Maintenance Permit |  | 0
Sanitation Permit |  | 0
Reporting (Common for Marine Service)
Search by date range, status, user name |  | 0
Export to Excel and PDF |  | 0
Dashboard (One each for Safety and Marine services)
List of submitted request |  | 0
List of rejected request |  | 0
List of approved requests |  | 0
System
Login, forgot password, remember password, Password salting |  | 0
Bilingual Site (Includes saving data in Arabic) |  | 0
Authentication and Authorization |  | 0
Auditing and logging |  | 0
Email, SMTP, SMS |  | 0
Exception Handling |  | 0
File management, convert to PDF |  | 0
HTTPS, SSL |  | 0
Admin
Manage Requirment docs for services |  | 0
User management (Roles: HAJT, DPC; Users: Safety Officer, end user) |  | 0
Manage Email templates (Approve, Reject, Received) |  | 0
Manage Approval Templates (10 templates) |  | 0
QA + UAT | 0 | 0
Total | 48 | 6
312

## Sheet2
Removed Features
Refer friend via email (Store Refferals to create email database) with referral bonus (gamification)
Promo Code management(dashboard, Coupon codes, Dates Valid, Distribution list, Discounts, Analytics)
Push Notification Channels( Email, SMS, Web Push, Onsite Personalization: Exit intent)
Context Sensitive Help Within tax Workflow (Hover over text for individual line items and eidtable text that can be managed via CMS)
Social Media Integration (link to FB, Lin, instagram , twitter, pinterest, google)
Promo code distribution
Referral links
Document Archival
Simple + Advanced search (Tax Documents + Site Search)
Save data on back button (Tax Workflow)
Prefill with PAN
Prior Year XML
Foreign income and assets validation : Premium plan
Other Batch Jobs (retry failed returns, Status updates pending failed returns)
End user reports (5 reports max)
Feedback form (Survey)
Values in the form should be saved on navigating to other tabs even without clicking save
Manage Customer Queries ( multi step drop down questions to narrow down common questions that requires human intervention)
Manage Email Templates (clarity required, not sure if this is relevant)
Loyalty Program for returning users (need clarity)
Email Marketing