## Sheet1
HAJT |  | 28/08/2018
Tuesday
Initiation | Hours | Days
Business Analysis | 16 | 2 |  | Resource | No | Man Days | Total Effort
Project Management | 37.45 | 4.6813 |  | Designer | 1 | 11 | 11
UI/UX | 88 | 11 |  | Sr Developer | 1 | 32 | 32 | 64.3125 | 64
Documentation | 8 | 1 |  | Jr Developer | 1 | 32 | 32
Development |  |  |  | PM | 1 | 4.6813 | 4.6813
User - Customer |  |  |  | BA | 1 | 2 | 2
User Registration | 8 | 1 |  | Tech writer | 1 | 1 | 1
Login | 4 | 0.5 |  | QA | 2 | 9.6469 | 19.2937
Dashboard, Notifications | 32 | 4 |  | Total |  |  | 101.975
Marine Services |  |  |  | Total Delivery days | 52.6469
Marine service form | 8 | 1 |  | Total Effort | 101.975 | (+1 Day deployment)
Sail out Permit form | 16 | 2
Extension vessel berthing form | 8 | 1
Vessel permit form | 8 | 1
Safety Services
Bunker permit request | 6 | 0.75
Hot work permit request | 6 | 0.75
Diving permit process | 6 | 0.75
Diesel discharge permit | 6 | 0.75
General maintenance permit | 4 | 0.5
Sanitation permit process | 4 | 0.5
User - DPC/HAJT User |  |  | Each individual Service includes the following features
Login (Assign services according to the roles) | 16 | 2 | Identify required Docs ( Each workflow has separate document requirments)
Dashboard, Notifications | 8 | 1 | Online Form
Marine Services - View/ Edit details, Approval/Reject |  |  | Vessel Berthing W/F (2 level Approvals: From Pilot and Port Officer)
Marine service (Listing with search) | 10 | 1.25 | NOC (Fixed Format) Issued by Pilot and Marine Office)
Sail out Permit (Listing with search) | 10 | 1.25 | Option to resubmit Documents
Extension vessel berthing (Listing with search) | 8.5 | 1.0625 | Preformatted emails (Submit, Approve, Reject)
Vessel permit (Listing with search) | 8 | 1 | Permit emailed (PDF version created and mailed)
Safety Services |  |  | customer survey
Bunker permit request | 8 | 1 | export to different file formats
Hot work permit request | 8 | 1
Diving permit process | 8 | 1
Diesel discharge permit | 6 | 0.75
General maintenance permit | 6 | 0.75
Sanitation permit process | 6 | 0.75
Reports (for each service) 10 services (Save as PDF & Excel)
10 Reports. Each having maximum 4 filters | 80 | 10
Report by date range
Report by status
Report using all combination filter
Report despite of date range.
Report by users name
Email attachments reports (PDF Format)
Vessel berthing | 8 | 1
Port clearance/ Sail out | 8 | 1
Extend vessel stay(2) | 8 | 1
Vessel permit to enter Ajman port | 8 | 1
Safety section | 8 | 1
Hot work permit and safety induction | 8 | 1
Diving permit and safety induction | 8 | 1
Diesel discharge permit and safety induction | 8 | 1
General maintenance permit and safety induction | 8 | 1
Sanitation permit and safety induction | 12 | 1.5
User - Administrator
Master entries - both in English and Arabic
Countries, Fees, Agents, Exit Ports, Hot work Fees, | 16 | 2
User Management | 8 | 1
User Role Management | 8 | 1
Manage Requirment docs for services | 16 | 2
Manage Email templates (Approve, Reject, Received) | 8 | 1
Manage Email notification trigger points (10 services - 3 status mails) | 8 | 1
System
Login, forgot password, remember password, Password salting | 8 | 1
Bilingual Site (Includes saving data in Arabic) | 32 | 4
Authentication and Authorization | 4 | 0.5
Auditing and logging | 8 | 1
Email, SMTP | 4 | 0.5
Exception Handling | 4 | 0.5
File management | 4 | 0.5
HTTPS, SSL | 4 | 0.5
QA + UAT | 154.35 | 19.2937
Total | 818.3 | 102.2875
Assumptions
Email attachments / Print outs will be system generated (Not in pre-printed bills).
Bilingual Site - The application will be viewable in both English and Arabic, Data entry can be done either languages.
For e.g. Vessel name entered by the end user will be either in English or Arabic. The entered text will be shown in all refrences of the Vessel name.
The effort may change based on detailed system study

## Sheet2
Removed Features
Refer friend via email (Store Refferals to create email database) with referral bonus (gamification)
Promo Code management(dashboard, Coupon codes, Dates Valid, Distribution list, Discounts, Analytics)
Push Notification Channels( Email, SMS, Web Push, Onsite Personalization: Exit intent)
Context Sensitive Help Within tax Workflow (Hover over text for individual line items and eidtable text that can be managed via CMS)
Social Media Integration (link to FB, Lin, instagram , twitter, pinterest, google)
Promo code distribution
Referral links
Document Archival
Simple + Advanced search (Tax Documents + Site Search)
Save data on back button (Tax Workflow)
Prefill with PAN
Prior Year XML
Foreign income and assets validation : Premium plan
Other Batch Jobs (retry failed returns, Status updates pending failed returns)
End user reports (5 reports max)
Feedback form (Survey)
Values in the form should be saved on navigating to other tabs even without clicking save
Manage Customer Queries ( multi step drop down questions to narrow down common questions that requires human intervention)
Manage Email Templates (clarity required, not sure if this is relevant)
Loyalty Program for returning users (need clarity)
Email Marketing