## Cost_article (Detail Tab)
Form
Attribute | 1toM | Formula | Notes | Cost code | Contract | Payment | Payment Certificate | Change Order request | Change Order
Cost code |  | Type in field |  | x | x | x | N/A | x | x
ContractID |  | Auto |  |  | x | x | N/A | x | x
Currency |  | Select field |  | x | x | x | N/A | x | x
Origin |  | Auto | From which form does it originate. |  |  |  | N/A
UsedInContract |  | Auto | Is it used at least once. |  |  |  | N/A
UsedInPayment |  | Auto | Is it used at least once. |  |  |  | N/A
UsedInChangeOrder |  | Auto | Is it used at least once. |  |  |  | N/A
UsedInMiscelaniousInvoice |  | Auto | Is it used at least once. |  |  |  | N/A
PaymentID | x | Auto |  |  |  | x | N/A
ChangeOrderID | x | Auto |  |  |  | x | N/A |  | x
ChangeRequestID | x | Auto |  |  |  |  | N/A | x
Description |  | Type in field |  | x | x | x | N/A | x | x
Notes1 |  | Type in field |  | x |  |  | N/A
Group1 |  | Type in field |  | x |  |  | N/A
Value1 |  | Type in field |  | x |  |  | N/A
GroupN |  | Type in field |  | x |  |  | N/A
ValueN |  | Type in field |  | x |  |  | N/A
Original value |  | Type in field and default value will be 0.00 |  |  | x |  | N/A
Adjustment |  | Type in field and default value will be 0.00 |  |  | x |  | N/A
Total cost? |  | Original value + Adjustment |  |  | x |  | N/A
Notes2 |  | Type in field |  |  | x |  | N/A
Scheduled Value | x | Coming from Total Cost (Contracts) |  |  |  | x | N/A
Current Invoice | x | Type in field and default value will be 0.00 |  |  |  | x | N/A
Current Invoice after retension | x | Current Invoice - (Retension% * Current Invoice) |  |  |  | x | N/A
Prior invoice | x | It will show the Total Invoiced of the prior Payment |  |  |  | x | N/A
Total invoiced | x | Current Invoice + Prior Invoice |  |  |  | x | N/A
Total Invoiced after retension | x | Total Invoiced - (Retension % * Total Invoiced |  |  |  | x | N/A
% Completed | x | Total Invoiced/Scheduled Value |  |  |  | x | N/A
Balance to Invoice | x | Scheduled Value - Total Invoiced |  |  |  | x | N/A
Notes3 | x | Type in field |  |  |  | x | N/A
Unit cost | x | Type in field and default value will be 0.00 | Only for use and support of CO process. |  |  |  | N/A | x | x
Quantity | x | Type in field and default value will be 0.00 | Only for use and support of CO process. |  |  |  | N/A | x | x
Amount Requested/Total cost???Total cost = Original value in Contract | x | Unit cost * Quantity |  |  |  |  | N/A | x | x
Amount Approved | x | Type in field and default value will be 0.00 | This will reflect on Contract Original value. Can be negative. |  |  |  | N/A |  | x
Notes4 | x | Type in field |  |  |  |  | N/A |  | x
Status? | x | Auto |  |  |  |  | N/A |  | x
Notes5 | x | Auto |  |  |  |  | N/A | x
Cost articles will be used through all of the module
In columns attributes that are used in that form are marked.
1toM: Many are valid at one time for one cost code, each adding partial information until complition. Each set will be connected to specitic form instance.
Note on A22: Miran Matko: I would not save calculated values in DB.
Note on A23: Miran Matko: Is this the same notes as Notes1?

## Cost_contract (Summary Tab)
Cost_contract (Summary Tab)
IMPORTANT: All sums are on contract level (if not specified differently)! There can be several contracts on project.
* If the Payment is against Change Order, then sums are related to Change order (and not Contract) |  |  |  | Form
Attribute | 1toM | Note | Formula | Cost code | Contract | Payment | Payment Certificate | Change Order request | Change Order
Original Contract value |  |  | Sum of the Total Cost value (Contract - Detail Tab, without change orders) |  | x
Approved changes |  |  | Sum of the approved amount from Change Orders. |  | x
Revised Contract Value |  |  | Original Value + Approved Changes |  | x
Pending changes |  |  | Sum of the Change Order values, that are still opened. Not rejected nor approved. |  | x
Billed |  |  | Sum of Total Invoiced (Payment form - Detail Tab) for Contract and |  | x
Un Billed |  |  | Revised Value - Billed |  | x
Projected Value |  |  | Revised Value + Pending changes |  | x
Original Contract value |  |  | Sum of the Total Cost value (Contract - Detail Tab, without change orders) |  |  | x
Approved changes |  |  | Sum of the approved amount from Change Orders. |  |  | x
Revised Contract Value |  |  | Original Value + Approved Changes |  |  | x
Invoiced |  | * | Sum of Total Invoiced (Payment form - Detail Tab) |  |  | x
Current Invoice |  | * | Sum of Current Invoice (Payment form - Detail Tab) |  |  | x
Balance to Finish |  | * | Sum of Balance To Invoice (Payment form - Detail Tab) |  |  | x
Original Contract value |  |  | Sum of the Total Cost value (Contract - Detail Tab, without change orders) |  |  |  | x
Approved changes |  |  | Sum of the approved amount from Change Orders. |  |  |  | x
Revised Contract Value |  |  | Orginal Contract + Approved Changes |  |  |  | x
Previous Value of Work done |  | * | Sum of Prior Invoice (Payment form - Detail Tab), excluding current linked Payment. Suppose we have selected Payment No 10 in Payment Certificate then, sum will refer to Payment No 9 Prior Invoice amount |  |  |  | x
Total Value of Work Done |  | * | Sum of Total Invoice (Payment form - Detail Tab), including current Payment. Suppose we have selected Payment No 10 in Payment Certificate then, sum will refer to Payment No 10 Total Invoice amount |  |  |  | x
Total Value of This Period |  | * | Total Value of Work Done - Previous Value of Work Done |  |  |  | x
With 9% Dedcution |  | * | Total Value of This Period * (1-0.09); Note: Deduction could in the future variable on project level |  |  |  | x
Less Retention |  | * | (Percentage input in Contract form under Retention field) * With 9% Dedcution |  |  |  | x
Original Contract value |  |  | Sum of the Total Cost value (Contract - Detail Tab, without change orders) | [5 empty] | x
Amount Requested |  |  | Sum of Amount Requested field for the current Change Order | [5 empty] | x
Prior Approved Changes |  |  | Sum of the approved amount from Change Orders. | [5 empty] | x
Total of This Changes |  |  | Sum of the Amount Approved for the current Change Order | [5 empty] | x
Prior Revised Contract value |  |  | Original Value + Prior Approved Changes | [5 empty] | x
Contract with Changes |  |  | Prior Revised Contract + Total Of This Changes | [5 empty] | x
Original Contract value |  |  | Sum of the Total Cost value (Contract - Detail Tab, without change orders) |  |  |  |  | x
Approved Changes |  |  | Sum of the approved amount from Change Orders. |  |  |  |  | x
Amount Requested |  |  | Sum of Amount Requested field for the current linked Change Order |  |  |  |  | x
Revised Contract Value |  |  | Original Changes + Approved Changes |  |  |  |  | x