## Version
Version | Date | Creator | Notes
1.0 | 2016-07-24 | Miran Matko | Handover
1.01 | 2016-07-28 | Miran Matko | Minor changes to List actions
1.02 | 2016-08-17 | Miran Matko | Updated Mapping sheet

## General
# | Entity | Attribute | Buisness Rule (message) | Buisness Rule (note) | TypeError | Code list
| General | Group |  | Procurement | Info
| General | Form name |  | Vendor Register | Info
| General | Acroynm |  | VendR | Info
| General | Description |  | Monitoring vendor performance, and ensuring that contract terms are followed. Helps to ensure that the supplier delivers the expected goods and services at the right place and the right time. | Info
| General | Creactor |  | Procurement Dept | Info
| General | Recipient |  | N/A | Info
| General | Edit |  | Yes | Info
| General | Delete |  | Yes | Info
| General | Draft |  | Yes | Info
| General | Contextual help |  | No | Info
| General | Localization |  | No | Info
| General | Export |  | Yes | Info
| General | Transmittal letter |  | Yes | Info
| General | Attachments |  | Yes | Info

## Form
# | Entity | Attribute | Buisness Rule (message) | Buisness Rule (note) | Type | Code list
| Planned | Production Lead Time | FCA Date - PO Placement Actual (From Procurement Register) |  | Calc
| Planned | Shipping Period | Date On Site - PO Placement Actual (From Procurement Register) |  | Calc
| Planned | FCA Date | Date from P6 corresponding ID field | See Mapping | Info
| Planned | Date On Site | Date from P6 corresponding ID field | See Mapping | Info
| Forecast | FCA Date | PO Placement Actual (From Procurement Register) + Production Lead Time |  | Calc
| Forecast | Date on Site | FCA Date + Shipping Period |  | Calc

## List actions
List actions allowed for:
User | Action allowed
| View | Edit | Respond | Delete | Draft
Creator | x | x |  | x | x
Recipient
Manager | x
Everybody else on project
* check cell comments
Note on E4: IEAG: Only active if received a response and the user has not yet responded.
Note on F4: IEAG: Not active if responses exist.
Note on G4: Miran Matko: Active if a draft from user exists
Note on E5: IEAG: Active if: - received a response and the user has not yet responded. - if there is a response from user and there is no response from others -> in this case the user will modify his last response Not active in other situation.
Note on G5: Miran Matko: Active if a draft from user exists

## Code lists
N/A

## Mapping
Base Form
| Procurement Register |  | Vendor Register
Section | Field |  | Field | Section
Body | Package | to | Description | Body
Actual | PO# | to | PO# | Body
Actual | PO Placement | to | For calculation | N/A
Planned Field Se(Mapping rules)
* It is integrated with Primavera P6 Base schedule
| Vendor Register |  | P6 Schedule
Section | Field |  | Field | Section
Planned | FCA Id | from | Manifacutring & Transportation | Base schedule
Planned | Date On Site Id | from | Materials required at site | Base schedule
Forecast/Actual Field Set (Mapping rules)
* It is integrated with Primavera P6 Update schedule
** When Actual value is filled then Actual value transfers to P6 Schedule. (even if Forecast is filled)
*** When Forecast values is filled and Actual value is NULL then Forecast value will transfers to P6 Schedule.
| Procurement Register |  | P6 Schedule
Section | Field |  | Field | Section
Forecast/Actual | FCA Id | to | Manifacutring & Transportation | Updated schedule
Forecast/Actual | Date On Site Id | to | Materials required at site | Updated schedule

## Export
Export function will pull the list as well the View fields
SL No | Revision | Drawing number | … other line fields | Date of Issue | …other revision fields