## Version
Version | Date | Creator | Notes
1.0 | 2016-07-24 | Miran Matko | Handover

## General
# | Entity | Attribute | Buisness Rule (message) | Buisness Rule (note) | TypeError | Code list
| General | Group |  | Procurement | Info
| General | Form name |  | Procurement Register | Info
| General | Acroynm |  | ProcR | Info
| General | Description |  | It allows the user to keep a record of all goods and services requested from suppliers, through out the project life cycle of the purchasing process up to PO placement. | Info
| General | Creactor |  | Procurement Dept | Info
| General | Recipient |  | N/A | Info
| General | Edit |  | Yes | Info
| General | Delete |  | Yes | Info
| General | Draft |  | Yes | Info
| General | Contextual help |  | No | Info
| General | Localization |  | No | Info
| General | Export |  | Yes | Info
| General | Transmittal letter |  | Yes | Info
| General | Attachments |  | No | Info

## Form
# | Entity | Attribute | Buisness Rule (message) | Buisness Rule (note) | Type | Code list
| Planned | Complete Of CBA | Complete of TBA + 5 days |  | Calc
| Planned | Approved BID | Complete Of CBA + 2 days |  | Calc
| Planned | MR To Procurement | Enquiry Issued - 2 days |  | Calc
| Planned | Enquiry Issued | Date for corresponding P6 ID field | See Mapping | Info
| Planned | BIDs Received | Date for corresponding P6 ID field | See Mapping | Info
| Planned | BIDs Opened | Date for corresponding P6 ID field | See Mapping | Info
| Planned | Issued for Technical Review | Date for corresponding P6 ID field | See Mapping | Info
| Planned | Complete of TBA | Date for corresponding P6 ID field | See Mapping | Info
| Planned | PO Placement | Date for corresponding P6 ID field | See Mapping | Info
| Planned | PO Placement Total float | Total float for corresponding P6 ID field | See Mapping | Info
| Forecast | Enquiry Issued | MR To Procurement + 2 Days |  | Info
| Forecast | BIDs Received | Enquiry Issued + 17 Days |  | Calc
| Forecast | BIDs Opened | BIDS Received + 2 Days |  | Calc
| Forecast | Issued For Technical Review | BIDs Opened + 1 Days |  | Calc
| Forecast | Complete Of TBA | Issued For Technical Review + 7 Days |  | Calc
| Forecast | Complete Of CBA | Complete Of TBA + 5 Days |  | Calc
| Forecast | Approved BIDs | Complete Of CBA + 2 Days |  | Calc
| Forecast | PO Placement | MR To Procurement + 1 days |  | Calc
| Actual | BIDs Opened | Due date of RFQ/RFP if it is in the past | It is updated when opening the form or once a day | Info
| Actual | Issued for TechnicalReview | Begining of BID Assessment in BIDSS | It is updated when opening the form or once a day | Info
| Actual | Complete of TBA | When starting CBA from TBA | It is updated when opening the form or once a day | Info
| Actual | Complete of CBA | When awarding the contract in CBA | It is updated when opening the form or once a day | Info
| Actual | PO Placement | PO Placement Date will be updated taking the Awarded date value from Cost BID. | It is updated when opening the form or once a day | Info
| Actual | PO# | PO# field will be updated from PO# field in CBA. | It is updated when opening the form or once a day | Info

## List actions
List actions allowed for:
User | Action allowed
| View | Edit | Respond | Delete | Draft
Creator | x | x |  | x | x
Recipient
Manager | x
Everybody else on project | x
* check cell comments

## Code lists
N/A

## Mapping
Planned Field Set (Mapping rules)
* It is integrated with Primavera P6 on project level
** In this case Bsse schedule will be revised and added activites and updated dates will be transfered to the same structure in IEAG platform, from where the date will be used.
| Procurement Register |  | P6 Schedule
Section | Field |  | Field | Section
Planned | Enquiry Issued Id | from | Folder forwarded by Project Dept to procurement | Base schedule
Planned | BIDS Received Id | from | Reciepit of qoutation | Base schedule
Planned | BIDS Opened Id | from | Finalisation by Procure.Dep't | Base schedule
Planned | Issued For Technical Review Id | from | Submission of Supplier to Client | Base schedule
Planned | Complete of TBA ID | from | Approval of supplier | Base schedule
Planned | PO Placement Id | from | Placement of Purchase order | Base schedule
Planned | Enquiry Issued (date) | from | Folder forwarded by Project Dept to procurement (date) | Base schedule
Planned | BIDs Received (date) | from | Reciepit of qoutation (date) | Base schedule
Planned | BIDs Opened (date) | from | Finalisation by Procure.Dep't (date) | Base schedule
Planned | Issued for Technical Review (date) | from | Submission of Supplier to Client (date) | Base schedule
Planned | Complete of TBA (date) | from | Approval of supplier (date) | Base schedule
Planned | PO Placement (date) | from | Placement of Purchase order (date) | Base schedule
Planned | PO Placement (total float) | from | Placement of Purchase order (total float) | Base schedule
Forecast/Actual Field Set (Mapping rules)
* It is integrated with Primavera P6 Update schedule
** When Actual value is filled then Actual value transfers to P6 Schedule. (even if Forecast is filled)
*** When Forecast values is filled and Actual value is NULL then Forecast value will transfers to P6 Schedule.
| Procurement Register |  | P6 Schedule
Section | Field |  | Field | Section
Forecast/Actual | Enquiry Issued (date) | to | Folder forwarded by Project Dept to procurement (date) | Updated schedule
Forecast/Actual | BIDs Received (date) | to | Reciepit of qoutation (date) | Updated schedule
Forecast/Actual | BIDs Opened (date) | to | Finalisation by Procure.Dep't (date) | Updated schedule
Forecast/Actual | Issued for Technical Review (date) | to | Submission of Supplier to Client (date) | Updated schedule
Forecast/Actual | Complete of TBA (date) | to | Approval of supplier (date) | Updated schedule
Forecast/Actual | PO Placement (date) | to | Placement of Purchase order (date) | Updated schedule

## Export
N/A

## Import
N/A