## Sheet1
Activity | Hours | Days
Planning Phase |  |  | Resource | No. | Days | Tot. Days
Business Analysis | 16 | 2 | Business Analysis | 1 | 2 | 2
Documentation | 16 | 2 | Documentation | 1 | 2 | 2
Project Management | 16.2 | 2.025 | UI / UX | 1 | 3 | 3
Design (UI/UX) | 24 | 3 | PM | 1 | 2.025 | 2.025
Development |  |  | Developer | 1.5 | 19.5 | 29.25 | 29.25
ERP |  | 0 | QA | 1.5 | 10.1083 | 15.1625
Enquiry | 8 | 1 | Total Effort (WEB) |  |  | 53.4375
Site Survey (Predefined) | 8 | 1
Proposal: Quotations linked to enquiry | 12 | 1.5 | Application Delivery Days | 31.6333
Contracts: Slaes order linked to Proposal | 12 | 1.5
Invoice linked to contracts | 12 | 1.5 | Mobile development (IOS) | 10
Purchase Order with approvals (one level) | 12 | 1.5 | Mobile development (Android) | 10
Customer Master Data | 8 | 1
Supplier Master data | 8 | 1
Customer Portal |  | 0
360 degree view of orders | 16 | 2
Online notifications and approvals | 8 | 1
Incident reports | 8 | 1
Escalations | 8 | 1
Employee Self Serve Portal |  | 0
Visa Renewal Date | 6 | 0.75
Labour card renewal date | 6 | 0.75
Passport renewal date | 6 | 0.75
Driving license renewal date | 6 | 0.75
Lifeguard security license renewal | 6 | 0.75
Leave requests | 6 | 0.75
Vacation requests | 6 | 0.75
System |  | 0
Work flow management | 16 | 2
Authentication and authorization | 6 | 0.75
Auditing & Logging | 6 | 0.75
Exception Management | 6 | 0.75
Manage master data | 6 | 0.75
API for mobile app | 32 | 4
QA
QA | 105.3 | 13.1625
UAT | 8 | 1
Deployment | 8 | 1
Total | 427.5 | 53.4375

## Sheet2
Activity | Hours | Days
Planning Phase
Business Analysis | 0 | 0
Documentation | 0 | 0
Project Management | 0 | 0
Design (UI/UX) | 0 | 0
Development |  | 0
Mobile App |  | 0
Check in / Check out | 8 | 1
Geo fence | 8 | 1
QR code for work order | 8 | 1
Incident report | 8 | 1
SOS button | 6 | 0.75
Upload pictures / Vide / voice | 6 | 0.75
Report Lost & found | 6 | 0.75
Report Injury related incidents | 8 | 1
Fire Alarm | 8 | 1
Design (Developer) | 16 | 2
Total | 82 | 10.25