## Telephone Bill System
Telephone Bill System |  | 2019-04-20
Saturday
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Designer | 1 | 10 | 10
Business Analysis | 24 | 3 | Sr Developer | 1 | 16 | 16 | 8.5 | 39.78 | 30 | 36
Project Management | 30.24 | 3.78 | Jr Developer | 1 | 20 | 20
Design and Prototype | 80 | 10 | PM | 1 | 3.78 | 3.78
Documentation (SRS, FS, Weekly Reports, User Manual) | 48 | 6 | BA | 1 | 3 | 3
Development |  |  | TechWriter | 1 | 6 | 6
Application Basic Setup | 8 | 1 | QA | 1 | 10.8 | 10.8
Login
Active Directory | 16 | 2 | Total |  | 69.58 | 0
User Phase |  |  | Total Delivery days | 40.8
Dashboard | 16 | 2
Call list | 8 | 1
Additional: Feature.. To mark personal calls and official calls | 12 | 1.5
Call History | 8 | 1 | Total Effort | 0 | (+1 Day deployment)
Administrator Phase
Dashboard | 16 | 2
Upload Bills (Extract bills) | 20 | 2.5
Call List update | 12 | 1.5
View Pending bills [Monthwise Pending bills that were not submitted by the user] | 20 | 2.5
Processed list Management | 8 | 1
Cost Centre Management | 8 | 1
Manage Employees (Get User, Search) | 12 | 1.5
Manage IP extensions | 8 | 1
Extract IPBAX (OR IP-phone server) file and Map with Telecome bill records | 32 | 4
Reports (3)
Cost Centre Report | 12 | 1.5
Employee Report for Bill Payment | 12 | 1.5
Bill Status Report | 12 | 1.5
Quality Assurance
QA & Bug Fixing | 86.4 | 10.8
UAT | 32 | 4
Deployment per instance | 16 | 2
Total Effort |  | 69.58
Assumptions
The effort might change after a detailed system study
The sample format for extraction of bills and PBX records will be provided during the system study
Please check if the client use AD for authentication/ Or we might need to do the usermanagement