## Maestro
Maestro |  | Apr 1 2019
Monday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 12 | 1.5 | Designer | 1 | 32 | 4 | 4
Functional Specification | 8 | 1 | Web Developer | 1 | 213 | 26.625 | 26.625 | 33.625 | 26.625
Project Management | 22.9 | 2.8625 | PM | 1 | 42.9 | 5.3625 | 5.3625
Graphic Design | 16 | 2 | QA | 2 | 42.35 | 5.2938 | 10.5875
Working Prototype | 16 | 2 | Total |  | 330.25 |  | 46.575
Development | [7 empty] | 372.6
Offline Ticket purchase |  |  | Total Delivery days | 35.9188
Collect Information about customer | 8 | 1 | Total Man day Effort | 46.575
integration with DTCM | 8 | 1
Print tickets | 8 | 1
Online ticket purchase |  | 0
Collect Information about customer | 4 | 0.5
Generate event links | 4 | 0.5
Share links | 8 | 1
Ticket payment | 8 | 1
Download e-tickets | 8 | 1
Barcode generation | 8 | 1
Ticketing Administration |  | 0
Ticket administration | 8 | 1
Event creation | 8 | 1
Group administration | 8 | 1
Ticket prices | 8 | 1
Ticket discount plans | 8 | 1
User Administration |  | 0
Users and roles | 8 | 1
API Integration |  | 0
50 service endpoints @ 2.5 hours per service call | 125 | 15.625
System features |  | 0
Authentication & authorization | 8 | 1
Auditing & logging | 8 | 1
Exception handling | 8 | 1
Manage files and directories | 8 | 1
Testing & Deployment
Testing | 68.7 | 8.5875
UAT | 8 | 1
Deployment | 8 | 1
Total Effort | 428.6 | 53.575
Assumptions
The application will be a responsive web application